## 14-15
Cost Center | School Name | Year Open | Request Dept | Assigned Dept | Lg Cap Project | In-House Maint Prj | MUNIS | Concatenate | Project Description | Priority | Bgt Yr | FUND | AMT | Rev Priority | Type | Budget Estimate | Adjusted Estimate | Final Cost | Status | Notes
0901 | Anclote ES | 1973 | PRT | MAINT |  |  | 85200 | 852000901 | Roof Replacement | 1 | 13/14 | 3101 3611 | 405000 | 1 |  | 405000 | 405000 |  | Design Requisition
0932 | Calusa ES | 1979 | PRT | MAINT |  |  | 84045 | 840450932 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 100000 | 100000 |  | Complete
0069 | Centennial MS | 2001 | PRT | CS&CC |  |  | 85190 | 851900069 | EHPA Generator Shelter | 1 | 13/14 | 3712 | 50000 | 1 |  | 60000 | 60000 |  | Roll | Well and Sanitary Lift coded to Centennial ES 0401
0069 | Centennial MS | 2001 | FNS | MAINT |  |  | 84070 | 840700069 | Cooler/Freezer Flooding | 1 | 13/14 |  |  | 1 |  | 70000 | 70000 |  | Complete
0069 | Chasco MS | 2001 | PRT | MAINT |  |  | 85200 | 852000069 | Replace Gutters | 1 | 13/14 | 3101 | 91776 | 1 |  | 91250 | 91250 |  | Complete
0311 | Cotee River ES | 1993 | PRT | MAINT |  |  | 85250 | 852500311 | Roof Replacement | 1 | 13/14 | 3611 | 700000 | 1 |  | 700000 | 700000 |  | In Progress
0311 | Cotee River ES | 1993 | PRT | MAINT |  |  | 84045 | 840450311 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 100000 | 100000 |  | Complete
0059 | Denham Oaks ES | 1994 | PRT | MAINT |  |  | 84045 | 840450059 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 100000 | 100000 |  | In Progress
9053 | District Complex | 1974 | PRT | CS&CC | Yes |  | 86100 | 861009053 | District Complex - Building 2 Architectural Design | 1 | 13/14 | 3900 | 300000 | 1 |  | 300000 | 300000 |  | In Progress
9053 | District Complex |  | PRT | CS&CC | Yes |  | 86100 | 861009053 | District Complex - Building 4 Remodel/Expansion | 1 | 13/14 | 3900 | 6748473 | 1 |  | 6511000 | 6511000 |  | Roll | $400,000 for furniture
9002 | District Wide |  | ATH | MAINT |  |  | 83240 | 832409002 | Annual ADA Compliance/Bleacher Retrofit | 1 | 13/14 | 3611 | 50000 | 1 |  | 50000 | 50000
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 1 | 13/14 | 3709 | 150000 | 1 |  | 150000 | 150000
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 1 | 13/14 | 3710 | 100000 | 1 |  | 100000 | 100000
9031 | District Wide |  | FIN | FIN |  |  | 84210 | 842109031 | Annual Buses | 1 | 13/14 | 3714 | 1500000 | 1 |  | 1700000 | 1700000
9061 | District Wide |  | FIN | FIN |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 1 | 13/14 | 3709 | 202000 | 1 |  | 202000 | 202000
0000 | District Wide |  | FIN | FIN |  |  | 00000 | 000000000 | Annual Debt Service Payments | 1 | 13/14 | 3714 3903 3921 | 34821519 | 1 |  | 38816856 | 38816856
9002 | District Wide |  | MAINT | MAINT |  |  | 85000 | 850009002 | Annual Emergency Renovations & Remodeling | 1 | 13/14 | 3714 | 500000 | 1 |  | 500000 | 500000
9061 | District Wide |  | MAINT | MAINT |  |  | 85500 | 855009061 | Annual Energy Retrofits | 1 | 13/14 | 3611 | 100000 | 1 |  | 100000 | 100000
9061 | District Wide |  | PRT | MAINT |  |  | 85160 | 851609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 1 | 13/14 | 3709 | 725000 | 1 |  | 725000 | 725000
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 1 | 13/14 | 3709 | 200000 | 1 |  | 200000 | 200000
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 1 | 13/14 | 3709 | 250000 | 1 |  | 500000 | 500000
9012 | District Wide |  | FIN | FIN |  |  | 83240 | 832409012 | Annual FISH Signage | 1 | 13/14 | 3711 | 10000 | 1 |  | 10000 | 10000
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | 851209061 | Annual Flooring Replacement ($300,000 Annually) | 1 | 13/14 | 3713 | 150000 | 1 |  | 150000 | 150000
9430 | District Wide |  | ATH | MAINT |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 1 | 13/14 | 3708 | 60000 | 1 |  | 60000 | 60000
9021 | District Wide |  | FIN | FIN |  |  | 80010 | 800109021 | Annual Habitat for Humanity | 1 | 13/14 | 3904 | 100000 | 1 |  | 100000 | 100000
9002 | District Wide |  | PRT | MAINT |  |  | 85110 | 851109002 | Annual HVAC Equipment Replacements ($250,000 Annually) | 1 | 13/14 | 3712 | 250000 | 1 |  | 250000 | 250000
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 1 | 13/14 | 3709 | 100000 | 1 |  | 100000 | 100000
9061 | District Wide |  | FIN | FIN |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 1 | 13/14 | 3709 | 1212000 | 1 |  | 1212000 | 1212000
9061 | District Wide |  | FIN | FIN |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 1 | 13/14 | 3709 | 202000 | 1 |  | 202000 | 202000
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 1 | 13/14 | 3711 | 15000 | 1 |  | 15000 | 15000
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 1 | 13/14 | 3712 | 350000 | 1 |  | 350000 | 350000
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 1 | 13/14 | 3714 | 200000 | 1 |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 1 | 13/14 | 3709 | 295000 | 1 |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms ($100,000 Annually) | 1 | 13/14 | 3708 | 100000 | 1 |  | 100000 | 100000
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 1 | 13/14 | 3713 | 75000 | 1 |  | 75000 | 75000
9002 | District Wide |  | MAINT | MAINT |  |  | 81150 | 811509002 | Annual Storage Buildings | 1 | 13/14 | 3712 | 15000 | 1 |  | 15000 | 15000
9420 | District Wide |  | OTIS | OTIS |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 1 | 13/14 |  |  | 1 |  | 7785000 | 7785000
9421 | District Wide |  | FIN | FIN |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 1 | 13/14 | 3713 | 800000 | 1 |  | 800000 | 800000
9009 | District Wide |  | FIN | FIN |  |  | 84500 | 845009009 | ERP System | 1 | 13/14 | 3900 | 8854577 | 1 |  | 4777563 | 4777563
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | 860009002 | Property Acquisition - Elementary School Site in North Land O' Lakes area | 1 | 13/14 | 3904 | 1500000 | 1 |  | 750000 | 750000 |  | Roll | Need to increase to $1.5 mill
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | 860009002 | Property Acquisition - Elementary "B" Site in 54 Corridor in Odessa Area | 1 | 13/14 | 3904 | 2500000 | 1 |  | 2200000 | 2200000 |  | Roll | Added for 2nd elementary site - Bexley Ranch
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | 860009002 | Property Acquisition - Elementary Site in 54 Corridor in Odessa Area - Elem "Q" | 1 | 13/14 | 3904 | 2200000 | 1 |  | 2200000 | 2200000 |  | Complete
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | 860009002 | Property Acquisition - High School Site in 54 Corridor in Odessa Area | 1 | 13/14 | 3904 | 1000000 | 1 |  | 2600000 | 2600000 |  | Roll
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | 860009002 | Property Acquisition - If land becomes available next to existing school sites | 1 | 13/14 | 3904 | 1000000 | 1 |  | 250000 | 250000 |  | Roll
0000 | District Wide |  | FIN | FIN |  |  | 00000 | 000000000 | Property Insurance | 1 | 13/14 | 3714 | 827000 | 1 |  | 827000 | 827000
6997 | Energy Marine Center |  | MAINT | MAINT |  |  | 85200 | 852006997 | Roof Maintenance | 1 | 13/14 | 3101 | 60000 | 1 |  | 60000 | 60000 |  | Summer
0351 | Fox Hollow ES | 1990 | FNS | CS&CC |  |  | 85250 | 852500351 | Serving Line Renovation | 1 | 13/14 | 3713 | 194596 | 1 |  | 194596 | 194596 |  | In Progress
0331 | Gulf HS | 1971 | FNS | CS&CC |  |  | 84070 | 840700331 | Cooler / Freezer | 1 | 13/14 | 3709 |  | 1 |  | 9879 | 9879 |  | Summer
0331 | Gulf HS | 1971 | PRT | CS&CC | Yes |  | 85110 | 851100331 | HVAC Hydronic Boiler Replacement | 1 | 13/14 | 3709 3711 | 322281 | 1 |  | 330203 | 330203 | 150000 | Out for Bid
0331 | Gulf HS | 1971 | PRT | MAINT |  |  | 84045 | 840450331 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 150000 | 150000 |  | Roll
0093 | Gulf Trace ES | 2008 | PRT | CS&CC |  |  | 86110 | 861100093 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3710 3711 3712 3713 3902 | 582703 | 1 |  | 90576 | 90576 |  | Complete | Need addl funding - $165,000 more than original $490,000
0911 | Gulfside ES | 1977 | PRT | MAINT |  |  | 85200 | 852000911 | Roofing Maintenance | 1 | 13/14 | 3101 | 60000 | 1 |  | 60000 | 60000 |  | Material Bid @ Purchasing
0242 | Harry Schwettman EC | 1923 | PRT | MAINT |  |  | 85200 | 852000242 | Roof Coating | 1 | 13/14 | 3101 | 40000 | 1 |  | 40000 | 40000
0951 | Hudson MS | 1984 | FNS | CS&CC |  |  | 85250 | 852500951 | Kitchen & Serving Line Renovation | 1 | 13/14 | 3108 3713 | 995273 | 1 |  | 222769 | 222769 |  | Complete
0073 | J.W. Mitchell HS | 2000 | FNS | CS&CC |  |  | 85250 | 852500073 | Kitchen Renovation - Phase 2 | 1 | 13/14 | 3611 3709 | 1859973 | 1 |  | 1343003 | 1343003 |  | Complete
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT |  |  | 82050 | 820500073 | Overlay Courts - Tennis | 1 | 13/14 | 3711 | 35000 | 1 |  | 35000 | 35000 |  | Complete
7071 | James Irvin EC | 1995 | PRT | MAINT |  |  | 86110 | 861107071 | Sign Relocation/Replacement | 1 | 13/14 |  |  | 1 |  |  |  |  | Budget being determined | Due to SR 52 DOT work
0321 | Lacoochee ES | 1971 | FNS | FNS |  |  | 86100 | 861000321 | Remodel - Add Multi-purpose Space | 1 | 13/14 | 3709 | 10000 | 1 |  | 10000 | 10000 |  | Complete
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82050 | 820500801 | Replace Gym Floor | 1 | 13/14 | 3708 | 71605 | 1 |  | 16093 | 16093 |  | Complete
0801 | Land O' Lakes HS | 1973 | PRT | MAINT |  |  | 85200 | 852000801 | Roof Maintenance - SMS | 1 | 13/14 | 3101 | 100000 | 1 |  | 100000 | 100000 |  | Roll
9061 | Maintenance Dept Building |  | PRT | MAINT |  |  | 85200 | 852009061 | Roofing Maintenance | 1 | 13/14 | 3713 | 25000 | 1 |  | 25000 | 25000 |  | Roll
0451 | Mary Giella ES | 1989 | PRT | MAINT |  |  | 84045 | 840450451 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 100000 | 100000 |  | Complete
0081 | Moore Mickens EC | 1952 | MAINT | MAINT |  |  | 85200 | 852000081 | Roof Repair - Building 1 Metal Roof | 1 | 13/14 | 3101 | 60000 | 1 |  | 60000 | 60000
0501 | Northwest ES | 1973 | PRT | FOSM |  |  | 85110 | 851100501 | HVAC Redesign/Replacement Fan Coil Units - ESE Bld #4 | 1 | 13/14 | 3714 | 400000 | 1 |  | 400000 | 400000 |  | roll
0031 | Pasco HS | 1964 | ATH | MAINT | Yes |  | 82020 | 820200031 | Booster Concession Stand and Restrooms | 1 | 13/14 |  |  | 1 |  | 50000 | 50000 |  | In Design | Community Project / Donation
0031 | Pasco HS | 1964 | PRT | CS&CC | Yes |  | 86100 | 861000031 | Master Plan Redevelopment - Finish Road/Retaining Wall | 1 | 13/14 | 3903 | 330487 | 1 | Penny/Intrl | 385148 | 385148 | 250000 | In Progress
0921 | Pine View MS | 1977 | PRT | FOSM | Yes |  | 85110 | 851100921 | HVAC Renovation Design | 1 | 13/14 | 3611 | 200000 | 1 |  | 200000 | 200000
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  | 86100 | 861000102 | Remodel Bld #4 #5 (Media And ESE) | 1 | 13/14 | 3903 |  | 1 |  | 1496472 | 1496472 |  | Complete | Combined with Gym Replacement in Priority 1
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  | 86100 | 861000102 | Replace Gym Bld #3 - Phase 1 | 1 | 13/14 | 3903 | 5547405 | 1 |  | 1400000 | 1400000 |  | Complete
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  | 86100 | 861000102 | Replace Gym Bld #3 - Phase 2 | 1 | 13/14 | 3903 |  | 1 |  | 1750000 | 1750000 |  | Complete | Need $1.4 million additional
0271 | Richey ES | 1958 | PRT | CS&CC |  |  | 86100 | 861000271 | Campus Redevelopment - Master Plan | 1 | 13/14 | 3900 3904 | 1761576 | 1 | Imp/Intrl | 760236 | 760236 |  | Complete
0471 | River Ridge HS | 1990 | FNS | CS&CC |  |  | 85250 | 852500471 | Cafeteria Renovation - Phase 2 | 1 | 13/14 | 3611 3713 | 1866305 | 1 |  | 1086115 | 1086115 |  | Complete
0471 | River Ridge HS | 1990 | ATH | CS&CC |  |  | 82020 | 820200471 | Concession Stand Bathrooms - Baseball/Softball | 1 | 13/14 | 3710 | 280102 | 1 |  | 100000 | 100000 |  | Complete
0471 | River Ridge HS | 1990 | PRT | CS&CC | Yes |  | 85110 | 851100471 | HVAC Renovation (controls) | 1 | 13/14 | 3900 | 493880 | 1 |  | 493880 | 493880 |  | Roll
0201 | Sanders Memorial ES | 1944 | PRT | CS&CC | Yes |  | 86100 | 861000201 | Campus Redevelopment | 1 | 13/14 | 3900 3904 | 15718272 | 1 |  | 16902130 | 16902130 |  | Open 2015 | Site Work Completed
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  | 86100 | 861000341 | Replacement Bldg #1 - Phase 1 | 1 | 13/14 | 3900 |  | 1 | Interlocal | 6984000 | 6984000 |  | Summer
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  | 86100 | 861000341 | Replacement Bldg #1 - Phase 2 | 1 | 13/14 | 3900 | 13793027 | 1 |  | 6520000 | 6520000 |  | Roll
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  | 86100 | 861000341 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3900 | 432000 | 1 |  | 432000 | 432000 |  | Roll
0057 | Seven Springs MS | 1995 | ATH | MAINT |  |  | 82050 | 820500057 | Basketball Court/Tennis Overlay | 1 | 13/14 | 3711 | 18635 | 1 |  | 6366 | 6366 |  | Complete
0057 | Seven Springs MS | 1995 | FNS | FNS |  |  | 84070 | 840700057 | Cooler / Freezer | 1 | 13/14 | 3709 | 18819 | 1 |  | 184638 | 184638 |  | Summer
0057 | Seven Springs MS | 1995 | PRT | CS&CC |  |  | 85110 | 851100057 | HVAC Chiller Pipe Replacement | 1 | 13/14 | 3611 | 721373 | 1 |  | 68774 | 68774 |  | Complete
0057 | Seven Springs MS | 1995 | PRT | MAINT |  |  | 84048 | 840480057 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 125000 | 125000 |  | Complete
0601 | Shady Hills ES | 1973 | PRT | CS&CC |  |  | 86100 | 861000601 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3709 3710 | 49972 | 1 |  | 28577 | 28577 |  | Design
0101 | Sunlake HS | 2007 | ATH | MAINT |  |  | 82020 | 820200101 | Add Air Conditioning To Field House | 1 | 13/14 | 3708 3710 3711 3713 | 109416 | 1 |  | 6108 | 6108 |  | Complete
0461 | Thomas E. Weightman MS | 1990 | PRT | MAINT |  |  | 84045 | 840450461 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 125000 | 125000 |  | Roll
9035 | Transportation NW | 1979 | PRT | CS&CC |  |  | 86110 | 861109035 | Retention Pond and Flooding Repairs | 1 | 13/14 | 3713 | 56662 | 1 |  | 18891 | 18891 |  | Complete | Flooding issue as a result of Tropical Storm Debby. Need additional money another $90,000
9038 | Transportation SE |  | PRT | CS&CC |  |  | 86110 | 861109038 | Retention Pond and Flooding Repairs | 1 | 13/14 | 3713 | 58745 | 1 |  | 48713 | 48713 |  | Complete | Retention pond overflowing to neighboring property
9039 | Transportation SW |  | PRT | CS&CC |  |  | 86110 | 861109039 | Pre-Installation of Utilities | 1 | 13/14 | 3611 | 195000 | 1 |  | 218000 | 218000 |  | Roll | Install Utilities while Interlaken Road being constructed
0032 | Trinity ES | 2000 | FNS | MAINT |  |  | 85250 | 852500032 | Renovate Kitchen Floors | 1 | 13/14 | 3709 3711 | 84881 | 1 |  | 57881 | 57881 |  | Roll
0032 | Trinity ES | 2000 | MAINT | MAINT |  |  | 85200 | 852000032 | Replace Gutters | 1 | 13/14 | 3103 | 50000 | 1 |  | 50000 | 50000 |  | Roll
0085 | Trinity Oaks ES | 2007 | PRT | CS&CC |  |  | 85110 | 851100085 | Add Dehumidification | 1 | 13/14 | 3709 3711 | 74148 | 1 |  | 1006 | 1006 |  | Complete
0063 | Wesley Chapel HS | 1998 | ATH | MAINT |  |  | 82020 | 820200063 | Add Air Conditioning To Field House | 1 | 13/14 | 3709 33710 3711 | 106499 | 1 |  | 6053 | 6053 |  | Complete
0063 | Wesley Chapel HS | 1998 | CCTE | CS&CC |  |  | 85240 | 852400063 | Career Academy - Automotive | 1 | 13/14 | 3712 | 43499 | 1 |  | 16416 | 16416 |  | Complete | Carry Forward from 12/13
0063 | Wesley Chapel HS | 1998 | ATH | ATH |  |  | 82040 | 820400063 | Scoreboard Replacement(s) | 1 | 13/14 |  |  | 1 |  | 75000 | 75000 |  | Complete
0091 | West Zephyrhills ES | 1958 | MAINT | MAINT |  |  | 85200 | 852000091 | Roof Replacement - Cafeteria and Media | 1 | 13/14 | 3101 | 301220 | 1 |  | 301220 | 301220 |  | Roll
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT |  |  | 82020 | 820200090 | Add Air Conditioning To Field House | 1 | 13/14 | 3708 3710 3711 | 106607 | 1 |  | 6162 | 6162 |  | Complete
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC | Yes |  | 86110 | 861100090 | Traffic Light @ Mansfield | 1 | 13/14 | 3611 | 125000 | 1 |  | 125000 | 125000 |  | Roll | Waiting on Developer
0132 | Woodland ES | 1977 | PRT | MAINT |  |  | 83260 | 832600132 | Fencing - Install Aluminum Weld Fence at Front Entrance and to Clinic Safety Issue | 1 | 13/14 | 3611 |  | 1 |  | 21000 | 21000 |  | Complete
0132 | Woodland ES | 1977 | PRT | MAINT |  |  | 84045 | 840450132 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  | 1 |  | 100000 | 100000 |  | Complete
0131 | Zephyrhills HS | 1973 | PRT | MAINT |  |  | 85110 | 851100131 | Rebuild Gym Air Handlers | 1 | 13/14 | 3900 |  | 1 |  | 89671 | 89671 |  | Summer
0131 | Zephyrhills HS | 1973 | ATH | CS&CC | Yes |  | 82020 | 820200131 | Weight Room Renovation/Expansion | 1 | 13/14 | 3712 3903 |  | 1 |  | 468257 | 468257 |  | In Progress
0331 | Gulf HS | 1971 | ATH | ATH |  |  | 82040 | 820400331 | Scoreboard Replacement(s) | 2 | 13/14 | 3709 3713 |  | 1 |  | 40000 | 41780
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  | 82040 | 820400931 | Scoreboard Replacement(s) | 2 | 13/14 |  |  | 1 |  | 25000 | 26112.5 |  | Complete
0057 | Seven Springs MS | 1995 | ATH | MAINT |  |  | 82040 | 820400057 | Sound Panel Refurb In Gym | 2 | 13/14 | 3710 3711 |  | 1 |  | 75000 | 78337.5 |  | Complete
9420 | District Wide |  | OTIS | OTIS |  |  | 84080 | 840809420 | Administrative Computers |  | 13/14 | 3714 | 1430000 | 1
9032 | District Wide |  | FIN | FIN |  |  | 84220 | 842209032 | Annual Other Vehicles |  | 13/14 | 3715 | 200000 | 1
9420 | District Wide |  | OTIS | OTIS |  |  | 84060 | 840609420 | Student Teacher Computers |  | 13/14 | 3900 | 4000000 | 1
0031 | Pasco HS | 1964 | PRT | CS&CC |  |  | 85000 | 850000031 | Master Redevelopment |  | 1314 | 3903 | 129375 | 1
0401 | Centennial ES | 1986 | OTIS | OTIS |  |  | 83000 | 830000401 | Technology Infrastructure Upgrades | 1 | 14/15 |  |  | 1 |  | 425000 | 425000 |  |  | IS needs to prioritze
0401 | Centennial ES | 1986 | PRT | MAINT |  |  | 84045 | 840450401 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0069 | Centennial MS | 2001 | PRT | MAINT |  |  | 84045 | 840450069 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 125000 | 125000 |  | On Hold
0060 | Chester Taylor ES | 1996 | PRT | MAINT |  |  | 84045 | 840450060 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0701 | Cypress ES | 1973 | PRT | MAINT |  |  | 84045 | 840450701 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0421 | Deer Park ES | 1988 | OTIS | OTIS |  |  | 83000 | 830000421 | Technology Infrastructure Upgrades | 1 | 14/15 |  |  | 1 |  | 425000 | 425000 |  |  | IS needs to prioritze
0421 | Deer Park ES | 1988 | PRT | MAINT |  |  | 84045 | 840450421 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
9053 | District Complex |  | PRT | CS&CC |  |  |  |  | District Complex - Building 4 Remodel/Expansion | 1 | 14/15 |  |  | 1 |  | 2489000 | 2489000 |  |  | Additional Funds Needed
9053 | District Complex |  | PRT | CS&CC |  |  |  |  | District Complex - Building 3 Temp Remodel Training | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  |  | Temp Train Space while Bldg 4 being remodeled. Will be offices later.
0084 | Double Branch ES | 2007 | PRT | CS&CC |  |  | 86151 | 861510084 | Covered Sidewalks to Prevent Water Intrusion | 1 | 14/15 |  |  | 1 |  | 85000 | 85000
0351 | Fox Hollow ES | 1990 | OTIS | OTIS |  |  | 83000 | 830000351 | Technology Infrastructure Upgrades | 1 | 14/15 |  |  | 3 |  | 425000 | 425000 |  |  | IS needs to prioritze
0351 | Fox Hollow ES | 1990 | PRT | MAINT |  |  | 84045 | 840450351 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0083 | Gulf Highlands ES | 2006 | PRT | MAINT |  |  | 84045 | 840450083 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0261 | Gulf MS | 1964 | PRT | MAINT |  |  | 84045 | 840450261 | TV Installation in Classrooms | 1 | 14/15 | 3714 |  | 1 |  | 125000 | 125000 |  | On Hold
0911 | Gulfside ES | 1977 | PRT | MAINT |  |  | 84045 | 840450911 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0521 | Hudson HS | 1973 | FNS | CS&CC |  |  | 85250 | 852500521 | Kitchen Renovation | 1 | 14/15 |  |  | 1 |  | 942463 | 942463 |  | Summer 2015 | Floor was done.
0951 | Hudson MS | 1984 | PRT | MAINT |  |  | 84045 | 840450951 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 125000 | 125000 |  | On Hold
0073 | J.W. Mitchell HS | 2000 | PRT | MAINT |  |  | 84045 | 840450073 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 150000 | 150000 |  | On Hold
0065 | James M. Marlowe ES | 1998 | PRT | MAINT |  |  | 84045 | 840450065 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0961 | Lake Myrtle ES | 1984 | PRT | MAINT |  |  | 84045 | 840450961 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
2081 | Longleaf ES | 2005 | PRT | MAINT |  |  | 84045 | 840452081 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0451 | Mary Giella ES | 1989 | SCHOOL | MAINT |  |  | 85170 | 851700451 | Fencing - Installl 6' Chain Link Fence on Bus Loop Side | 1 | 14/15 |  |  | 1 |  | 25000 | 25000 |  | New
0941 | Moon Lake ES | 1982 | OTIS | OTIS |  |  | 83000 | 830000941 | Technology Infrastructure Upgrades | 1 | 14/15 |  |  | 2 |  | 425000 | 425000 |  |  | IS needs to prioritze
0941 | Moon Lake ES | 1982 | PRT | MAINT |  |  | 84045 | 840450941 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
9099 | New Elementary School | 2016 | PLAN | CS&CC | Yes |  | 87055 | 870559099 | Elementary W - Wiregrass | 1 | 14/15 | 3903 3921 | 17691000 | 1 | Penny & Other | 19801000 | 19801000 |  |  | Added $1 mill for 850 students & Extensive Site Development
9099 | New High School | 2017 | PLAN | CS&CC | Yes |  | 89020 | 890209099 | High School GGG - Old Pasco Road | 1 | 14/15 | 3904 | 28956000 | 1 | Impact Fees | 85000000 | 85000000
0501 | Northwest ES | 1973 | PRT | MAINT |  |  | 84045 | 840450501 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0071 | Pasco MS | 1946 | PRT | MAINT |  |  | 84045 | 840450071 | TV Installation in Classrooms - CCTE Building | 1 | 14/15 |  |  | 1 |  | 10000 | 10000
0902 | Pine View ES | 2003 | PRT | MAINT |  |  | 84045 | 840450902 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0921 | Pine View MS | 1977 | PRT | FOSM | Yes |  | 85110 | 851100921 | HVAC Renovation | 1 | 14/15 |  |  | 1 |  | 3000000 | 3000000
0921 | Pine View MS | 1977 | PRT | MAINT |  |  | 85200 | 852000921 | Roof Replacement | 1 | 14/15 |  |  | 1 |  | 900000 | 900000 |  | Re-allocate funds to CRES & PVMS HVAC Design | Schedule after HVAC Renovation
0102 | R.B. Stewart MS | 1926 | PRT | MAINT |  |  | 84045 | 840450102 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 125000 | 125000
0931 | Ridgewood HS | 1977 | PRT | FOSM |  |  | 85110 | 851100931 | HVAC Renovation | 1 | 14/15 |  |  | 1 |  | 2500000 | 2500000 |  | Design | Will do in 13/14 if money available
0931 | Ridgewood HS | 1977 | ATH | CS&CC |  |  |  |  | Tennis Court Renovation | 1 | 14/15 |  |  | 1 |  | 250000 | 250000
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  |  |  | Track Reconstruction | 1 | 14/15 |  |  | 1 |  | 150000 | 150000
0471 | River Ridge HS | 1990 | MAINT | MAINT |  |  |  |  | Drainage Improvements | 1 | 14/15 |  |  | 1 |  | 50000 | 50000
0471 | River Ridge HS | 1990 | PRT | MAINT |  |  | 84045 | 840450471 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 150000 | 150000 |  | On Hold
0472 | River Ridge MS | 1990 | PRT | MAINT |  |  | 84045 | 840450472 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 125000 | 125000 |  | On Hold
0251 | San Antonio ES | 1981 | OTIS | CS&CC |  |  | 83000 | 830000251 | Technology Infrastructure Upgrades | 1 | 14/15 |  |  | 1 |  | 425000 | 425000 |  |  | IS needs to prioritze
0251 | San Antonio ES | 1981 | PRT | MAINT |  |  | 84045 | 840450251 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
2061 | Sand Pine ES | 1998 | PRT | MAINT |  |  | 84045 | 840452061 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0201 | Sanders Memorial ES | 1944 | PRT | CS&CC |  |  |  |  | Campus Redevelopment Added Cost | 1 | 14/15 |  |  | 1 |  | 6000000 | 6000000
0341 | Schrader ES | 1972 | PRT | MAINT |  |  | 84045 | 840450341 | TV Installation in Classrooms - Bld #9 | 1 | 14/15 |  |  | 1 |  | 40000 | 40000 |  | On Hold
2091 | Seven Oaks ES | 2005 | PRT | MAINT |  |  | 84045 | 840452091 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0411 | Seven Springs ES | 1987 | PRT | MAINT |  |  | 84045 | 840450411 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0057 | Seven Springs MS | 1995 | OTIS | CS&CC |  |  | 83000 | 830000057 | Technology Infrastructure Upgrades | 1 | 14/15 |  |  | 3 |  | 650000 | 650000 |  |  | IS needs to prioritze
0072 | Sunray ES | 2000 | PRT | MAINT |  |  | 84045 | 840450072 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0032 | Trinity ES | 2000 | PRT | MAINT |  |  | 84045 | 840450032 | TV Installation in Classrooms | 1 | 14/15 |  |  | 1 |  | 100000 | 100000 |  | On Hold
0063 | Wesley Chapel HS | 1998 | PRT | CS&CC |  |  | 85140 | 851400063 | Maintenance of Drainage Canal behind school complex | 1 | 14/15 |  |  | 1 |  | 0 | 0 |  |  | Mark will check on
0063 | Wesley Chapel HS | 1998 | PRT | FOSM |  |  | 85110 | 851100063 | HVAC controls replacement phase 2 | 1 | 14/15 |  |  | 1 |  | 350000 | 350000
0063 | Wesley Chapel HS | 1998 | ATH | MAINT |  |  | 82050 | 820500063 | Overlay Courts | 1 | 14/15 |  |  | 1 |  | 150000 | 150000
0091 | West Zephyrhills ES | 1958 | OTIS | CS&CC |  |  | 83000 | 830000091 | Technology Infrastructure Upgrades | 1 | 14/15 |  |  | 1 |  | 425000 | 425000 |  |  | IS needs to prioritze
0090 | Wiregrass Ranch HS | 2006 | PRT | MAINT |  |  | 84045 | 840450090 | TV Installation in Classrooms - audio only | 1 | 14/15 |  |  | 1 |  | 51000 | 51000 |  | On Hold
0932 | Calusa ES | 1979 | FNS | CS&CC |  |  | 85250 | 852500932 | Cooler / Freezer with Renovations | 2 | 14/15 |  |  | 1 |  | 203963 | 213039.3535
0932 | Calusa ES | 1979 | FNS | FNS |  |  | 85250 | 852500932 | Kitchen Hood | 2 | 14/15 |  |  | 1 |  | 60775 | 63479.4875
0932 | Calusa ES | 1979 | FNS | CS&CC |  |  | 85250 | 852500932 | Serving Line Renovation | 2 | 14/15 |  |  | 1 |  | 286815 | 299578.2675
0060 | Chester Taylor ES | 1996 | PRT | MAINT |  |  | 85200 | 852000060 | Roof Maintenance | 2 | 14/15 |  |  | 1 |  | 80000 | 83560
0701 | Cypress ES | 1973 | FNS | FNS |  |  | 84070 | 840700701 | Cooler / Freezer | 2 | 14/15 |  |  | 1 |  | 66701 | 69669.1945
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 2 | 14/15 |  |  | 1 |  | 150000 | 156675
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
9031 | District Wide |  | FIN | FIN |  |  | 84210 | 842109031 | Annual Buses & Other Vehicles | 2 | 14/15 |  |  | 1 |  | 1700000 | 1775650
9061 | District Wide |  | FIN | FIN |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 2 | 14/15 |  |  | 1 |  | 210161 | 219513.1645
9061 | District Wide |  | FIN | FIN |  |  | 83260 | 832609061 | Annual Compliance with ADA | 2 | 14/15 |  |  | 1 |  | 150000 | 156675
0000 | District Wide |  | FIN | FIN |  |  | 00000 | 000000000 | Annual Debt Service Payments | 2 | 14/15 |  |  | 1 |  | 38816856 | 40544206.092
9061 | District Wide |  | PRT | MAINT |  |  | 86160 | 861609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 2 | 14/15 |  |  | 1 |  | 850000 | 887825
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 2 | 14/15 |  |  | 1 |  | 50000 | 52225
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 2 | 14/15 |  |  | 1 |  | 200000 | 208900
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 2 | 14/15 |  |  | 1 |  | 500000 | 522250
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | 851209061 | Annual Flooring Replacement | 2 | 14/15 |  |  | 1 |  | 300000 | 313350
9430 | District Wide |  | ATH | ATH |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 2 | 14/15 |  |  | 1 |  | 70000 | 73115 |  |  | Need $10k extra for GMS
9061 | District Wide |  | PRT | MAINT |  |  | 85110 | 851109061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 2 | 14/15 |  |  | 1 |  | 250000 | 261125
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 2 | 14/15 |  |  | 1 |  | 200000 | 208900
9061 | District Wide |  | FIN | FIN |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 2 | 14/15 |  |  | 1 |  | 1261000 | 1317114.5
9061 | District Wide |  | FIN | FIN |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 2 | 14/15 |  |  | 1 |  | 210000 | 219345
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 2 | 14/15 |  |  | 1 |  | 15000 | 15667.5
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 2 | 14/15 |  |  | 1 |  | 500000 | 522250
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 2 | 14/15 |  |  | 1 |  | 75000 | 78337.5
9420 | District Wide |  | OTIS | OTIS |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 2 | 14/15 |  |  | 1 |  | 6000000 | 6267000
9420 | District Wide |  | OTIS | OTIS |  |  | 84080 | 840809420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 2 | 14/15 |  |  | 1 |  | 1950000 | 2036775
9421 | District Wide |  | FIN | FIN |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 2 | 14/15 |  |  | 1 |  | 800000 | 835600
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 2 | 14/15 |  |  | 1 |  | 200000 | 208900
0084 | Double Branch ES | 2007 | PRT | CS&CC |  |  | 86150 | 861500084 | Traffic Safety and Parking Improvements - Add Turn Lane to Chauncey | 2 | 14/15 |  |  | 1 |  | 500000 | 522250 |  | Design is funded | County beginning design of extension
0261 | Gulf MS | 1964 | PRT | MAINT |  |  | 85000 | 850000261 | Renovate Restroom Bld #17 | 2 | 14/15 |  |  | 1 |  | 100000 | 104450 |  |  | Maintenance will check on
0321 | Lacoochee ES | 1971 | FNS | FNS |  |  | 85250 | 852500321 | Kitchen Hood | 2 | 14/15 |  |  | 1 |  | 60775 | 63479.4875
0321 | Lacoochee ES | 1971 | FNS | CS&CC |  |  | 85250 | 852500321 | Kitchen Renovation | 2 | 14/15 |  |  | 1 |  | 708852 | 740395.914
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  | 82050 | 820500801 | Baseball and Dugout Reconstruction | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC |  |  | 85250 | 852500801 | Cooler / Freezer with Renovations | 2 | 14/15 |  |  | 1 |  | 203963 | 213039.3535
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  | 82050 | 820500801 | Lighting - Replace Baseball Field | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC |  |  | 85250 | 852500801 | Serving Line Renovation | 2 | 14/15 |  |  | 1 |  | 981708.9975 | 1025395.0479
0211 | Mittye P. Locke ES | 1966 | FNS | CS&CC |  |  | 85250 | 852500211 | Kitchen Renovation | 2 | 14/15 |  |  | 1 |  | 708852 | 740395.914
0941 | Moon Lake ES | 1982 | FNS | CS&CC |  |  | 85110 | 851100941 | A/C Renovation To Kitchen | 2 | 14/15 |  |  | 1 |  | 204750 | 213861.375
0941 | Moon Lake ES | 1982 | FNS | CS&CC |  |  | 85250 | 852500941 | Serving Line Renovation | 2 | 14/15 |  |  | 1 |  | 286815 | 299578.2675
0501 | Northwest ES | 1973 | FNS | MAINT |  |  | 85250 | 852500501 | Kitchen Floor Renovation | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
0031 | Pasco HS | 1964 | ATH | MAINT |  |  | 82050 | 820500031 | Lighting - Replace Baseball Field | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
0921 | Pine View MS | 1977 | ATH | MAINT |  |  | 82050 | 820500921 | Overlay Outdoor Courts | 2 | 14/15 |  |  | 1 |  | 30000 | 31335
0921 | Pine View MS | 1977 | ATH | ATH |  |  | 82050 | 820500921 | Track Overlay | 2 | 14/15 |  |  | 1 |  | 40000 | 41780
0021 | R. B. Cox ES | 1925 | PRT | CS&CC | Yes |  |  |  | Remodel Clinic | 2 | 14/15 |  |  | 1 |  | 0 | 0 |  |  | Budget to be determined
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  | 82050 | 820500931 | Lighting - Replace Baseball Field | 2 | 14/15 |  |  | 1 |  | 100000 | 104450
0471 | River Ridge HS | 1990 | PRT | CS&CC |  |  | 85000 | 850000471 | Remodel Restrooms ADA | 2 | 14/15 |  |  | 2 |  | 731150 | 763686.175 |  |  | Not sure when this should be done
0472 | River Ridge MS | 1990 | PRT | CS&CC |  |  | 85000 | 850000472 | Remodel Restrooms ADA | 2 | 14/15 |  |  | 2 |  | 731150 | 763686.175 |  |  | Not sure when this should be done
0251 | San Antonio ES | 1981 | PRT | FOSM |  |  | 85110 | 851100251 | HVAC Upgrade - Phase 2 | 2 | 14/15 |  |  | 1 |  | 1300000 | 1357850
0411 | Seven Springs ES | 1987 | PRT | FOSM |  |  | 85110 | 851100411 | HVAC Replace 200 Ton Chiller | 2 | 14/15 |  |  | 1 |  | 250000 | 261125
0461 | Thomas E. Weightman MS | 1990 | PRT | FOSM |  |  | 85110 | 851100461 | HVAC Replace (2) 200 Ton Chillers & Controls | 2 | 14/15 |  |  | 1 |  | 1100000 | 1148950
0342 | Bayonet Point MS | 1973 | PRT | CS&CC | Yes |  | 86100 | 861000342 | Remodel School - Kelley School | 1 | 13/14 | 3921 | 15145250 | 2 | Penny Bond | 14500000 | 14500000 |  |  | Should this be $15.15 mill? Combined with Tech Infrastructure Upgrades?
9426 | District Wide |  | FIN | FIN |  |  | 84510 | 845109426 | Quest Student Information System | 1 | 13/14 | 3921 | 11277535 | 1 |  | 11277535 | 11277535
0801 | Land O' Lakes HS | 1973 | PRT | CS&CC |  |  | 86100 | 861000801 | Remodel School - Kelley School + Add Capacity | 1 |  | 3913 |  | 7 | Penny | 20600000 | 20600000
0451 | Mary Giella ES | 1989 | PRT | CS&CC | Yes |  | 86110 | 861100451 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3611 3713 | 381786 | 1 | Penny | 431786 | 431786 |  |  | Original Budget $355,826
0361 | Quail Hollow ES | 1975 | PRT | CS&CC | Yes |  | 86100 | 861000361 | Remodel School - Kelley School + Add Capacity | 1 | 13/14 | 3921 | 10360000 | 1 | Penny | 14500000 | 14500000 |  | In Progress
0931 | Ridgewood HS | 1977 | OTIS | OTIS |  |  | 83000 | 830000931 | Technology Infrastructure Upgrades | 1 |  | 3913 |  |  |  | 800000 | 800000 |  |  | IS needs to prioritze
0601 | Shady Hills ES | 1973 | PRT | CS&CC | Yes |  | 86100 | 861000601 | Remodel School - Kelley School + Add Capacity | 1 | 13/14 | 3921 | 10670000 | 1 | Penny | 11500000 | 11500000
0901 | Anclote ES | 1973 | PRT | CS&CC | Yes |  | 86100 | 861000901 | Remodel School - Kelley School + Add Capacity | 2 | 13/14 | 3921 | 11500000 | 2 |  | 14500000 | 15145250 |  |  | Added $3 mill to budget for roof replacement, new classroom building, additional site costs for stie dev / stormwater
0901 | Anclote ES | 1973 | OTIS | CS&CC |  |  | 83000 | 830000901 | Technology Infrastructure Upgrades | 2 |  | 3913 |  | 2 |  | 425000 | 443912.5 |  | Part of Renovation
0311 | Cotee River ES | 1993 | OTIS | OTIS |  |  | 83000 | 830000311 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 2 | 14/15 | 3913 |  | 1 |  | 200000 | 208900
9061 | District Wide |  | PRT | MAINT |  |  | 85211 | 852119061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 2 | 15/16 | 3913 |  | 2 |  | 200000 | 208900
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel Automotive Technology | 2 |  | 3921 |  | 1 |  | 1500000 | 1566750
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel Carpentry & Vet Assisting Program to HVAC Program | 2 |  | 3921 |  | 1 |  | 700000 | 731150
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel Commercial Art Room | 2 |  | 3921 |  | 1 |  | 110000 | 114895
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel Cosmetology Room | 2 |  | 3921 |  | 1 |  | 1007000 | 1051811.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel Culinary Arts Room | 2 |  | 3921 |  | 1 |  | 1200000 | 1253400
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel Electricity Room | 2 |  | 3921 |  | 1 |  | 415000 | 433467.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel HVAC Program Room | 2 |  | 3921 |  | 1 |  | 530000 | 553585
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel Marine Service Technology Program | 2 |  | 3921 |  | 1 |  | 300000 | 313350
0991 | Fred K. Marchman EC | 1984 | PRT | CS&CC | Yes |  | 86100 | 861000991 | Remodel School | 2 |  | 3921 |  | 1 |  | 518529 | 541603.5405
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Remodel TV Production Space | 2 |  | 3921 |  | 1 |  | 80000 | 83560
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Renovate Autobody Repair Bld., New Paint Booth, Paint Mixing Room, Frame Straightener, Welding Booth | 2 |  | 3921 |  | 1 |  | 500000 | 522250
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Yes |  | 86100 | 861000991 | Sign - New Marquee | 2 |  | 3921 |  | 1 |  | 7000 | 7311.5
0911 | Gulfside ES | 1977 | OTIS | OTIS |  |  | 83000 | 830000911 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0301 | Hudson ES | 1966 | OTIS | OTIS |  |  | 83000 | 830000301 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0951 | Hudson MS | 1984 | OTIS | OTIS |  |  | 83000 | 830000951 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 650000 | 678925
0321 | Lacoochee ES | 1971 | OTIS | OTIS |  |  | 83000 | 830000321 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0061 | Pasco ES | 1954 | PRT | CS&CC | Yes |  | 86100 | 861000061 | Renovate Bld #1-7, #9, #20, #21, #41 | 2 |  | 3921 | 5614560 | 1 |  | 5614560 | 5864407.92 |  |  | added Bld 9 to include cafeteria serving line renovation
0021 | R. B. Cox ES | 1925 | PRT | CS&CC | Yes |  | 86100 | 861000021 | Remodel School - Build New Cafeteria, Tear Down Old Cafeteria, Remove Concrete Portables, Traffic And Parking Improvements, Replace Remaining Old Windows, Install Securtiy System | 2 |  | 3921 | 7500000 | 1 |  | 6510441 | 6800155.6245
0472 | River Ridge MS | 1990 | CCTE | CS&CC |  |  | 85000 | 850000472 | Remodel Technology Education Space for PLTW Curriculum | 2 |  | 3913 |  | 1 |  | 160000 | 167120
2061 | Sand Pine ES | 1998 | OTIS | OTIS |  |  | 83000 | 830002061 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0601 | Shady Hills ES | 1973 | OTIS | CS&CC |  |  | 83000 | 830000601 | Technology Infrastructure Upgrades | 2 |  | 3913 |  | 1 |  | 425000 | 443912.5 |  | Part of Renovation
0063 | Wesley Chapel HS | 1998 | OTIS | OTIS |  |  | 83000 | 830000063 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 800000 | 835600
0131 | Zephyrhills HS | 1973 | OTIS | CS&CC |  |  | 83000 | 830000131 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 800000 | 835600
0060 | Chester Taylor ES | 1996 | OTIS | OTIS |  |  | 83000 | 830000060 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0311 | Cotee River ES | 1993 | PRT | CS&CC |  |  | 86150 | 861500311 | Traffic Safety and Parking Improvements | 3 |  | 3913 |  | 6 |  | 1000000 | 1090900
0701 | Cypress ES | 1973 | OTIS | CS&CC |  |  | 83000 | 830000701 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0059 | Denham Oaks ES | 1994 | OTIS | CS&CC |  |  | 83000 | 830000059 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 3 | 16/17 | 3913 |  | 3 |  | 200000 | 218180
9061 | District Wide |  | PRT | MAINT |  |  | 85211 | 852119061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 3 | 17/18 | 3913 |  | 4 |  | 200000 | 218180
0302 | Hudson ES | 1967 | PRT | CS&CC |  |  | 85000 | 850000302 | Remodel Bld #1 | 3 |  | 3913 |  | 6 |  | 400000 | 436360
0065 | James M. Marlowe ES | 1999 | OTIS | OTIS |  |  | 83000 | 830000065 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0211 | Mittye P. Locke ES | 1966 | PRT | CS&CC |  |  | 86100 | 861000211 | Remodel School, Replace Covered Walks, Traffic Improvements | 3 |  | 3913 |  | 6 |  | 8000000 | 8727200
0501 | Northwest ES | 1973 | OTIS | CS&CC |  |  | 83000 | 830000501 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0361 | Quail Hollow ES | 1975 | OTIS | CS&CC |  |  | 83000 | 830000361 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0021 | R. B. Cox ES | 1925 | OTIS | CS&CC |  |  | 83000 | 830000021 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0471 | River Ridge HS | 1990 | OTIS | OTIS |  |  | 83000 | 830000471 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 800000 | 872720
0472 | River Ridge MS | 1990 | OTIS | OTIS |  |  | 83000 | 830000472 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 650000 | 709085
0341 | Schrader ES | 1972 | OTIS | CS&CC |  |  | 83000 | 830000341 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0131 | Zephyrhills HS | 1973 | CCTE | CS&CC |  |  | 85240 | 852400131 | Remodel Automotive Technology To Lab Space/Convert To Health Academy | 3 |  | 3913 |  |  |  | 560000 | 610904
0131 | Zephyrhills HS | 1973 | PRT | CS&CC |  |  | 86100 | 861000131 | Remodel School - Kelley School + Add Capacity | 3 |  | 3913 |  |  |  | 20600000 | 22472540
0932 | Calusa ES | 1979 | OTIS | OTIS |  |  | 83000 | 830000932 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0074 | Centennial MS | 2001 | OTIS | OTIS |  |  | 83000 | 830000074 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 650000 | 740675
0070 | Chasco ES | 2000 | OTIS | OTIS |  |  | 83000 | 830000070 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0069 | Chasco MS | 2001 | OTIS | OTIS |  |  | 83000 | 830000069 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 650000 | 740675
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 4 | 18/19 | 3913 |  | 5 |  | 200000 | 227900
9061 | District Wide |  | PRT | MAINT |  |  | 85211 | 852119061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 4 | 19/20 | 3914 |  | 6 |  | 200000 | 227900
0991 | Fred K. Marchman EC | 1984 | PRT | MAINT |  |  | 85200 | 852000991 | Roof Replacement | 4 |  | 3913 |  |  |  | 250000 | 284875
0331 | Gulf HS | 1971 | PRT | CS&CC |  |  | 86100 | 861000331 | Remodel School Phase 1 - Bld #1 | 4 |  | 3913 |  |  |  | 9150000 | 10426425
0331 | Gulf HS | 1971 | PRT | CS&CC |  |  | 86100 | 861000331 | Remodel School Phase 2 | 4 |  | 3913 |  |  |  | 2514150 | 2864873.925
0911 | Gulfside ES | 1977 | PRT | CS&CC |  |  | 86100 | 861000911 | Remodel Bld #1 & #2; Parking And Traffic Improvements | 4 |  | 3913 |  |  |  | 2500000 | 2848750
0521 | Hudson HS | 1973 | PRT | CS&CC |  |  | 86100 | 861000521 | Remodel School - Kelley School | 4 |  | 3913 |  |  |  | 19100000 | 21764450
0521 | Hudson HS | 1973 | OTIS | CS&CC |  |  | 83000 | 830000521 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 800000 | 911600
0521 | Hudson HS | 1973 | PRT | CS&CC |  |  | 86110 | 861100521 | Traffic Safety and Parking Improvements | 4 | [5 empty] | 860000 | 979970
0321 | Lacoochee ES | 1971 | PRT | CS&CC |  |  | 86100 | 861000321 | Remodel Classroom Bld #8,9,11,12,13 | 4 |  | 3913 |  |  |  | 1348655 | 1536792.3725
0961 | Lake Myrtle ES | 1984 | OTIS | OTIS |  |  | 83000 | 830000961 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0801 | Land O' Lakes HS | 1973 | OTIS | CS&CC |  |  | 83000 | 830000801 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 800000 | 911600
0941 | Moon Lake ES | 1982 | PRT | CS&CC |  |  | 86110 | 861100941 | Traffic Safety and Parking Improvements | 4 |  | 3913 |  |  |  | 758000 | 863741
0411 | Seven Springs ES | 1987 | OTIS | OTIS |  |  | 83000 | 830000411 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
2071 | Wesley Chapel ES | 2002 | OTIS | OTIS |  |  | 83000 | 830002071 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0132 | Woodland ES | 1977 | OTIS | CS&CC |  |  | 83000 | 830000132 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0342 | Bayonet Point MS | 1973 | OTIS | CS&CC |  |  | 83000 | 830000342 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 650000 | 773630
0932 | Calusa ES | 1979 | PRT | CS&CC |  |  | 86110 | 861100932 | Traffic Safety and Parking Improvements | 5 |  | 3913 |  |  |  | 650000 | 773630
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 5 | 20/21 | 3913 |  | 7 |  | 200000 | 238040
9061 | District Wide |  | PRT | MAINT |  |  | 85211 | 852119061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 5 | 21/22 | 3914 |  | 8 |  | 200000 | 238040
0331 | Gulf HS | 1971 | OTIS | OTIS |  |  | 83000 | 830000331 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
0261 | Gulf MS | 1964 | OTIS | OTIS |  |  | 83000 | 830000261 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 650000 | 773630
0073 | J.W. Mitchell HS | 2000 | OTIS | OTIS |  |  | 83000 | 830000073 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
2081 | Longleaf ES | 2005 | OTIS | OTIS |  |  | 83000 | 830002081 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0451 | Mary Giella ES | 1989 | OTIS | OTIS |  |  | 83000 | 830000451 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0501 | Northwest ES | 1973 | PRT | CS&CC |  |  | 86100 | 861000501 | Remodel School - Kelley School | 5 |  | 3913 |  |  |  | 7000000 | 8331400
0902 | Pine View ES | 2003 | OTIS | OTIS |  |  | 83000 | 830000902 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0921 | Pine View MS | 1977 | OTIS | OTIS |  |  | 83000 | 830000921 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
0931 | Ridgewood HS | 1977 | PRT | CS&CC |  |  | 86100 | 861000931 | Remodel Bld #1 | 5 |  | 3913 |  |  |  | 9000000 | 10711800
0931 | Ridgewood HS | 1977 | CCTE | CS&CC |  |  | 83000 | 830000931 | Remodel Technology Lab - Room 404 | 5 |  | 3913 |  |  |  | 300000 | 357060
0251 | San Antonio ES | 1981 | PRT | CS&CC |  |  | 86100 | 861000251 | Remodel Bld #1 #2 #10 | 5 |  | 3913 |  |  |  | 3965541 | 4719786.8982
0072 | Sunray ES | 2000 | OTIS | OTIS |  |  | 83000 | 830000072 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0032 | Trinity ES | 2000 | OTIS | OTIS |  |  | 83000 | 830000032 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0132 | Woodland ES | 1977 | PRT | CS&CC |  |  | 86100 | 861000132 | Remodel School, Expand Cafeteria | 5 |  | 3913 |  |  |  | 4514705 | 5373401.891
0070 | Chasco ES | 2000 | SCHOOL | CS&CC |  |  | 86190 | 861900070 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 100000 | 124310
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 6 | 22/23 | 3913 |  | 9 |  | 200000 | 248620
9061 | District Wide |  | PRT | MAINT |  |  | 85211 | 852119061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 6 | 23/24 | 3914 |  | 10 |  | 200000 | 248620
0521 | Hudson HS | 1973 | SCHOOL | CS&CC |  |  | 86190 | 861900521 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 100000 | 124310
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  | 86190 | 861900921 | Covered Walkways - ESE | 6 |  | 3913 |  |  |  | 406000 | 504698.6
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  | 86190 | 861900921 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 550000 | 683705
0461 | Thomas E. Weightman MS | 1990 | PRT | CS&CC |  |  | 86110 | 861100461 | Traffic Safety and Parking Improvements | 6 |  | 3913 |  |  |  | 540000 | 671274
9099 | New K-8 School |  | PLAN | CS&CC | Yes |  |  |  | Starkey Ranch K-8 Site Engineering | 1 | 14/15 |  |  | 1 |  | 0 | 0
0117 | Odessa ES | 2010 | PRT | CS&CC |  |  |  |  | Traffic and Safety Improvements with Interlaken Road | 1 | 14/15 |  |  | 1 | [5 empty] | Curr Car line on Interlaken. Do we need to do something?
0361 | Quail Hollow ES | 1975 | PRT | CS&CC | Yes |  | 86100 | 861000361 | Remodel School - Kelley School + Add Capacity | 1 | 14/15 |  |  | 1 |  | 3000000 | 3000000 |  |  | Additional funds needed for roof replacement, add new classroom building, additional site costs for site dev / stormwater
0521 | Hudson HS | 1973 | ATH | ATH |  |  | 82050 | 820500521 | Track Overlay | 2 | [5 empty] | 60000 | 62670
0472 | River Ridge MS | 1990 | ATH | MAINT |  |  | 82050 | 820500472 | Overlay Middle School Track | 2 | [5 empty] | 125000 | 130562.5
9099 | New Elementary School | 2017 | PLAN | CS&CC | Yes |  |  |  | Elementary B - Bexley Ranch South | 3 | 16/17 |  |  | 3 |  | 19000000 | 20727100
0063 | Wesley Chapel HS | 1998 | PRT | FOSM |  |  | 85110 | 851100063 | HVAC Replace 400 Ton Chiller | 3 | [5 empty] | 300000 | 327270 |  |  | Should this be tied to controls replacement?
0031 | Pasco HS | 1964 | CCTE | CS&CC |  |  |  |  | Remodel or Build New Space for Cosmetology | 5 |  |  |  | 5 |  | 600000 | 714120
0131 | Zephyrhills HS | 1973 | ATH | CS&CC |  |  |  |  | Shift Baseball Field Complex due to Road Widening | 5 |  |  |  | 5 |  | 0 | 0
0901 | Anclote ES | 1973 | PRT | MAINT |  |  | 84045 | 840450901 | TV Installation in Classrooms | 1 |  |  |  | 2 |  | 100000 | 100000 |  |  | Merge with renovation
0342 | Bayonet Point MS | 1973 | PRT | MAINT |  |  | 85200 | 852000342 | Roof Replacement | 1 |  |  |  | 2 |  | 1000000 | 1000000 |  |  | Needs to be done with remodel
0342 | Bayonet Point MS | 1973 | PRT | MAINT |  |  | 84045 | 840450342 | TV Installation in Classrooms | 1 |  |  |  | 2 |  | 125000 | 125000 |  |  | Merge with renovation
0701 | Cypress ES | 1973 | PRT | MAINT |  |  | 85200 | 852000701 | Roof Replacement | 1 | 15/16 |  |  | 2 |  | 300000 | 300000
0521 | Hudson HS | 1973 | PRT | MAINT |  |  | 84045 | 840450521 | TV Installation in Classrooms | 1 |  |  |  | 3 |  | 150000 | 150000 |  |  | TBD
0211 | Mittye P. Locke ES | 1966 | OTIS | CS&CC |  |  | 83000 | 830000211 | Technology Infrastructure Upgrades | 1 |  |  |  | 2 |  | 425000 | 425000 |  |  | Merge with renovation
0941 | Moon Lake ES | 1982 | PRT | MAINT |  |  | 85200 | 852000941 | Roof Replacement | 1 | 15/16 |  |  | 2 |  | 500000 | 500000
0061 | Pasco ES | 1954 | OTIS | CS&CC |  |  | 83000 | 830000061 | Technology Infrastructure Upgrades | 1 |  |  |  | 2 |  | 425000 | 425000 |  |  | Merge with renovation
0601 | Shady Hills ES | 1973 | PRT | MAINT |  |  | 85200 | 852000601 | Roof Replacement | 1 |  |  |  | 5 |  | 300000 | 300000 |  |  | Not needed now.
0342 | Bayonet Point MS | 1973 | FNS | CS&CC |  |  | 85250 | 852500342 | Cooler / Freezer with Renovations (Stock Room) | 2 |  |  |  | 1 |  | 203963 | 213039.3535 |  |  | Merge with renovation
0342 | Bayonet Point MS | 1973 | ATH | MAINT |  |  | 85000 | 850000342 | Renovate Girls & Boys Locker Rooms | 2 |  |  |  | 1 |  | 100000 | 104450 |  |  | Merge with renovation
0100 | Charles S. Rushe MS | 2007 | FNS | MAINT |  |  |  |  | Kitchen Floor Renovation | 2 | 15/16 |  |  | 2 |  | 150000 | 156675
0069 | Chasco MS | 2001 | FNS | FNS |  |  | 84070 | 840700069 | Cooler / Freezer | 2 | 15/16 |  |  | 2 |  | 66701.25 | 69669.4556
9053 | District Complex | 1974 | PRT | CS&CC | Yes |  |  |  | District Complex - Building 2 Remodel | 2 | 15/16 |  |  | 2 |  | 3000000 | 3133500
9430 | District Wide |  | ATH | MAINT |  |  | 82051 | 820519430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 2 | 15/16 |  |  | 2 |  | 150000 | 156675
9061 | District Wide |  | ATH | MAINT |  |  | 82011 | 820119061 | Annual Bleacher Repair ($100,000 Annually) | 2 | 15/16 |  |  | 2 |  | 100000 | 104450
9031 | District Wide |  | FIN | FIN |  |  | 84211 | 842119031 | Annual Buses & Other Vehicles | 2 | 15/16 |  |  | 2 |  | 1700000 | 1775650
9061 | District Wide |  | FIN | FIN |  |  | 83241 | 832419061 | Annual Compliance w/Environmental Reg | 2 | 15/16 |  |  | 2 |  | 210161 | 219513.1645
9061 | District Wide |  | FIN | FIN |  |  | 83261 | 832619061 | Annual Compliance with ADA | 2 | 15/16 |  |  | 2 |  | 150000 | 156675
0000 | District Wide |  | FIN | FIN |  |  | 00001 | 000010000 | Annual Debt Service Payments | 2 | 15/16 |  |  | 2 |  | 38816856 | 40544206.092
9061 | District Wide |  | PRT | MAINT |  |  | 86161 | 861619061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 2 | 15/16 |  |  | 2 |  | 850000 | 887825
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 2 | 15/16 |  |  | 2 |  | 50000 | 52225
9061 | District Wide |  | PRT | MAINT |  |  | 85181 | 851819061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 2 | 15/16 |  |  | 2 |  | 200000 | 208900
9019 | District Wide |  | PRT | CS&CC |  |  | 85181 | 851819019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 2 | 15/16 |  |  | 2 |  | 500000 | 522250
9061 | District Wide |  | PRT | MAINT |  |  | 85121 | 851219061 | Annual Flooring Replacement | 2 | 15/16 |  |  | 2 |  | 300000 | 313350
9430 | District Wide |  | ATH | ATH |  |  | 82001 | 820019430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 2 | 15/16 |  |  | 2 |  | 60000 | 62670
9061 | District Wide |  | PRT | MAINT |  |  | 85111 | 851119061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 2 | 15/16 |  |  | 2 |  | 250000 | 261125
9061 | District Wide |  | PRT | MAINT |  |  | 86181 | 861819061 | Annual Lift Station Upgrades ($100,000 Annually) | 2 | 15/16 |  |  | 2 |  | 200000 | 208900
9061 | District Wide |  | FIN | FIN |  |  | 85101 | 851019061 | Annual Maintenance & Repairs Projects (Small) | 2 | 15/16 |  |  | 2 |  | 1261000 | 1317114.5
9061 | District Wide |  | FIN | FIN |  |  | 83241 | 832419061 | Annual Maintenance Health & Safety | 2 | 15/16 |  |  | 2 |  | 210000 | 219345
9002 | District Wide |  | PRT | MAINT |  |  | 86111 | 861119002 | Annual Marquee Sign Replacements ($15,000 Annually) | 2 | 15/16 |  |  | 2 |  | 15000 | 15667.5
9061 | District Wide |  | PRT | MAINT |  |  | 86141 | 861419061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 2 | 15/16 |  |  | 2 |  | 500000 | 522250
9061 | District Wide |  | PRT | MAINT |  |  | 81001 | 810019061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 2 | 15/16 |  |  | 2 |  | 100000 | 104450
9061 | District Wide |  | PRT | MAINT |  |  | 85221 | 852219061 | Annual Security Cameras & Alarms | 2 | 15/16 |  |  | 2 |  | 100000 | 104450
9430 | District Wide |  | ATH | MAINT |  |  | 82041 | 820419430 | Annual Sound System Repairs ($75,000 Annually) | 2 | 15/16 |  |  | 2 |  | 75000 | 78337.5
9420 | District Wide |  | OTIS | OTIS |  |  | 84061 | 840619420 | Annual Technology and Equipment ( Student Computers) | 2 | 15/16 |  |  | 2 |  | 6000000 | 6267000
9420 | District Wide |  | OTIS | OTIS |  |  | 84081 | 840819420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 2 | 15/16 |  |  | 2 |  | 1950000 | 2036775
9421 | District Wide |  | FIN | FIN |  |  | 83001 | 830019421 | Annual Telecommunications Repairs Projects (Small) | 2 | 15/16 |  |  | 2 |  | 800000 | 835600
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 2 | 15/16 |  |  | 2 |  | 200000 | 208900
0301 | Hudson ES | 1966 | PRT | CS&CC |  |  | 85000 | 850000301 | Remodel Restrooms ADA | 2 | 16/17 |  |  | 3 |  | 731150 | 763686.175 |  |  | Couple this with other projects
0301 | Hudson ES | 1966 | FNS | MAINT |  |  | 85250 | 852500301 | Kitchen Floor Renovation | 2 | 16/17 |  |  | 3 |  | 35280 | 36849.96
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  | 82020 | 820200521 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 2 | 16/17 |  |  | 3 |  | 2500000 | 2611250
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  | 82020 | 820200521 | Renovate/Build Athletic Field House | 2 | 16/17 |  |  | 3 |  | 1044500 | 1090980.25
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  | 82020 | 820200521 | Concession Stand Bathrooms - Baseball/Softball | 2 | 16/17 |  |  | 3 |  | 250000 | 261125
0451 | Mary Giella ES | 1989 | PRT | FOSM |  |  | 85110 | 851100451 | HVAC Replace Air Handlers & Controls | 2 | 15/16 |  |  | 2 |  | 2500000 | 2611250
0031 | Pasco HS | 1964 | ATH | CS&CC |  |  | 82050 | 820500031 | New Bleachers, Male/Female Lockers | 2 | 16/17 |  |  | 3 |  | 2500000 | 2611250
0091 | West Zephyrhills ES | 1958 | PRT | CS&CC |  |  | 86100 | 861000091 | Remodel School - Tear Down Or Remodel Cafeteria Bld #2 Into Classrooms, Renovate Bld #1,3,4,5,8,9,14 | 2 |  |  |  | 5 |  | 8592752 | 8975129.464
0090 | Wiregrass Ranch HS | 2006 | CCTE | CS&CC |  |  | 85240 | 852400090 | Remodel/Expand Culinary Classroom | 2 |  |  |  | 6 |  | 420000 | 438690
0901 | Anclote ES | 1973 | FNS | FNS |  |  | 85250 | 852500901 | Kitchen Hood | 3 | [5 empty] | 66853 | 72929.9377
0901 | Anclote ES | 1973 | FNS | CS&CC |  |  | 85250 | 852500901 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0342 | Bayonet Point MS | 1973 | FNS | CS&CC |  |  | 85250 | 852500342 | Serving Line Renovation | 3 | [5 empty] | 120329 | 131266.9061
0060 | Chester Taylor ES | 1996 | FNS | CS&CC |  |  | 85110 | 851100060 | A/C Renovation To Kitchen | 3 | [5 empty] | 195000 | 212725.5
0060 | Chester Taylor ES | 1996 | FNS | CS&CC |  |  | 85250 | 852500060 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0701 | Cypress ES | 1973 | PRT | CS&CC |  |  | 86100 | 861000701 | Remodel School - Kelley School + Add Capacity | 3 |  |  |  | 8 |  | 11000000 | 11999900
0059 | Denham Oaks ES | 1994 | PRT | MAINT |  |  | 85200 | 852000059 | Roof Maintenance and Internal Gutters | 3 | [5 empty] | 50000 | 54545
0059 | Denham Oaks ES | 1994 | FNS | CS&CC |  |  | 85250 | 852500059 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
9430 | District Wide |  | ATH | MAINT |  |  | 82052 | 820529430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 3 | 16/17 |  |  | 3 |  | 150000 | 163635
9430 | District Wide |  | ATH | MAINT |  |  | 82053 | 820539430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 3 | 17/18 |  |  | 4 |  | 150000 | 163635
9061 | District Wide |  | ATH | MAINT |  |  | 82012 | 820129061 | Annual Bleacher Repair ($100,000 Annually) | 3 | 16/17 |  |  | 3 |  | 100000 | 109090
9061 | District Wide |  | ATH | MAINT |  |  | 82013 | 820139061 | Annual Bleacher Repair ($100,000 Annually) | 3 | 17/18 |  |  | 4 |  | 100000 | 109090
9031 | District Wide |  | FIN | FIN |  |  | 84212 | 842129031 | Annual Buses & Other Vehicles | 3 | 16/17 |  |  | 3 |  | 1700000 | 1854530
9031 | District Wide |  | FIN | FIN |  |  | 84213 | 842139031 | Annual Buses & Other Vehicles | 3 | 17/18 |  |  | 4 |  | 1700000 | 1854530
9061 | District Wide |  | FIN | FIN |  |  | 83242 | 832429061 | Annual Compliance w/Environmental Reg | 3 | 16/17 |  |  | 3 |  | 210161 | 229264.6349
9061 | District Wide |  | FIN | FIN |  |  | 83243 | 832439061 | Annual Compliance w/Environmental Reg | 3 | 17/18 |  |  | 4 |  | 210161 | 229264.6349
9061 | District Wide |  | FIN | FIN |  |  | 83262 | 832629061 | Annual Compliance with ADA | 3 | 14/16 |  |  | 3 |  | 150000 | 163635
9061 | District Wide |  | FIN | FIN |  |  | 83263 | 832639061 | Annual Compliance with ADA | 3 | 15/17 |  |  | 4 |  | 150000 | 163635
0000 | District Wide |  | FIN | FIN |  |  | 00002 | 000020000 | Annual Debt Service Payments | 3 | 16/17 |  |  | 3 |  | 38816856 | 42345308.2104
0000 | District Wide |  | FIN | FIN |  |  | 00003 | 000030000 | Annual Debt Service Payments | 3 | 17/18 |  |  | 4 |  | 38816856 | 42345308.2104
9061 | District Wide |  | PRT | MAINT |  |  | 86162 | 861629061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 3 | 16/17 |  |  | 3 |  | 850000 | 927265
9061 | District Wide |  | PRT | MAINT |  |  | 86163 | 861639061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 3 | 17/18 |  |  | 4 |  | 850000 | 927265
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 3 | 16/17 |  |  | 3 |  | 50000 | 54545
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 3 | 17/18 |  |  | 4 |  | 50000 | 54545
9061 | District Wide |  | PRT | MAINT |  |  | 85182 | 851829061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 3 | 16/17 |  |  | 3 |  | 200000 | 218180
9061 | District Wide |  | PRT | MAINT |  |  | 85183 | 851839061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 3 | 17/18 |  |  | 4 |  | 200000 | 218180
9019 | District Wide |  | PRT | CS&CC |  |  | 85182 | 851829019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 3 | 16/17 |  |  | 3 |  | 500000 | 545450
9019 | District Wide |  | PRT | CS&CC |  |  | 85183 | 851839019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 3 | 17/18 |  |  | 4 |  | 500000 | 545450
9061 | District Wide |  | PRT | MAINT |  |  | 85122 | 851229061 | Annual Flooring Replacement | 3 | 16/17 |  |  | 3 |  | 300000 | 327270
9061 | District Wide |  | PRT | MAINT |  |  | 85123 | 851239061 | Annual Flooring Replacement | 3 | 17/18 |  |  | 4 |  | 300000 | 327270
9430 | District Wide |  | ATH | ATH |  |  | 82002 | 820029430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 3 | 16/17 |  |  | 3 |  | 60000 | 65454
9430 | District Wide |  | ATH | ATH |  |  | 82003 | 820039430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 3 | 17/18 |  |  | 4 |  | 60000 | 65454
9061 | District Wide |  | PRT | MAINT |  |  | 85112 | 851129061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 3 | 16/17 |  |  | 3 |  | 250000 | 272725
9061 | District Wide |  | PRT | MAINT |  |  | 85113 | 851139061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 3 | 17/18 |  |  | 4 |  | 250000 | 272725
9061 | District Wide |  | PRT | MAINT |  |  | 86182 | 861829061 | Annual Lift Station Upgrades ($100,000 Annually) | 3 | 16/17 |  |  | 3 |  | 200000 | 218180
9061 | District Wide |  | PRT | MAINT |  |  | 86183 | 861839061 | Annual Lift Station Upgrades ($100,000 Annually) | 3 | 17/18 |  |  | 4 |  | 200000 | 218180
9061 | District Wide |  | FIN | FIN |  |  | 85102 | 851029061 | Annual Maintenance & Repairs Projects (Small) | 3 | 16/17 |  |  | 3 |  | 1261000 | 1375624.9
9061 | District Wide |  | FIN | FIN |  |  | 85103 | 851039061 | Annual Maintenance & Repairs Projects (Small) | 3 | 17/18 |  |  | 4 |  | 1261000 | 1375624.9
9061 | District Wide |  | FIN | FIN |  |  | 83242 | 832429061 | Annual Maintenance Health & Safety | 3 | 16/17 |  |  | 3 |  | 210000 | 229089
9061 | District Wide |  | FIN | FIN |  |  | 83243 | 832439061 | Annual Maintenance Health & Safety | 3 | 17/18 |  |  | 4 |  | 210000 | 229089
9002 | District Wide |  | PRT | MAINT |  |  | 86112 | 861129002 | Annual Marquee Sign Replacements ($15,000 Annually) | 3 | 16/17 |  |  | 3 |  | 15000 | 16363.5
9002 | District Wide |  | PRT | MAINT |  |  | 86113 | 861139002 | Annual Marquee Sign Replacements ($15,000 Annually) | 3 | 17/18 |  |  | 4 |  | 15000 | 16363.5
9061 | District Wide |  | PRT | MAINT |  |  | 86142 | 861429061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 3 | 16/17 |  |  | 3 |  | 500000 | 545450
9061 | District Wide |  | PRT | MAINT |  |  | 86143 | 861439061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 3 | 17/18 |  |  | 4 |  | 500000 | 545450
9061 | District Wide |  | PRT | MAINT |  |  | 81002 | 810029061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 3 | 16/17 |  |  | 3 |  | 100000 | 109090
9061 | District Wide |  | PRT | MAINT |  |  | 81003 | 810039061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 3 | 17/18 |  |  | 4 |  | 100000 | 109090
9061 | District Wide |  | PRT | MAINT |  |  | 85222 | 852229061 | Annual Security Cameras & Alarms | 3 | 16/17 |  |  | 3 |  | 100000 | 109090
9061 | District Wide |  | PRT | MAINT |  |  | 85223 | 852239061 | Annual Security Cameras & Alarms | 3 | 17/18 |  |  | 4 |  | 100000 | 109090
9430 | District Wide |  | ATH | MAINT |  |  | 82042 | 820429430 | Annual Sound System Repairs ($75,000 Annually) | 3 | 16/17 |  |  | 3 |  | 75000 | 81817.5
9430 | District Wide |  | ATH | MAINT |  |  | 82043 | 820439430 | Annual Sound System Repairs ($75,000 Annually) | 3 | 17/18 |  |  | 4 |  | 75000 | 81817.5
9420 | District Wide |  | OTIS | OTIS |  |  | 84062 | 840629420 | Annual Technology and Equipment ( Student Computers) | 3 | 16/17 |  |  | 3 |  | 6000000 | 6545400
9420 | District Wide |  | OTIS | OTIS |  |  | 84063 | 840639420 | Annual Technology and Equipment ( Student Computers) | 3 | 17/18 |  |  | 4 |  | 6000000 | 6545400
9420 | District Wide |  | OTIS | OTIS |  |  | 84082 | 840829420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 3 | 16/17 |  |  | 3 |  | 1950000 | 2127255
9420 | District Wide |  | OTIS | OTIS |  |  | 84083 | 840839420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 3 | 17/18 |  |  | 4 |  | 1950000 | 2127255
9421 | District Wide |  | FIN | FIN |  |  | 83002 | 830029421 | Annual Telecommunications Repairs Projects (Small) | 3 | 16/17 |  |  | 3 |  | 800000 | 872720
9421 | District Wide |  | FIN | FIN |  |  | 83003 | 830039421 | Annual Telecommunications Repairs Projects (Small) | 3 | 17/18 |  |  | 4 |  | 800000 | 872720
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 3 | 16/17 |  |  | 3 |  | 200000 | 218180
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 3 | 17/18 |  |  | 4 |  | 200000 | 218180
9012 | District Wide |  | PLAN | PLAN |  |  | 89990 | 899909012 | Property Acquisition - Middle/High Site in River Landing (Wesley Chapel) | 3 | [5 empty] | 4000000 | 4363600
0086 | Dr. John Long MS | 2006 | PRT | CS&CC |  |  | 86100 | 861000086 | Addition - Classroom Wing | 3 | [5 empty] | 4000000 | 4363600
0086 | Dr. John Long MS | 2006 | ATH | ATH |  |  | 82000 | 820000086 | Sand & Paint Gym Floors | 3 | [5 empty] | 25000 | 27272.5
0331 | Gulf HS | 1971 | ATH | MAINT |  |  | 85170 | 851700331 | Fencing - Baseball Field | 3 | [5 empty] | 20000 | 21818
0331 | Gulf HS | 1971 | ATH | MAINT |  |  | 85170 | 851700331 | Fencing - Tennis Court Fence | 3 | [5 empty] | 15000 | 16363.5 |  |  | Phil will check to see if need to move up in priority
0261 | Gulf MS | 1964 | FNS | MAINT |  |  | 85250 | 852500261 | Kitchen Renovation Flooring, Paint, Ovens, Steamers | 3 | [5 empty] | 120329 | 131266.9061
0261 | Gulf MS | 1964 | PRT | CS&CC |  |  | 86100 | 861000261 | Remodel School Bld 1, 2, 3, 9. 10, 11, 14 | 3 |  |  |  | 6 |  | 9439558 | 10297613.8222
0301 | Hudson ES | 1966 | FNS | CS&CC |  |  | 85250 | 852500301 | Remodel Kitchen And Serving Line | 3 |  |  |  | 6 |  | 850616 | 927936.9944
0521 | Hudson HS | 1973 | ATH | MAINT |  |  | 85170 | 851700521 | Fencing - Perimeter | 3 | [5 empty] | 20000 | 21818
0073 | J.W. Mitchell HS | 2000 | ATH | CS&CC |  |  | 82050 | 820500073 | Refurbish Football Field Elevation and Field Drainage | 3 | [5 empty] | 320000 | 349088
0065 | James M. Marlowe ES | 1999 | PRT | MAINT |  |  | 85200 | 852000065 | Roof Maintenance | 3 | [5 empty] | 80000 | 87272
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  | 85170 | 851700801 | Fencing - Tennis | 3 | [5 empty] | 15000 | 16363.5
9099 | New K-8 School |  | PLAN | CS&CC | Yes |  |  |  | Starkey Ranch K-8 | 3 | [5 empty] | 50000000 | 54545000
0089 | Paul R. Smith MS | 2006 | ATH | ATH |  |  | 82000 | 820000089 | Sand & Paint Gym Floors | 3 | [5 empty] | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  | 85000 | 850000931 | Replace Wall Tile In PE Locker Room | 3 | [5 empty] | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  | 82040 | 820400931 | Scoreboard Replacement(s) | 3 | [5 empty] | 25000 | 27272.5
0471 | River Ridge HS | 1990 | ATH | MAINT |  |  | 85170 | 851700471 | Fencing - Tennis | 3 | [5 empty] | 30000 | 32727
0072 | Sunray ES | 2000 | PRT | MAINT |  |  | 85200 | 852000072 | Roof Maintenance | 3 | [5 empty] | 80000 | 87272
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT |  |  | 85170 | 851700461 | Fencing - Tennis Court Fence | 3 | [5 empty] | 20000 | 21818 |  |  | Phil Bell will check to see if need to move up in priority
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT |  |  | 82050 | 820500461 | Overlay Courts | 3 | [5 empty] | 80000 | 87272
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC |  |  | 86100 | 861000090 | Addition - Classroom Wing | 3 | [5 empty] | 4000000 | 4363600
0132 | Woodland ES | 1977 | PRT | FOSM |  |  | 85110 | 851100132 | HVAC Upgrade - Phase 2 | 3 |  |  |  | 1 |  | 4500000 | 4909050
0401 | Centennial ES | 1986 | PRT | FOSM |  |  | 85110 | 851100401 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 250000 | 284875
0074 | Centennial MS | 2001 | FNS | FNS |  |  | 86200 | 862000074 | Outside Dining Sun Shade | 4 | [5 empty] | 10000 | 11395
0074 | Centennial MS | 2001 | PRT | MAINT |  |  | 85200 | 852000074 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0074 | Centennial MS | 2001 | FNS | CS&CC |  |  | 85250 | 852500074 | Serving Line Renovation | 4 | [5 empty] | 981709 | 1118657.4055
0070 | Chasco ES | 2000 | PRT | MAINT |  |  | 85200 | 852000070 | Roof Maintenance | 4 | [5 empty] | 40000 | 45580
0069 | Chasco MS | 2001 | PRT | MAINT |  |  | 85200 | 852000069 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0069 | Chasco MS | 2000 | ATH | ATH |  |  | 82000 | 820000069 | Sand & Paint Gym Floors | 4 | [5 empty] | 25000 | 28487.5
0311 | Cotee River ES | 1993 | FNS | FNS |  |  | 84070 | 840700311 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0311 | Cotee River ES | 1993 | PRT | FOSM |  |  | 85110 | 851100311 | HVAC Replace (2) chillers & controls | 4 | [5 empty] | 350000 | 398825
0701 | Cypress ES | 1973 | FNS | FNS |  |  | 85250 | 852500701 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0421 | Deer Park ES | 1988 | PRT | FOSM |  |  | 85110 | 851100421 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 225000 | 256387.5
0421 | Deer Park ES | 1988 | FNS | CS&CC |  |  | 85250 | 852500421 | Serving Line Renovation | 4 | [5 empty] | 347047 | 395460.0565
0059 | Denham Oaks ES | 1994 | PRT | FOSM |  |  | 85110 | 851100059 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 200000 | 227900
9430 | District Wide |  | ATH | MAINT |  |  | 82054 | 820549430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 4 | 18/19 |  |  | 5 |  | 150000 | 170925
9430 | District Wide |  | ATH | MAINT |  |  | 82055 | 820559430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 4 | 19/20 |  |  | 6 |  | 150000 | 170925
9061 | District Wide |  | ATH | MAINT |  |  | 82014 | 820149061 | Annual Bleacher Repair ($100,000 Annually) | 4 | 18/19 |  |  | 5 |  | 100000 | 113950
9061 | District Wide |  | ATH | MAINT |  |  | 82015 | 820159061 | Annual Bleacher Repair ($100,000 Annually) | 4 | 19/20 |  |  | 6 |  | 100000 | 113950
9031 | District Wide |  | FIN | FIN |  |  | 84214 | 842149031 | Annual Buses & Other Vehicles | 4 | 18/19 |  |  | 5 |  | 1700000 | 1937150
9031 | District Wide |  | FIN | FIN |  |  | 84215 | 842159031 | Annual Buses & Other Vehicles | 4 | 19/20 |  |  | 6 |  | 1700000 | 1937150
9061 | District Wide |  | FIN | FIN |  |  | 83244 | 832449061 | Annual Compliance w/Environmental Reg | 4 | 18/19 |  |  | 5 |  | 210161 | 239478.4595
9061 | District Wide |  | FIN | FIN |  |  | 83245 | 832459061 | Annual Compliance w/Environmental Reg | 4 | 19/20 |  |  | 6 |  | 210161 | 239478.4595
9061 | District Wide |  | FIN | FIN |  |  | 83264 | 832649061 | Annual Compliance with ADA | 4 | 14/17 |  |  | 5 |  | 150000 | 170925
9061 | District Wide |  | FIN | FIN |  |  | 83265 | 832659061 | Annual Compliance with ADA | 4 | 15/18 |  |  | 6 |  | 150000 | 170925
0000 | District Wide |  | FIN | FIN |  |  | 00004 | 000040000 | Annual Debt Service Payments | 4 | 18/19 |  |  | 5 |  | 38816856 | 44231807.412
0000 | District Wide |  | FIN | FIN |  |  | 00005 | 000050000 | Annual Debt Service Payments | 4 | 19/20 |  |  | 6 |  | 38816856 | 44231807.412
9061 | District Wide |  | PRT | MAINT |  |  | 86164 | 861649061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 4 | 18/19 |  |  | 5 |  | 850000 | 968575
9061 | District Wide |  | PRT | MAINT |  |  | 86165 | 861659061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 4 | 19/20 |  |  | 6 |  | 850000 | 968575
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 4 | 18/19 |  |  | 5 |  | 50000 | 56975
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 4 | 19/20 |  |  | 6 |  | 50000 | 56975
9061 | District Wide |  | PRT | MAINT |  |  | 85184 | 851849061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 4 | 18/19 |  |  | 5 |  | 200000 | 227900
9061 | District Wide |  | PRT | MAINT |  |  | 85185 | 851859061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 4 | 19/20 |  |  | 6 |  | 200000 | 227900
9019 | District Wide |  | PRT | CS&CC |  |  | 85184 | 851849019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 4 | 18/19 |  |  | 5 |  | 500000 | 569750
9019 | District Wide |  | PRT | CS&CC |  |  | 85185 | 851859019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 4 | 19/20 |  |  | 6 |  | 500000 | 569750
9061 | District Wide |  | PRT | MAINT |  |  | 85124 | 851249061 | Annual Flooring Replacement | 4 | 18/19 |  |  | 5 |  | 300000 | 341850
9061 | District Wide |  | PRT | MAINT |  |  | 85125 | 851259061 | Annual Flooring Replacement | 4 | 19/20 |  |  | 6 |  | 300000 | 341850
9430 | District Wide |  | ATH | ATH |  |  | 82004 | 820049430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 4 | 18/19 |  |  | 5 |  | 60000 | 68370
9430 | District Wide |  | ATH | ATH |  |  | 82005 | 820059430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 4 | 19/20 |  |  | 6 |  | 60000 | 68370
9061 | District Wide |  | PRT | MAINT |  |  | 85114 | 851149061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 4 | 18/19 |  |  | 5 |  | 250000 | 284875
9061 | District Wide |  | PRT | MAINT |  |  | 85115 | 851159061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 4 | 19/20 |  |  | 6 |  | 250000 | 284875
9061 | District Wide |  | PRT | MAINT |  |  | 86184 | 861849061 | Annual Lift Station Upgrades ($100,000 Annually) | 4 | 18/19 |  |  | 5 |  | 200000 | 227900
9061 | District Wide |  | PRT | MAINT |  |  | 86185 | 861859061 | Annual Lift Station Upgrades ($100,000 Annually) | 4 | 19/20 |  |  | 6 |  | 200000 | 227900
9061 | District Wide |  | FIN | FIN |  |  | 85104 | 851049061 | Annual Maintenance & Repairs Projects (Small) | 4 | 18/19 |  |  | 5 |  | 1261000 | 1436909.5
9061 | District Wide |  | FIN | FIN |  |  | 85105 | 851059061 | Annual Maintenance & Repairs Projects (Small) | 4 | 19/20 |  |  | 6 |  | 1261000 | 1436909.5
9061 | District Wide |  | FIN | FIN |  |  | 83244 | 832449061 | Annual Maintenance Health & Safety | 4 | 18/19 |  |  | 5 |  | 210000 | 239295
9061 | District Wide |  | FIN | FIN |  |  | 83245 | 832459061 | Annual Maintenance Health & Safety | 4 | 19/20 |  |  | 6 |  | 210000 | 239295
9002 | District Wide |  | PRT | MAINT |  |  | 86114 | 861149002 | Annual Marquee Sign Replacements ($15,000 Annually) | 4 | 18/19 |  |  | 5 |  | 15000 | 17092.5
9002 | District Wide |  | PRT | MAINT |  |  | 86115 | 861159002 | Annual Marquee Sign Replacements ($15,000 Annually) | 4 | 19/20 |  |  | 6 |  | 15000 | 17092.5
9061 | District Wide |  | PRT | MAINT |  |  | 86144 | 861449061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 4 | 18/19 |  |  | 5 |  | 500000 | 569750
9061 | District Wide |  | PRT | MAINT |  |  | 86145 | 861459061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 4 | 19/20 |  |  | 6 |  | 500000 | 569750
9061 | District Wide |  | PRT | MAINT |  |  | 81004 | 810049061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 4 | 18/19 |  |  | 5 |  | 100000 | 113950
9061 | District Wide |  | PRT | MAINT |  |  | 81005 | 810059061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 4 | 19/20 |  |  | 6 |  | 100000 | 113950
9061 | District Wide |  | PRT | MAINT |  |  | 85224 | 852249061 | Annual Security Cameras & Alarms | 4 | 18/19 |  |  | 5 |  | 100000 | 113950
9061 | District Wide |  | PRT | MAINT |  |  | 85225 | 852259061 | Annual Security Cameras & Alarms | 4 | 19/20 |  |  | 6 |  | 100000 | 113950
9430 | District Wide |  | ATH | MAINT |  |  | 82044 | 820449430 | Annual Sound System Repairs ($75,000 Annually) | 4 | 18/19 |  |  | 5 |  | 75000 | 85462.5
9430 | District Wide |  | ATH | MAINT |  |  | 82045 | 820459430 | Annual Sound System Repairs ($75,000 Annually) | 4 | 19/20 |  |  | 6 |  | 75000 | 85462.5
9420 | District Wide |  | OTIS | OTIS |  |  | 84064 | 840649420 | Annual Technology and Equipment ( Student Computers) | 4 | 18/19 |  |  | 5 |  | 6000000 | 6837000
9420 | District Wide |  | OTIS | OTIS |  |  | 84065 | 840659420 | Annual Technology and Equipment ( Student Computers) | 4 | 19/20 |  |  | 6 |  | 6000000 | 6837000
9420 | District Wide |  | OTIS | OTIS |  |  | 84084 | 840849420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 4 | 18/19 |  |  | 5 |  | 1950000 | 2222025
9420 | District Wide |  | OTIS | OTIS |  |  | 84085 | 840859420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 4 | 19/20 |  |  | 6 |  | 1950000 | 2222025
9421 | District Wide |  | FIN | FIN |  |  | 83004 | 830049421 | Annual Telecommunications Repairs Projects (Small) | 4 | 18/19 |  |  | 5 |  | 800000 | 911600
9421 | District Wide |  | FIN | FIN |  |  | 83005 | 830059421 | Annual Telecommunications Repairs Projects (Small) | 4 | 19/20 |  |  | 6 |  | 800000 | 911600
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 4 | 18/19 |  |  | 5 |  | 200000 | 227900
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 4 | 19/20 |  |  | 6 |  | 200000 | 227900
0084 | Double Branch ES | 2007 | FNS | CS&CC |  |  | 85110 | 851100084 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0351 | Fox Hollow ES | 1990 | FNS | CS&CC |  |  | 85110 | 851100351 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  | 85110 | 851100991 | HVAC Replace 200 Ton Chiller | 4 | [5 empty] | 250000 | 284875
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  | 85110 | 851100991 | HVAC Replace Control System | 4 | [5 empty] | 400000 | 455800
0083 | Gulf Highlands ES | 2006 | FNS | CS&CC |  |  | 85110 | 851100083 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0331 | Gulf HS | 1971 | PRT | FOSM |  |  | 85110 | 851100331 | HVAC Replace (2) 250 Ton Chillers | 4 | [5 empty] | 500000 | 569750
0331 | Gulf HS | 1971 | ATH | MAINT |  |  | 85000 | 850000331 | Replace Wall Tile In PE Locker Room | 4 | [5 empty] | 15000 | 17092.5
0261 | Gulf MS | 1964 | ATH | ATH |  |  | 82000 | 820000261 | Sand & Paint Gym Floors | 4 | [5 empty] | 25000 | 28487.5
0301 | Hudson ES | 1966 | FNS | FNS |  |  | 84070 | 840700301 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0521 | Hudson HS | 1973 | PRT | FOSM |  |  | 85110 | 851100521 | HVAC Replace 200 Ton Chiller (Gym) | 4 | [5 empty] | 250000 | 284875
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT |  |  | 81150 | 811500073 | Storage Garage | 4 | [5 empty] | 25000 | 28487.5
0961 | Lake Myrtle ES | 1984 | FNS | FNS |  |  | 85250 | 852500961 | Serving Line Update - from RES | 4 | [5 empty] | 7383 | 8412.9285
0801 | Land O' Lakes HS | 1973 | PRT | FOSM |  |  | 85110 | 851100801 | HVAC Replace 200 Ton Chiller (Gym) | 4 | [5 empty] | 250000 | 284875
0801 | Land O' Lakes HS | 1973 | PRT | MAINT |  |  | 85200 | 852000801 | Roof Replacement | 4 | [5 empty] | 600000 | 683700
2081 | Longleaf ES | 2005 | FNS | CS&CC |  |  | 85110 | 851102081 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0941 | Moon Lake ES | 1982 | PRT | CS&CC |  |  | 86100 | 861000941 | Remodel Bld #1 | 4 |  |  |  | 8 |  | 5539200 | 6311918.4
0081 | Moore Mickens EC | 1952 | FNS | MAINT |  |  | 84070 | 840700081 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0092 | New River ES | 2007 | FNS | CS&CC |  |  | 85110 | 851100092 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0501 | Northwest ES | 1973 | FNS | FNS |  |  | 85250 | 852500501 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0082 | Oakstead ES | 2006 | FNS | CS&CC |  |  | 85110 | 851100082 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0902 | Pine View ES | 2003 | FNS | CS&CC |  |  | 85110 | 851100902 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  | 82000 | 820000931 | Sand & Paint Gym Floors | 4 | [5 empty] | 60000 | 68370
2061 | Sand Pine ES | 1998 | PRT | FOSM |  |  | 85110 | 851102061 | HVAC Replace (2) 100 Ton Chillers & Controls | 4 | [5 empty] | 580000 | 660910
2091 | Seven Oaks ES | 2005 | FNS | CS&CC |  |  | 85110 | 851102091 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  | 85250 | 852500411 | Serving Line Renovation | 4 | [5 empty] | 347047 | 395460.0565
0601 | Shady Hills ES | 1973 | FNS | FNS |  |  | 85250 | 852500601 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0032 | Trinity ES | 2000 | PRT | MAINT |  |  | 85200 | 852000032 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC |  |  | 85110 | 851100085 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0063 | Wesley Chapel HS | 1998 | PRT | MAINT |  |  | 85200 | 852000063 | Roof Maintenance | 4 | [5 empty] | 100000 | 113950
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT |  |  | 82050 | 820500090 | Overlay Courts - Basketball & Tennis | 4 | [5 empty] | 25000 | 28487.5
0131 | Zephyrhills HS | 1973 | FNS | FNS |  |  | 84070 | 840700131 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0113 | Anclote HS | 2009 | ATH | ATH |  |  | 82000 | 820000113 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0401 | Centennial ES | 1986 | FNS | CS&CC |  |  | 85110 | 851100401 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0100 | Charles S. Rushe MS | 2007 | ATH | ATH |  |  | 82050 | 820500100 | Resurface Track Courts | 5 | [5 empty] | 50000 | 59510
0100 | Charles S. Rushe MS | 2007 | ATH | ATH |  |  | 82000 | 820000100 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0070 | Chasco ES | 2000 | FNS | CS&CC |  |  | 85110 | 851100070 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0070 | Chasco ES | 2000 | PRT | FOSM |  |  | 85110 | 851100070 | HVAC (2) 300 ton chillers | 5 | [5 empty] | 600000 | 714120
0070 | Chasco ES | 2000 | FNS | CS&CC |  |  | 85250 | 852500070 | Kitchen Renovation | 5 | [5 empty] | 943483 | 1122933.4666
0069 | Chasco MS | 2001 | FNS | FNS |  |  | 86200 | 862000069 | Outside Dining Sun Shade | 5 | [5 empty] | 8000 | 9521.6
0069 | Chasco MS | 2001 | FNS | CS&CC |  |  | 85250 | 852500069 | Serving Line Renovation | 5 | [5 empty] | 811329.75 | 965644.6684
0060 | Chester Taylor ES | 1996 | FNS | FNS |  |  | 84070 | 840700060 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0103 | Crews Lake MS | 2008 | ATH | ATH |  |  | 82050 | 820500103 | Resurface Track Courts | 5 | [5 empty] | 50000 | 59510
0103 | Crews Lake MS | 2008 | ATH | ATH |  |  | 82000 | 820000103 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0421 | Deer Park ES | 1988 | FNS | CS&CC |  |  | 85110 | 851100421 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0059 | Denham Oaks ES | 1994 | FNS | FNS |  |  | 84070 | 840700059 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
9430 | District Wide |  | ATH | MAINT |  |  | 82056 | 820569430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 5 | 20/21 |  |  | 7 |  | 150000 | 178530
9430 | District Wide |  | ATH | MAINT |  |  | 82057 | 820579430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 5 | 21/22 |  |  | 8 |  | 150000 | 178530
9061 | District Wide |  | ATH | MAINT |  |  | 82016 | 820169061 | Annual Bleacher Repair ($100,000 Annually) | 5 | 20/21 |  |  | 7 |  | 100000 | 119020
9061 | District Wide |  | ATH | MAINT |  |  | 82017 | 820179061 | Annual Bleacher Repair ($100,000 Annually) | 5 | 21/22 |  |  | 8 |  | 100000 | 119020
9031 | District Wide |  | FIN | FIN |  |  | 84216 | 842169031 | Annual Buses & Other Vehicles | 5 | 20/21 |  |  | 7 |  | 1700000 | 2023340
9031 | District Wide |  | FIN | FIN |  |  | 84217 | 842179031 | Annual Buses & Other Vehicles | 5 | 21/22 |  |  | 8 |  | 1700000 | 2023340
9061 | District Wide |  | FIN | FIN |  |  | 83246 | 832469061 | Annual Compliance w/Environmental Reg | 5 | 20/21 |  |  | 7 |  | 210161 | 250133.6222
9061 | District Wide |  | FIN | FIN |  |  | 83247 | 832479061 | Annual Compliance w/Environmental Reg | 5 | 21/22 |  |  | 8 |  | 210161 | 250133.6222
9061 | District Wide |  | FIN | FIN |  |  | 83266 | 832669061 | Annual Compliance with ADA | 5 | 14/18 |  |  | 7 |  | 150000 | 178530
9061 | District Wide |  | FIN | FIN |  |  | 83267 | 832679061 | Annual Compliance with ADA | 5 | 15/19 |  |  | 8 |  | 150000 | 178530
0000 | District Wide |  | FIN | FIN |  |  | 00006 | 000060000 | Annual Debt Service Payments | 5 | 20/21 |  |  | 7 |  | 38816856 | 46199822.0112
0000 | District Wide |  | FIN | FIN |  |  | 00007 | 000070000 | Annual Debt Service Payments | 5 | 21/22 |  |  | 8 |  | 38816856 | 46199822.0112
9061 | District Wide |  | PRT | MAINT |  |  | 86166 | 861669061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 5 | 20/21 |  |  | 7 |  | 850000 | 1011670
9061 | District Wide |  | PRT | MAINT |  |  | 86167 | 861679061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 5 | 21/22 |  |  | 8 |  | 850000 | 1011670
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 5 | 20/21 |  |  | 7 |  | 50000 | 59510
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 5 | 21/22 |  |  | 8 |  | 50000 | 59510
9061 | District Wide |  | PRT | MAINT |  |  | 85186 | 851869061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 5 | 20/21 |  |  | 7 |  | 200000 | 238040
9061 | District Wide |  | PRT | MAINT |  |  | 85187 | 851879061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 5 | 21/22 |  |  | 8 |  | 200000 | 238040
9019 | District Wide |  | PRT | CS&CC |  |  | 85186 | 851869019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 5 | 20/21 |  |  | 7 |  | 500000 | 595100
9019 | District Wide |  | PRT | CS&CC |  |  | 85187 | 851879019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 5 | 21/22 |  |  | 8 |  | 500000 | 595100
9061 | District Wide |  | PRT | MAINT |  |  | 85126 | 851269061 | Annual Flooring Replacement | 5 | 20/21 |  |  | 7 |  | 300000 | 357060
9061 | District Wide |  | PRT | MAINT |  |  | 85127 | 851279061 | Annual Flooring Replacement | 5 | 21/22 |  |  | 8 |  | 300000 | 357060
9430 | District Wide |  | ATH | ATH |  |  | 82006 | 820069430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 5 | 20/21 |  |  | 7 |  | 60000 | 71412
9430 | District Wide |  | ATH | ATH |  |  | 82007 | 820079430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 5 | 21/22 |  |  | 8 |  | 60000 | 71412
9061 | District Wide |  | PRT | MAINT |  |  | 85116 | 851169061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 5 | 20/21 |  |  | 7 |  | 250000 | 297550
9061 | District Wide |  | PRT | MAINT |  |  | 85117 | 851179061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 5 | 21/22 |  |  | 8 |  | 250000 | 297550
9061 | District Wide |  | PRT | MAINT |  |  | 86186 | 861869061 | Annual Lift Station Upgrades ($100,000 Annually) | 5 | 20/21 |  |  | 7 |  | 200000 | 238040
9061 | District Wide |  | PRT | MAINT |  |  | 86187 | 861879061 | Annual Lift Station Upgrades ($100,000 Annually) | 5 | 21/22 |  |  | 8 |  | 200000 | 238040
9061 | District Wide |  | FIN | FIN |  |  | 85106 | 851069061 | Annual Maintenance & Repairs Projects (Small) | 5 | 20/21 |  |  | 7 |  | 1261000 | 1500842.2
9061 | District Wide |  | FIN | FIN |  |  | 85107 | 851079061 | Annual Maintenance & Repairs Projects (Small) | 5 | 21/22 |  |  | 8 |  | 1261000 | 1500842.2
9061 | District Wide |  | FIN | FIN |  |  | 83246 | 832469061 | Annual Maintenance Health & Safety | 5 | 20/21 |  |  | 7 |  | 210000 | 249942
9061 | District Wide |  | FIN | FIN |  |  | 83247 | 832479061 | Annual Maintenance Health & Safety | 5 | 21/22 |  |  | 8 |  | 210000 | 249942
9002 | District Wide |  | PRT | MAINT |  |  | 86116 | 861169002 | Annual Marquee Sign Replacements ($15,000 Annually) | 5 | 20/21 |  |  | 7 |  | 15000 | 17853
9002 | District Wide |  | PRT | MAINT |  |  | 86117 | 861179002 | Annual Marquee Sign Replacements ($15,000 Annually) | 5 | 21/22 |  |  | 8 |  | 15000 | 17853
9061 | District Wide |  | PRT | MAINT |  |  | 86146 | 861469061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 5 | 20/21 |  |  | 7 |  | 500000 | 595100
9061 | District Wide |  | PRT | MAINT |  |  | 86147 | 861479061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 5 | 21/22 |  |  | 8 |  | 500000 | 595100
9061 | District Wide |  | PRT | MAINT |  |  | 81006 | 810069061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 5 | 20/21 |  |  | 7 |  | 100000 | 119020
9061 | District Wide |  | PRT | MAINT |  |  | 81007 | 810079061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 5 | 21/22 |  |  | 8 |  | 100000 | 119020
9061 | District Wide |  | PRT | MAINT |  |  | 85226 | 852269061 | Annual Security Cameras & Alarms | 5 | 20/21 |  |  | 7 |  | 100000 | 119020
9061 | District Wide |  | PRT | MAINT |  |  | 85227 | 852279061 | Annual Security Cameras & Alarms | 5 | 21/22 |  |  | 8 |  | 100000 | 119020
9430 | District Wide |  | ATH | MAINT |  |  | 82046 | 820469430 | Annual Sound System Repairs ($75,000 Annually) | 5 | 20/21 |  |  | 7 |  | 75000 | 89265
9430 | District Wide |  | ATH | MAINT |  |  | 82047 | 820479430 | Annual Sound System Repairs ($75,000 Annually) | 5 | 21/22 |  |  | 8 |  | 75000 | 89265
9420 | District Wide |  | OTIS | OTIS |  |  | 84066 | 840669420 | Annual Technology and Equipment ( Student Computers) | 5 | 20/21 |  |  | 7 |  | 6000000 | 7141200
9420 | District Wide |  | OTIS | OTIS |  |  | 84067 | 840679420 | Annual Technology and Equipment ( Student Computers) | 5 | 21/22 |  |  | 8 |  | 6000000 | 7141200
9420 | District Wide |  | OTIS | OTIS |  |  | 84086 | 840869420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 5 | 20/21 |  |  | 7 |  | 1950000 | 2320890
9420 | District Wide |  | OTIS | OTIS |  |  | 84087 | 840879420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 5 | 21/22 |  |  | 8 |  | 1950000 | 2320890
9421 | District Wide |  | FIN | FIN |  |  | 83006 | 830069421 | Annual Telecommunications Repairs Projects (Small) | 5 | 20/21 |  |  | 7 |  | 800000 | 952160
9421 | District Wide |  | FIN | FIN |  |  | 83007 | 830079421 | Annual Telecommunications Repairs Projects (Small) | 5 | 21/22 |  |  | 8 |  | 800000 | 952160
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 5 | 20/21 |  |  | 7 |  | 200000 | 238040
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 5 | 21/22 |  |  | 8 |  | 200000 | 238040
9012 | District Wide |  | PLAN | PLAN |  |  | 89990 | 899909012 | Property Acquisition - Elementary site #2 in Wiregrass | 5 | [5 empty] | 750000 | 892650
0331 | Gulf HS | 1971 | ATH | CS&CC |  |  | 82020 | 820200331 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0911 | Gulfside ES | 1977 | FNS | CS&CC |  |  | 85110 | 851100911 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC |  |  | 00000 | 000000242 | Determine Long Range Use | 5 | [6 empty] | 0
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC |  |  | 85000 | 850000242 | Remodel School | 5 | [5 empty] | 266999 | 317782.2098
7071 | James Irvin EC | 1995 | CCTE | CS&CC |  |  | 86100 | 861007071 | Redevelopment of Campus | 5 | [5 empty] | 5000000 | 5951000
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC |  |  | 85110 | 851100065 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0065 | James M. Marlowe ES | 1999 | FNS | FNS |  |  | 84070 | 840700065 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC |  |  | 85250 | 852500065 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0961 | Lake Myrtle ES | 1984 | FNS | CS&CC |  |  | 85110 | 851100961 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82020 | 820200801 | Concession Stand Bathrooms - Baseball/Softball | 5 | [5 empty] | 250000 | 297550
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82020 | 820200801 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82020 | 820200801 | Renovate/Build Athletic Field House | 5 | [5 empty] | 1500000 | 1785300
0451 | Mary Giella ES | 1989 | FNS | CS&CC |  |  | 85110 | 851100451 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0081 | Moore Mickens EC | 1952 | PRT | CS&CC |  |  | 86100 | 861000081 | Redevelopment of Campus | 5 | [5 empty] | 5000000 | 5951000 |  | On Hold
9099 | New Elementary School |  | PLAN | CS&CC | Yes |  | 87099 | 870999099 | Elementary Q - 54 Corridor near Suncoast Parkway | 5 | [5 empty] | 20121372 | 23948456.9544
9099 | New Elementary School |  | PLAN | CS&CC | Yes |  | 87045 | 870459099 | Elementary U - Northwood | 5 | [5 empty] | 18597372 | 22134592.1544
0061 | Pasco ES | 1954 | FNS | FNS |  |  | 84070 | 840700061 | Cooler / Freezer | 5 | 13/14 | 3709 | 76103 |  |  | 80709 | 96059.8518
0031 | Pasco HS | 1964 | FNS | FNS |  |  | 84070 | 840700031 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0031 | Pasco HS | 1964 | PRT | FOSM |  |  | 85110 | 851100031 | HVAC Replace 250 ton chiller | 5 | [5 empty] | 250000 | 297550
0031 | Pasco HS | 1964 | FNS | CS&CC |  |  | 85250 | 852500031 | Serving Line Renovation | 5 | [5 empty] | 1079880 | 1285273.176
0071 | Pasco MS | 1946 | ATH | CS&CC |  |  | 82050 | 820500071 | Replace Gym Floor | 5 | [5 empty] | 175000 | 208285 |  |  | Gym Floor Synthetic Overlay just complete - does that replace this project?
0902 | Pine View ES | 2003 | PRT | MAINT |  |  | 85200 | 852000902 | Roof Maintenance | 5 | [5 empty] | 80000 | 95216
0921 | Pine View MS | 1977 | PRT | CS&CC |  |  | 86100 | 861000921 | Remodel School | 5 | [5 empty] | 15930180 | 18960100.236
0931 | Ridgewood HS | 1977 | PRT | MAINT |  |  | 85200 | 852000931 | Roof Replacement | 5 | [5 empty] | 400000 | 476080
2061 | Sand Pine ES | 1998 | FNS | CS&CC |  |  | 85110 | 851102061 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
2061 | Sand Pine ES | 1998 | FNS | CS&CC |  |  | 85250 | 852502061 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  | 85110 | 851100411 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0601 | Shady Hills ES | 1973 | FNS | CS&CC |  |  | 85250 | 852500601 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0101 | Sunlake HS | 2007 | ATH | ATH |  |  | 82000 | 820000101 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0072 | Sunray ES | 2000 | FNS | CS&CC |  |  | 85110 | 851100072 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0072 | Sunray ES | 2000 | FNS | CS&CC |  |  | 85250 | 852500072 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0461 | Thomas E. Weightman MS | 1990 | FNS | FNS |  |  | 84070 | 840700461 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
9032 | Transportation E | 1972 | PRT | CS&CC |  |  | 85000 | 850009032 | Remodel Interior | 5 | [5 empty] | 250000 | 297550
9035 | Transportation NW | 1979 | PRT | CS&CC |  |  | 86100 | 861009035 | Remodel Office Interior, Add Parking | 5 | [5 empty] | 2500000 | 2975500
9019 | Transportation SW |  | PRT | CS&CC |  |  | 86100 | 861009019 | Construction of New Facility | 5 | [5 empty] | 5500000 | 6546100
9033 | Transportation W | 1971 | PRT | CS&CC |  |  | 85000 | 850009033 | Remodel Interior, Add Paint Booth, Expand Parking | 5 | [5 empty] | 650000 | 773630
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH |  |  | 82000 | 820000090 | Sand & Paint Gym Floors | 5 | [5 empty] | 40000 | 47608
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH |  |  | 82040 | 820400090 | Scoreboard Replacement(s) | 5 | [5 empty] | 75000 | 89265
0131 | Zephyrhills HS | 1973 | ATH | CS&CC |  |  | 82020 | 820200131 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0131 | Zephyrhills HS | 1973 | ATH | MAINT |  |  | 82050 | 820500131 | Overlay Tennis Court | 5 | [5 empty] | 50000 | 59510
0901 | Anclote ES | 1973 | SCHOOL | CS&CC |  |  | 86190 | 861900901 | Covered Walkways | 6 | [5 empty] | 114696 | 142578.5976
0113 | Anclote HS | 2009 | FNS | CS&CC |  |  | 85250 | 852500113 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0342 | Bayonet Point MS | 1973 | SCHOOL | MAINT |  |  | 86190 | 861900342 | Covered Walkways | 6 | [5 empty] | 25000 | 31077.5
0932 | Calusa ES | 1979 | SCHOOL | CS&CC |  |  | 86190 | 861900932 | Covered Walkways | 6 | [5 empty] | 206000 | 256078.6
0074 | Centennial MS | 2001 | FNS | FNS |  |  | 84070 | 840700074 | Cooler / Freezer | 6 | 13/14 | 3709 | 89711 |  |  | 88779 | 110361.1749
0074 | Centennial MS | 2001 | SCHOOL | CS&CC |  |  | 86190 | 861900074 | Covered Walkways | 6 | [5 empty] | 130000 | 161603
0074 | Centennial MS | 2001 | PRT | FOSM |  |  | 85110 | 851100074 | HVAC Replace Control System | 6 | [5 empty] | 600000 | 745860
0100 | Charles S. Rushe MS | 2007 | FNS | CS&CC |  |  | 85250 | 852500100 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0070 | Chasco ES | 2000 | SCHOOL | MAINT |  |  | 85000 | 850000070 | Restroom for PE Classes | 6 | [5 empty] | 300000 | 372930 |  | New | Evaluating
0060 | Chester Taylor ES | 1996 | PRT | FOSM |  |  | 85110 | 851100060 | HVAC Replace Control System | 6 | [5 empty] | 400000 | 497240
0311 | Cotee River ES | 1993 | SCHOOL | CS&CC |  |  | 86190 | 861900311 | Covered Walkways | 6 | [5 empty] | 162000 | 201382.2
0103 | Crews Lake MS | 2008 | FNS | CS&CC |  |  | 85250 | 852500103 | Serving Line Renovation | 6 | [5 empty] | 2314818 | 2877550.2558
0701 | Cypress ES | 1973 | SCHOOL | CS&CC |  |  | 86190 | 861900701 | Covered Walkways | 6 | [5 empty] | 475000 | 590472.5
0059 | Denham Oaks ES | 1994 | SCHOOL | CS&CC |  |  | 86190 | 861900059 | Covered Walkways | 6 | [5 empty] | 135000 | 167818.5
9053 | District Complex |  | PRT | FOSM |  |  | 85110 | 851109053 | District Complex - Bulding 4 HVAC Replace Control System | 6 | [5 empty] | 200000 | 248620
9430 | District Wide |  | ATH | MAINT |  |  | 82058 | 820589430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 6 | 22/23 |  |  | 9 |  | 150000 | 186465
9430 | District Wide |  | ATH | MAINT |  |  | 82059 | 820599430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 6 | 23/24 |  |  | 10 |  | 150000 | 186465
9061 | District Wide |  | ATH | MAINT |  |  | 82018 | 820189061 | Annual Bleacher Repair ($100,000 Annually) | 6 | 22/23 |  |  | 9 |  | 100000 | 124310
9061 | District Wide |  | ATH | MAINT |  |  | 82019 | 820199061 | Annual Bleacher Repair ($100,000 Annually) | 6 | 23/24 |  |  | 10 |  | 100000 | 124310
9031 | District Wide |  | FIN | FIN |  |  | 84218 | 842189031 | Annual Buses & Other Vehicles | 6 | 22/23 |  |  | 9 |  | 1700000 | 2113270
9031 | District Wide |  | FIN | FIN |  |  | 84219 | 842199031 | Annual Buses & Other Vehicles | 6 | 23/24 |  |  | 10 |  | 1700000 | 2113270
9061 | District Wide |  | FIN | FIN |  |  | 83248 | 832489061 | Annual Compliance w/Environmental Reg | 6 | 22/23 |  |  | 9 |  | 210161 | 261251.1391
9061 | District Wide |  | FIN | FIN |  |  | 83249 | 832499061 | Annual Compliance w/Environmental Reg | 6 | 23/24 |  |  | 10 |  | 210161 | 261251.1391
9061 | District Wide |  | FIN | FIN |  |  | 83268 | 832689061 | Annual Compliance with ADA | 6 | 14/19 |  |  | 9 |  | 150000 | 186465
9061 | District Wide |  | FIN | FIN |  |  | 83269 | 832699061 | Annual Compliance with ADA | 6 | 15/20 |  |  | 10 |  | 150000 | 186465
0000 | District Wide |  | FIN | FIN |  |  | 00008 | 000080000 | Annual Debt Service Payments | 6 | 22/23 |  |  | 9 |  | 38816856 | 48253233.6936
0000 | District Wide |  | FIN | FIN |  |  | 00009 | 000090000 | Annual Debt Service Payments | 6 | 23/24 |  |  | 10 |  | 38816856 | 48253233.6936
9061 | District Wide |  | PRT | MAINT |  |  | 86168 | 861689061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 6 | 22/23 |  |  | 9 |  | 850000 | 1056635
9061 | District Wide |  | PRT | MAINT |  |  | 86169 | 861699061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 6 | 23/24 |  |  | 10 |  | 850000 | 1056635
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 6 | 22/23 |  |  | 9 |  | 50000 | 62155
9061 | District Wide |  | PRT | MAINT |  |  |  |  | Annual Fencing Repair and Upgrade | 6 | 23/24 |  |  | 10 |  | 50000 | 62155
9061 | District Wide |  | PRT | MAINT |  |  | 85188 | 851889061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 6 | 22/23 |  |  | 9 |  | 200000 | 248620
9061 | District Wide |  | PRT | MAINT |  |  | 85189 | 851899061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 6 | 23/24 |  |  | 10 |  | 200000 | 248620
9019 | District Wide |  | PRT | CS&CC |  |  | 85188 | 851889019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 6 | 22/23 |  |  | 9 |  | 500000 | 621550
9019 | District Wide |  | PRT | CS&CC |  |  | 85189 | 851899019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 6 | 23/24 |  |  | 10 |  | 500000 | 621550
9061 | District Wide |  | PRT | MAINT |  |  | 85128 | 851289061 | Annual Flooring Replacement | 6 | 22/23 |  |  | 9 |  | 300000 | 372930
9061 | District Wide |  | PRT | MAINT |  |  | 85129 | 851299061 | Annual Flooring Replacement | 6 | 23/24 |  |  | 10 |  | 300000 | 372930
9430 | District Wide |  | ATH | ATH |  |  | 82008 | 820089430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 6 | 22/23 |  |  | 9 |  | 60000 | 74586
9430 | District Wide |  | ATH | ATH |  |  | 82009 | 820099430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 6 | 23/24 |  |  | 10 |  | 60000 | 74586
9061 | District Wide |  | PRT | MAINT |  |  | 85118 | 851189061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 6 | 22/23 |  |  | 9 |  | 250000 | 310775
9061 | District Wide |  | PRT | MAINT |  |  | 85119 | 851199061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 6 | 23/24 |  |  | 10 |  | 250000 | 310775
9061 | District Wide |  | PRT | MAINT |  |  | 86188 | 861889061 | Annual Lift Station Upgrades ($100,000 Annually) | 6 | 22/23 |  |  | 9 |  | 200000 | 248620
9061 | District Wide |  | PRT | MAINT |  |  | 86189 | 861899061 | Annual Lift Station Upgrades ($100,000 Annually) | 6 | 23/24 |  |  | 10 |  | 200000 | 248620
9061 | District Wide |  | FIN | FIN |  |  | 85108 | 851089061 | Annual Maintenance & Repairs Projects (Small) | 6 | 22/23 |  |  | 9 |  | 1261000 | 1567549.1
9061 | District Wide |  | FIN | FIN |  |  | 85109 | 851099061 | Annual Maintenance & Repairs Projects (Small) | 6 | 23/24 |  |  | 10 |  | 1261000 | 1567549.1
9061 | District Wide |  | FIN | FIN |  |  | 83248 | 832489061 | Annual Maintenance Health & Safety | 6 | 22/23 |  |  | 9 |  | 210000 | 261051
9061 | District Wide |  | FIN | FIN |  |  | 83249 | 832499061 | Annual Maintenance Health & Safety | 6 | 23/24 |  |  | 10 |  | 210000 | 261051
9002 | District Wide |  | PRT | MAINT |  |  | 86118 | 861189002 | Annual Marquee Sign Replacements ($15,000 Annually) | 6 | 22/23 |  |  | 9 |  | 15000 | 18646.5
9002 | District Wide |  | PRT | MAINT |  |  | 86119 | 861199002 | Annual Marquee Sign Replacements ($15,000 Annually) | 6 | 23/24 |  |  | 10 |  | 15000 | 18646.5
9061 | District Wide |  | PRT | MAINT |  |  | 86148 | 861489061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 6 | 22/23 |  |  | 9 |  | 500000 | 621550
9061 | District Wide |  | PRT | MAINT |  |  | 86149 | 861499061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 6 | 23/24 |  |  | 10 |  | 500000 | 621550
9061 | District Wide |  | PRT | MAINT |  |  | 81008 | 810089061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 6 | 22/23 |  |  | 9 |  | 100000 | 124310
9061 | District Wide |  | PRT | MAINT |  |  | 81009 | 810099061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 6 | 23/24 |  |  | 10 |  | 100000 | 124310
9061 | District Wide |  | PRT | MAINT |  |  | 85228 | 852289061 | Annual Security Cameras & Alarms | 6 | 22/23 |  |  | 9 |  | 100000 | 124310
9061 | District Wide |  | PRT | MAINT |  |  | 85229 | 852299061 | Annual Security Cameras & Alarms | 6 | 23/24 |  |  | 10 |  | 100000 | 124310
9430 | District Wide |  | ATH | MAINT |  |  | 82048 | 820489430 | Annual Sound System Repairs ($75,000 Annually) | 6 | 22/23 |  |  | 9 |  | 75000 | 93232.5
9430 | District Wide |  | ATH | MAINT |  |  | 82049 | 820499430 | Annual Sound System Repairs ($75,000 Annually) | 6 | 23/24 |  |  | 10 |  | 75000 | 93232.5
9420 | District Wide |  | OTIS | OTIS |  |  | 84068 | 840689420 | Annual Technology and Equipment ( Student Computers) | 6 | 22/23 |  |  | 9 |  | 6000000 | 7458600
9420 | District Wide |  | OTIS | OTIS |  |  | 84069 | 840699420 | Annual Technology and Equipment ( Student Computers) | 6 | 23/24 |  |  | 10 |  | 6000000 | 7458600
9420 | District Wide |  | OTIS | OTIS |  |  | 84088 | 840889420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 6 | 22/23 |  |  | 9 |  | 1950000 | 2424045
9420 | District Wide |  | OTIS | OTIS |  |  | 84089 | 840899420 | Annual Technology and Equipment (Admin Computers, Servers, Software) | 6 | 23/24 |  |  | 10 |  | 1950000 | 2424045
9421 | District Wide |  | FIN | FIN |  |  | 83008 | 830089421 | Annual Telecommunications Repairs Projects (Small) | 6 | 22/23 |  |  | 9 |  | 800000 | 994480
9421 | District Wide |  | FIN | FIN |  |  | 83009 | 830099421 | Annual Telecommunications Repairs Projects (Small) | 6 | 23/24 |  |  | 10 |  | 800000 | 994480
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 6 | 22/23 |  |  | 9 |  | 200000 | 248620
9421 | District Wide |  | OTIS | OTIS |  |  |  |  | Annual Telephone Repair | 6 | 23/24 |  |  | 10 |  | 200000 | 248620
9012 | District Wide |  | PLAN | PLAN |  |  | 89990 | 899909012 | Property Acquisition - Elementary site #3 in Wiregrass | 6 | [5 empty] | 750000 | 932325
0084 | Double Branch ES | 2007 | FNS | FNS |  |  | 85250 | 852500084 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 583619 | 725496.7789
0086 | Dr. John Long MS | 2006 | FNS | CS&CC |  |  | 85250 | 852500086 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0114 | Fivay HS | 2010 | FNS | CS&CC |  |  | 85250 | 852500114 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0351 | Fox Hollow ES | 1990 | FNS | FNS |  |  | 84070 | 840700351 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0083 | Gulf Highlands ES | 2006 | FNS | FNS |  |  | 85250 | 852500083 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 583619 | 725496.7789
0331 | Gulf HS | 1971 | PRT | MAINT |  |  | 85120 | 851200331 | Replace Quarry Tile throughout campus | 6 | [5 empty] | 355000 | 441300.5
0261 | Gulf MS | 1964 | FNS | CS&CC |  |  | 85250 | 852500261 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0093 | Gulf Trace ES | 2008 | FNS | FNS |  |  | 85250 | 852500093 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 641980 | 798045.338
0911 | Gulfside ES | 1977 | SCHOOL | CS&CC |  |  | 86190 | 861900911 | Covered Walkways - 224' each side of school | 6 | [5 empty] | 0 | 0 |  | New
0242 | Harry Schwettman EC | 1923 | FNS | CS&CC |  |  | 85250 | 852500242 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0521 | Hudson HS | 1973 | CCTE | CS&CC |  |  | 85230 | 852300521 | Agriculture Barn for Vet Assisting Program | 6 | [5 empty] | 50000 | 62155
0073 | J.W. Mitchell HS | 2000 | SCHOOL | CS&CC |  |  | 86190 | 861900073 | Covered Walkways | 6 | [5 empty] | 150000 | 186465
7071 | James Irvin EC | 1995 | SCHOOL | CS&CC |  |  | 86190 | 861907071 | Covered Walkways | 6 | [5 empty] | 135600 | 168564.36
2081 | Longleaf ES | 2005 | FNS | FNS |  |  | 85250 | 852502081 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 530562 | 659541.6222
0451 | Mary Giella ES | 1989 | SCHOOL | CS&CC |  |  | 86190 | 861900451 | Covered Walkways | 6 | [5 empty] | 110000 | 136741
0092 | New River ES | 2007 | FNS | FNS |  |  | 85250 | 852500092 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 641980 | 798045.338
0501 | Northwest ES | 1973 | FNS | CS&CC |  |  | 85250 | 852500501 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0082 | Oakstead ES | 2006 | FNS | FNS |  |  | 84070 | 840700082 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0082 | Oakstead ES | 2006 | FNS | CS&CC |  |  | 85250 | 852500082 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0089 | Paul R. Smith MS | 2006 | FNS | FNS |  |  | 86200 | 862000089 | Outside Dining Sun Shade | 6 | [5 empty] | 10000 | 12431
0089 | Paul R. Smith MS | 2006 | FNS | CS&CC |  |  | 85250 | 852500089 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0902 | Pine View ES | 2003 | FNS | FNS |  |  | 84070 | 840700902 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0902 | Pine View ES | 2003 | SCHOOL | CS&CC |  |  | 86190 | 861900902 | Covered Walkways | 6 | [5 empty] | 30000 | 37293
0902 | Pine View ES | 2003 | FNS | CS&CC |  |  | 85250 | 852500902 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0921 | Pine View MS | 1977 | FNS | FNS |  |  | 84070 | 840700921 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  | 86190 | 861900921 | Covered Walkways - Car Loop | 6 | [5 empty] | 418000 | 519615.8
0361 | Quail Hollow ES | 1975 | FNS | CS&CC |  |  | 85110 | 851100361 | A/C Renovation To Kitchen | 6 | [5 empty] | 204750 | 254524.725
0361 | Quail Hollow ES | 1975 | FNS | FNS |  |  | 84070 | 840700361 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0361 | Quail Hollow ES | 1975 | SCHOOL | MAINT |  |  | 86190 | 861900361 | Covered Walkways | 6 | [5 empty] | 55000 | 68370.5
0361 | Quail Hollow ES | 1975 | FNS | CS&CC |  |  | 85250 | 852500361 | Kitchen Renovation | 6 | [5 empty] | 1037831 | 1290127.7161
0361 | Quail Hollow ES | 1975 | PRT | CS&CC |  |  | 86150 | 861500361 | Traffic Safety and Parking Improvements | 6 | [5 empty] | 210000 | 261051
0102 | R.B. Stewart MS | 1926 | FNS | FNS |  |  | 84070 | 840700102 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0931 | Ridgewood HS | 1977 | ATH | CS&CC |  |  | 82020 | 820200931 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 6 | [5 empty] | 2500000 | 3107750
0471 | River Ridge HS | 1990 | SCHOOL | CS&CC |  |  | 86190 | 861900471 | Covered Walkways | 6 | [5 empty] | 300000 | 372930
0471 | River Ridge HS | 1990 | PRT | FOSM |  |  | 85110 | 851100471 | HVAC Replace 450 Ton & 250 Ton Chillers | 6 | [5 empty] | 500000 | 621550
0472 | River Ridge MS | 1990 | SCHOOL | CS&CC |  |  | 86190 | 861900472 | Covered Walkways | 6 | [5 empty] | 166000 | 206354.6
2061 | Sand Pine ES | 1998 | FNS | FNS |  |  | 84070 | 840702061 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
2061 | Sand Pine ES | 1998 | SCHOOL | MAINT |  |  | 86190 | 861902061 | Covered Walkways | 6 | [5 empty] | 13000 | 16160.3
2091 | Seven Oaks ES | 2005 | FNS | FNS |  |  | 85250 | 852502091 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 530562 | 659541.6222
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  | 85250 | 852500411 | Cooler / Freezer with Renovations | 6 | [5 empty] | 340000 | 422654
0411 | Seven Springs ES | 1987 | SCHOOL | MAINT |  |  | 86190 | 861900411 | Covered Walkways | 6 | [5 empty] | 28980 | 36025.038
0057 | Seven Springs MS | 1995 | SCHOOL | CS&CC |  |  | 86200 | 862000057 | Covered Walkways | 6 | [5 empty] | 80000 | 99448
0101 | Sunlake HS | 2007 | FNS | CS&CC |  |  | 85250 | 852500101 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0072 | Sunray ES | 2000 | SCHOOL | MAINT |  |  | 86190 | 861900072 | Covered Walkways | 6 | [5 empty] | 30000 | 37293
0461 | Thomas E. Weightman MS | 1990 | SCHOOL | CS&CC |  |  | 86190 | 861900461 | Covered Walkways | 6 | [5 empty] | 194400 | 241658.64
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC |  |  | 85250 | 852500085 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0110 | Veterans ES | 2008 | FNS | FNS |  |  | 85250 | 852500110 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 706178 | 877849.8718
0063 | Wesley Chapel HS | 1998 | SCHOOL | MAINT |  |  | 86190 | 861900063 | Covered Walkways | 6 | [5 empty] | 20000 | 24862
0091 | West Zephyrhills ES | 1958 | SCHOOL | CS&CC |  |  | 86190 | 861900091 | Covered Walkways | 6 | [5 empty] | 220000 | 273482
0091 | West Zephyrhills ES | 1958 | PRT | FOSM |  |  | 85110 | 851100091 | HVAC Replace Control System | 6 | [5 empty] | 400000 | 497240
0090 | Wiregrass Ranch HS | 2006 | FNS | FNS |  |  | 84070 | 840700090 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0090 | Wiregrass Ranch HS | 2006 | FNS | CS&CC |  |  | 85250 | 852500090 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0132 | Woodland ES | 1977 | SCHOOL | CS&CC |  |  | 86190 | 861900132 | Covered Walkways | 6 | [5 empty] | 432000 | 537019.2
Priority Code | Year | Escalator | [6 empty] | Totals | All | [5 empty] | 1306352788.9975 | 1439922729.6709
1 | 12/13 - 13/14 | 0% | [6 empty] | Total for Priority 1 | 1 | [5 empty] | 328517286 | 328517286
2 | 14/15 - 15/16 | 4.45% | [6 empty] | Total for Priority 2 | 2 | [5 empty] | 180339180.2475 | 188364273.7685
3 | 16/17 - 17/18 | 9.09% | [6 empty] | Total for Priority 3 | 3 | [5 empty] | 254675210 | 277825186.589
4 | 18/19 - 19/20 | 13.95% | [6 empty] | Total for Priority 4 | 4 | [5 empty] | 165738323 | 188858819.0585
5 | 20/21 - 21/22 | 19.02% | [6 empty] | Total for Priority 5 | 5 | [5 empty] | 234299653.75 | 278863447.8932
6 | 22/23 - 23/24 | 24.31% | [6 empty] | Total for Priority 6 | 6 | [5 empty] | 142783136 | 177493716.3616
|  | = | 2013-2014 Budget Year Projects
|  | = | Penny for Pasco Projects
|  | = | Questions
|  | = | Proposed 14-15 Projects

## 13-14
Cost Center | School Name | Year Open | Request Dept | Assigned Dept | Large Cap Project | In-House Maint Prj | Large Cap Project | MUNIS | Concatenate | Project Description | Priority | Bgt Yr | FUND | AMT | Revised | Type | Budget Estimate | Adjusted Estimate | Final Cost | Status | Notes
0901 | Anclote ES | 1973 | PRT | MAINT |  |  |  | 85200 | 852000901 | Roof Replacement | 1 | 13/14 | 3101 3611 | 405000 | 1 |  | 405000 | 405000 |  | Design Requisition
0901 | Anclote ES | 1973 | PRT | MAINT |  |  |  | 84045 | 840450901 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | Part of Renovation
0342 | Bayonet Point MS | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000342 | Remodel School - Kelley School | 1 | 13/14 | 3921 | 15145250 | 1 | Penny Bond | 15150000 | 15150000
0342 | Bayonet Point MS | 1973 | PRT | MAINT |  |  |  | 85200 | 852000342 | Roof Replacement | 1 | [5 empty] | 1000000 | 1000000
0342 | Bayonet Point MS | 1973 | PRT | MAINT |  |  |  | 84045 | 840450342 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | Part of Renovation
0932 | Calusa ES | 1979 | PRT | MAINT |  |  |  | 84045 | 840450932 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000 |  | Complete
0401 | Centennial ES | 1986 | IS | CS&CC |  |  |  | 83000 | 830000401 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0401 | Centennial ES | 1986 | PRT | MAINT |  |  |  | 84045 | 840450401 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0069 | Centennial MS | 2001 | PRT | CS&CC |  |  |  | 85190 | 851900069 | EHPA Generator Shelter | 1 | 13/14 | 3712 | 50000 |  |  | 60000 | 60000 |  | Roll | Well and Sanitary Lift coded to Centennial ES 0401
0069 | Centennial MS | 2001 | FNS | MAINT |  |  |  | 84070 | 840700069 | Cooler/Freezer Flooding | 1 | 14/15 |  |  |  |  | 70000 | 70000
0069 | Centennial MS | 2001 | PRT | MAINT |  |  |  | 84045 | 840450069 | TV Installation in Classrooms | 1 | 14/15 |  |  |  |  | 125000 | 125000 |  | On Hold
0069 | Chasco MS | 2001 | PRT | MAINT |  |  |  | 85200 | 852000069 | Replace Gutters | 1 | 13/14 | 3101 | 91776 |  |  | 91250 | 91250 |  | Complete
0060 | Chester Taylor ES | 1996 | PRT | MAINT |  |  |  | 84045 | 840450060 | TV Installation in Classrooms | 1 | 14/15 |  |  |  |  | 100000 | 100000 |  | On Hold
0311 | Cotee River ES | 1993 | PRT | MAINT |  |  |  | 85250 | 852500311 | Roof Replacement | 1 | 13/14 | 3611 | 700000 |  |  | 700000 | 700000
0311 | Cotee River ES | 1993 | PRT | MAINT |  |  |  | 84045 | 840450311 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000 |  | Complete
0701 | Cypress ES | 1973 | PRT | MAINT |  |  |  | 85200 | 852000701 | Roof Replacement | 1 | 15/16 |  |  |  |  | 300000 | 300000
0701 | Cypress ES | 1973 | PRT | MAINT |  |  |  | 84045 | 840450701 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0421 | Deer Park ES | 1988 | IS | CS&CC |  |  |  | 83000 | 830000421 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0421 | Deer Park ES | 1988 | PRT | MAINT |  |  |  | 84045 | 840450421 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0059 | Denham Oaks ES | 1994 | PRT | MAINT |  |  |  | 84045 | 840450059 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000 |  | In Progress
9053 | District Complex | 1974 | PRT | CS&CC | Yes |  |  | 86100 | 861009053 | District Complex - Building 2 Architectural Design | 1 | 13/14 | 3900 | 300000 |  |  | 300000 | 300000 |  | In Progress
9053 | District Complex |  | PRT | CS&CC | Yes |  |  | 86100 | 861009053 | District Complex - Building 4 Remodel/Expansion | 1 | 13/14 | 3900 | 6748473 |  |  | 6511000 | 6511000 |  | Roll
9019 | District Wide |  | PRT | CS&CC |  |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 1 | 13/14 | 3709 | 250000 |  |  | 500000 | 500000
0000 | District Wide |  | FIN | FIN |  |  |  | 00000 | 000000000 | Annual Debt Service Payments | 1 | 13/14 | 3714 3903 3921 | 34821519 |  |  | 38816856 | 38816856
0000 | District Wide |  | FIN | FIN |  |  |  | 00000 | 000000000 | Property Insurance | 1 | 13/14 | 3714 | 827000 |  |  | 827000 | 827000
9012 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409012 | Annual FISH Signage | 1 | 13/14 | 3711 | 10000 |  |  | 10000 | 10000
9031 | District Wide |  | FIN | FIN |  |  |  | 84210 | 842109031 | Annual Buses | 1 | 13/14 | 3714 | 1500000 |  |  | 1700000 | 1700000
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 1 | 13/14 | 3709 | 202000 |  |  | 202000 | 202000
9061 | District Wide |  | FIN | FIN |  |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 1 | 13/14 | 3709 | 1212000 |  |  | 1212000 | 1212000
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 1 | 13/14 | 3709 | 202000 |  |  | 202000 | 202000
9421 | District Wide |  | FIN | FIN |  |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 1 | 13/14 | 3713 | 800000 |  |  | 800000 | 800000
9009 | District Wide |  | FIN | FIN |  |  |  | 84500 | 845009009 | ERP System | 1 | 13/14 | 3900 | 8854577 |  |  | 4777563 | 4777563
9021 | District Wide |  | FIN | FIN |  |  |  | 80010 | 800109021 | Annual Habitat for Humanity | 1 | 13/14 | 3904 | 100000 |  |  | 100000 | 100000
9426 | District Wide |  | FIN | FIN |  |  |  | 84510 | 845109426 | Quest Student Information System | 1 | 13/14 | 3921 | 11277535 |  |  | 11277535 | 11277535
9420 | District Wide |  | IS | IS |  |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 1 | 13/14 |  |  |  |  | 7785000 | 7785000
9002 | District Wide |  | ATH | MAINT |  |  |  | 83240 | 832409002 | Annual ADA Compliance/Bleacher Retrofit | 1 | 13/14 | 3611 | 50000 |  |  | 50000 | 50000
9002 | District Wide |  | MAINT | MAINT |  |  |  | 85000 | 850009002 | Annual Emergency Renovations & Remodeling | 1 | 13/14 | 3714 | 500000 |  |  | 500000 | 500000
9061 | District Wide |  | MAINT | MAINT |  |  |  | 85500 | 855009061 | Annual Energy Retrofits | 1 | 13/14 | 3611 | 100000 |  |  | 100000 | 100000
9002 | District Wide |  | PRT | MAINT |  |  |  | 85110 | 851109002 | Annual HVAC Equipment Replacements ($250,000 Annually) | 1 | 13/14 | 3712 | 250000 |  |  | 250000 | 250000
9002 | District Wide |  | PRT | MAINT |  |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 1 | 13/14 | 3711 | 15000 |  |  | 15000 | 15000
9002 | District Wide |  | MAINT | MAINT |  |  |  | 81150 | 811509002 | Annual Storage Buildings | 1 | 13/14 | 3712 | 15000 |  |  | 15000 | 15000
9061 | District Wide |  | ATH | MAINT |  |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 1 | 13/14 | 3710 | 100000 |  |  | 100000 | 100000
9061 | District Wide |  | PRT | MAINT |  |  |  | 85160 | 851609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 1 | 13/14 | 3709 | 725000 |  |  | 725000 | 725000
9061 | District Wide |  | PRT | MAINT |  |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 1 | 13/14 | 3709 | 200000 |  |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  |  | 85120 | 851209061 | Annual Flooring Replacement ($300,000 Annually) | 1 | 13/14 | 3713 | 150000 |  |  | 150000 | 150000
9061 | District Wide |  | PRT | MAINT |  |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 1 | 13/14 | 3709 | 100000 |  |  | 100000 | 100000
9061 | District Wide |  | PRT | MAINT |  |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 1 | 13/14 | 3712 | 350000 |  |  | 350000 | 350000
9061 | District Wide |  | PRT | MAINT |  |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 1 | 13/14 | 3714 | 200000 |  |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 1 | 13/14 | 3709 | 295000 |  |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms ($100,000 Annually) | 1 | 13/14 | 3708 | 100000 |  |  | 100000 | 100000
9430 | District Wide |  | ATH | MAINT |  |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 1 | 13/14 | 3709 | 150000 |  |  | 150000 | 150000
9430 | District Wide |  | ATH | MAINT |  |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 1 | 13/14 | 3708 | 60000 |  |  | 60000 | 60000
9430 | District Wide |  | ATH | MAINT |  |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 1 | 13/14 | 3713 | 75000 |  |  | 75000 | 75000
9002 | District Wide |  | PLAN | PLAN |  |  |  | 86000 | 860009002 | Property Acquisition - Elementary School Site in North Land O' Lakes area | 1 | 13/14 | 3904 | 750000 |  |  | 750000 | 750000 |  |  | Need to increase to $1.5 mill
9002 | District Wide |  | PLAN | PLAN |  |  |  | 86000 | 860009002 | Property Acquisition - Elementary Site in 54 Corridor in Odessa Area | 1 | 13/14 | 3904 | 2200000 |  |  | 2200000 | 2200000 |  |  | Added for 2nd elementary site - Ashley Glen and Smith 54
9002 | District Wide |  | PLAN | PLAN |  |  |  | 86000 | 860009002 | Property Acquisition - Elementary Site in 54 Corridor in Odessa Area - Elem "Q" | 1 | 13/14 | 3904 | 2200000 |  |  | 2200000 | 2200000 |  | Complete
9002 | District Wide |  | PLAN | PLAN |  |  |  | 86000 | 860009002 | Property Acquisition - High School Site in 54 Corridor in Odessa Area | 1 | 13/14 | 3904 | 2600000 |  |  | 2600000 | 2600000
9002 | District Wide |  | PLAN | PLAN |  |  |  | 86000 | 860009002 | Property Acquisition - If land becomes available next to existing school sites | 1 | 13/14 | 3904 | 250000 |  |  | 250000 | 250000
6997 | Energy Marine Center |  | MAINT | MAINT |  |  |  | 85200 | 852006997 | Roof Maintenance | 1 | 13/14 | 3101 | 60000 |  |  | 60000 | 60000 |  | Summer
0351 | Fox Hollow ES | 1990 | FNS | CS&CC |  |  |  | 85250 | 852500351 | Serving Line Renovation | 1 | 13/14 | 3713 | 194596 |  |  | 194596 | 194596 |  | In Progress
0351 | Fox Hollow ES | 1990 | IS | CS&CC |  |  |  | 83000 | 830000351 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0351 | Fox Hollow ES | 1990 | PRT | MAINT |  |  |  | 84045 | 840450351 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  |  | 85110 | 851100991 | HVAC Redesign/Replacement Fan Coil Units | 1 | [5 empty] | 1000000 | 1000000 |  |  | Added 9/23/13 Part of redevelopment?
0083 | Gulf Highlands ES | 2006 | PRT | MAINT |  |  |  | 84045 | 840450083 | TV Installation in Classrooms | 1 | 14/15 |  |  |  |  | 100000 | 100000 |  | On Hold
0331 | Gulf HS | 1971 | FNS | CS&CC |  |  |  | 84070 | 840700331 | Cooler / Freezer | 1 | 13/14 | 3709 |  |  |  | 9879 | 9879 |  | Summer
0331 | Gulf HS | 1971 | PRT | CS&CC | Yes |  |  | 85110 | 851100331 | HVAC Hydronic Boiler Replacement | 1 | 13/14 | 3709 3711 | 322281 |  |  | 330203 | 330203 | 150000 | Out for Bid
0331 | Gulf HS | 1971 | PRT | MAINT |  |  |  | 84045 | 840450331 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 150000 | 150000 |  | Roll
0261 | Gulf MS | 1964 | PRT | MAINT |  |  |  | 84045 | 840450261 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 125000 | 125000 |  | On Hold
0093 | Gulf Trace ES | 2008 | PRT | CS&CC |  |  |  | 86110 | 861100093 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3710 3711 3712 3713 3902 | 582703 |  |  | 90576 | 90576 |  | Complete | Need addl funding - $165,000 more than original $490,000
0911 | Gulfside ES | 1977 | PRT | MAINT |  |  |  | 85200 | 852000911 | Roofing Maintenance | 1 | 13/14 | 3101 | 60000 |  |  | 60000 | 60000 |  | Material Bid @ Purchasing
0911 | Gulfside ES | 1977 | PRT | MAINT |  |  |  | 84045 | 840450911 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0242 | Harry Schwettman EC | 1923 | PRT | MAINT |  |  |  | 85200 | 852000242 | Roof Coating | 1 | 13/14 | 3101 | 40000 |  |  | 40000 | 40000
0521 | Hudson HS | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500521 | Kitchen Renovation - Phase 1 | 1 |  |  |  |  | LCIF | 50000 | 50000 |  | On Hold | Floor Project Complete Merge with Renovation
0521 | Hudson HS | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500521 | Kitchen Renovation - Phase 2 | 1 | [5 empty] | 892462.725 | 892462.725 |  | On Hold | Floor Project Complete Merge with Renovation
0521 | Hudson HS | 1973 | PRT | MAINT |  |  |  | 84045 | 840450521 | TV Installation in Classrooms | 1 | [5 empty] | 150000 | 150000 |  | On Hold
0951 | Hudson MS | 1984 | FNS | CS&CC |  |  |  | 85250 | 852500951 | Kitchen & Serving Line Renovation | 1 | 13/14 | 3108 3713 | 995273 |  |  | 222769 | 222769 |  | Complete
0951 | Hudson MS | 1984 | PRT | MAINT |  |  |  | 84045 | 840450951 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | On Hold
0073 | J.W. Mitchell HS | 2000 | FNS | CS&CC |  |  |  | 85250 | 852500073 | Kitchen Renovation - Phase 2 | 1 | 13/14 | 3611 3709 | 1859973 |  |  | 1343003 | 1343003 |  | Complete
0073 | J.W. Mitchell HS | 2000 | PRT | MAINT |  |  |  | 84045 | 840450073 | TV Installation in Classrooms | 1 | 14/15 |  |  |  |  | 150000 | 150000 |  | On Hold
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT |  |  |  | 82050 | 820500073 | Overlay Courts - Tennis | 1 | 13/14 | 3711 | 35000 |  |  | 35000 | 35000 |  | Complete
7071 | James Irvin EC | 1995 | PRT | MAINT |  |  |  | 86110 | 861107071 | Sign Relocation/Replacement | 1 | 14/15 |  |  | 4/18/14 | [5 empty] | Due to SR 52 DOT work
0065 | James M. Marlowe ES | 1998 | PRT | MAINT |  |  |  | 84045 | 840450065 | TV Installation in Classrooms | 1 | 14/15 |  |  |  |  | 100000 | 100000 |  | On Hold
0321 | Lacoochee ES | 1971 | FNS | FNS |  |  |  | 86100 | 861000321 | Remodel - Add Multi-purpose Space | 1 | 13/14 | 3709 | 10000 |  |  | 10000 | 10000 |  | Complete
0961 | Lake Myrtle ES | 1984 | PRT | MAINT |  |  |  | 84045 | 840450961 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  |  | 82050 | 820500801 | Replace Gym Floor | 1 | 13/14 | 3708 | 71605 |  |  | 16093 | 16093 |  | Complete
0801 | Land O' Lakes HS | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000801 | Remodel School - Kelley School + Add Capacity | 1 |  | 3913 |  | 7 | Penny | 20600000 | 20600000
0801 | Land O' Lakes HS | 1973 | PRT | MAINT |  |  |  | 85200 | 852000801 | Roof Maintenance - SMS | 1 | 13/14 | 3101 | 100000 |  |  | 100000 | 100000 |  | Roll
2081 | Longleaf ES | 2005 | PRT | MAINT |  |  |  | 84045 | 840452081 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
9061 | Maintenance Dept Building |  | PRT | MAINT |  |  |  | 85200 | 852009061 | Roofing Maintenance | 1 | 13/14 | 3713 | 25000 |  |  | 25000 | 25000 |  | Roll
0451 | Mary Giella ES | 1989 | PRT | CS&CC | Yes |  |  | 86110 | 861100451 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3611 3713 | 381786 |  | Penny | 355826 | 355826 |  |  | Need to do in conjunction with Offsite Infrastructure Project
0451 | Mary Giella ES | 1989 | SCHOOL | MAINT |  |  |  | 85170 | 851700451 | Fencing - Installl 6' Chain Link Fence on Bus Loop Side | 1 | 14/15 |  |  |  |  | 25000 | 25000 |  | New
0451 | Mary Giella ES | 1989 | PRT | MAINT |  |  |  | 84045 | 840450451 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000 |  | Complete
0211 | Mittye P. Locke ES | 1966 | PRT | CS&CC |  |  |  | 83260 | 832600211 | Fire Egress Remodeling to Pre-K Building | 1 | 14/15 |  |  |  |  | 20000 | 20000 |  | TBD | Pre-K moving to Richey Elem?
0211 | Mittye P. Locke ES | 1966 | IS | CS&CC |  |  |  | 83000 | 830000211 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0941 | Moon Lake ES | 1982 | IS | CS&CC |  |  |  | 83000 | 830000941 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0941 | Moon Lake ES | 1982 | PRT | MAINT |  |  |  | 85200 | 852000941 | Roof Replacement | 1 | 14/15 |  |  |  |  | 500000 | 500000
0941 | Moon Lake ES | 1982 | PRT | MAINT |  |  |  | 84045 | 840450941 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0081 | Moore Mickens EC | 1952 | CTE | MAINT |  |  |  | 85000 | 850000081 | Remodel CNA Room | 1 | [5 empty] | 108000 | 108000
0081 | Moore Mickens EC | 1952 | CTE | MAINT |  |  |  | 85000 | 850000081 | Remodel Or Build New Space For Cosmetology | 1 | [5 empty] | 600000 | 600000 |  | On Hold
0081 | Moore Mickens EC | 1952 | MAINT | MAINT |  |  |  | 85200 | 852000081 | Roof Repair - Building 1 Metal Roof | 1 | 13/14 | 3101 | 60000 |  |  | 60000 | 60000
9099 | New Elementary School |  | PLAN | CS&CC | Yes |  | Yes | 87055 | 870559099 | Elementary W - Wiregrass | 1 | 14/15 | 3903 3921 | 17691000 |  | Penny & Other | 18801000 | 18801000
9099 | New High School |  | PLAN | CS&CC | Yes |  | Yes | 89020 | 890209099 | High School GGG - Old Pasco Road | 1 | 14/15 | 3904 | 28956000 |  | Impact Fees | 62700000 | 62700000
0501 | Northwest ES | 1973 | PRT | FOSM |  |  |  | 85110 | 851100501 | HVAC Redesign/Replacement Fan Coil Units | 1 | 13/14 | 3714 | 400000 |  |  | 400000 | 400000
0501 | Northwest ES | 1973 | PRT | MAINT |  |  |  | 84045 | 840450501 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0061 | Pasco ES | 1954 | IS | CS&CC |  |  |  | 83000 | 830000061 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | Merge with renovation
0031 | Pasco HS | 1964 | PRT | CS&CC | Yes |  |  | 86100 | 861000031 | Master Plan Redevelopment - Finish Road/Retaining Wall | 1 | 13/14 | 3903 | 330487 |  | Penny/Intrl | 385148 | 385148 | 250000 | In Progress
0031 | Pasco HS | 1964 | ATH | MAINT | Yes |  |  | 82020 | 820200031 | Football Stadium Concession Stands, Etc. | 1 | [8 empty] | Community Project / Donation
0071 | Pasco MS | 1946 | PRT | MAINT |  |  |  | 84045 | 840450071 | TV Installation in Classrooms - CCTE Building | 1 | 14/15 |  |  |  |  | 10000 | 10000
0902 | Pine View ES | 2003 | PRT | MAINT |  |  |  | 84045 | 840450902 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0921 | Pine View MS | 1977 | PRT | FOSM | Yes |  |  | 85110 | 851100921 | HVAC Renovation | 1 | 14/15 |  |  |  |  | 2800000 | 2800000
0921 | Pine View MS | 1977 | PRT | FOSM | Yes |  |  | 85110 | 851100921 | HVAC Renovation Design | 1 | 13/14 | 3611 | 200000 |  |  | 200000 | 200000
0921 | Pine View MS | 1977 | PRT | MAINT |  |  |  | 85200 | 852000921 | Roof Replacement | 1 | 14/15 |  |  |  |  | 900000 | 900000 |  | Re-allocate funds to CRES & PVMS HVAC Design | Schedule after HVAC Renovation
0361 | Quail Hollow ES | 1975 | PRT | CS&CC | Yes |  |  | 86100 | 861000361 | Remodel School - Kelley School + Add Capacity | 1 | 13/14 | 3921 | 10360000 |  | Penny | 11500000 | 11500000 |  | In Progress
0361 | Quail Hollow ES | 1975 | FNS | FNS |  |  |  | 85250 | 852500361 | Kitchen Hood - Code Violations | 1 | [5 empty] | 57881 | 57881 |  | Part of Renovation
0361 | Quail Hollow ES | 1975 | PRT | MAINT |  |  |  | 84045 | 840450361 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | Part of Renovation
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  |  | 86100 | 861000102 | Remodel Bld #4 #5 (Media And ESE) | 1 | 13/14 | 3903 |  |  |  | 1496472 | 1496472 |  | Complete | Combined with Gym Replacement in Priority 1
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  |  | 86100 | 861000102 | Replace Gym Bld #3 - Phase 1 | 1 | 13/14 | 3903 | 5547405 |  |  | 1400000 | 1400000 |  | Complete
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  |  | 86100 | 861000102 | Replace Gym Bld #3 - Phase 2 | 1 | 13/14 | 3903 |  |  |  | 1750000 | 1750000 |  | Complete | Need $1.4 million additional
0102 | R.B. Stewart MS | 1926 | PRT | MAINT |  |  |  | 84045 | 840450102 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000
0271 | Richey ES | 1958 | PRT | CS&CC |  |  |  | 86100 | 861000271 | Campus Redevelopment - Master Plan | 1 | 13/14 | 3900 3904 | 1761576 |  | Imp/Intrl | 760236 | 760236 |  | Complete
0931 | Ridgewood HS | 1977 | IS | CS&CC |  |  |  | 83000 | 830000931 | Technology Infrastructure Upgrades | 1 |  | 3913 |  |  |  | 800000 | 800000 |  |  | IS needs to prioritze
0931 | Ridgewood HS | 1977 | PRT | FOSM |  |  |  | 85110 | 851100931 | HVAC Renovation | 1 | 14/15 |  |  |  |  | 2200000 | 2200000 |  | Design | Will do in 13/14 if money available
0471 | River Ridge HS | 1990 | FNS | CS&CC |  |  |  | 85250 | 852500471 | Cafeteria Renovation - Phase 2 | 1 | 13/14 | 3611 3713 | 1866305 |  |  | 1086115 | 1086115 |  | Complete
0471 | River Ridge HS | 1990 | ATH | CS&CC |  |  |  | 82020 | 820200471 | Concession Stand Bathrooms - Baseball/Softball | 1 | 13/14 | 3710 | 280102 |  |  | 100000 | 100000 |  | Complete
0471 | River Ridge HS | 1990 | PRT | CS&CC | Yes |  |  | 85110 | 851100471 | HVAC Renovation (controls) | 1 | 13/14 | 3900 | 493880 |  |  | 493880 | 493880 |  | Roll
0471 | River Ridge HS | 1990 | CCTE | MAINT |  |  |  | 85000 | 850000471 | Open Doorway Between Engineering Rooms | 1 | [5 empty] | 50000 | 50000 |  | Hold | Olga will speak with Rob
0471 | River Ridge HS | 1990 | PRT | MAINT |  |  |  | 84045 | 840450471 | TV Installation in Classrooms | 1 | [5 empty] | 150000 | 150000 |  | On Hold
0472 | River Ridge MS | 1990 | PRT | MAINT |  |  |  | 84045 | 840450472 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | On Hold
0251 | San Antonio ES | 1981 | IS | CS&CC |  |  |  | 83000 | 830000251 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0251 | San Antonio ES | 1981 | PRT | MAINT |  |  |  | 84045 | 840450251 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
2061 | Sand Pine ES | 1998 | PRT | MAINT |  |  |  | 84045 | 840452061 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0201 | Sanders Memorial ES | 1944 | PRT | CS&CC | Yes |  |  | 86100 | 861000201 | Campus Redevelopment | 1 | 13/14 | 3900 3904 | 15718272 |  |  | 16902130 | 16902130 |  | Open 2015 | Site Work Completed
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  |  | 86100 | 861000341 | Replacement Bldg #1 - Phase 1 | 1 | 13/14 | 3900 |  |  | Interlocal | 6984000 | 6984000 |  | Summer
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  |  | 86100 | 861000341 | Replacement Bldg #1 - Phase 2 | 1 | 13/14 | 3900 | 13793027 |  |  | 6520000 | 6520000 |  | Roll
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  |  | 86100 | 861000341 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3900 | 432000 |  |  | 432000 | 432000 |  | Roll
0341 | Schrader ES | 1972 | PRT | MAINT |  |  |  | 84045 | 840450341 | TV Installation in Classrooms - Bld #9 | 1 | [5 empty] | 40000 | 40000 |  | On Hold
2091 | Seven Oaks ES | 2005 | PRT | MAINT |  |  |  | 84045 | 840452091 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0411 | Seven Springs ES | 1987 | PRT | MAINT |  |  |  | 84045 | 840450411 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0057 | Seven Springs MS | 1995 | PRT | CS&CC |  |  |  | 85110 | 851100057 | HVAC Chiller Pipe Replacement | 1 | 13/14 | 3611 | 721373 |  |  | 68774 | 68774 |  | Complete
0057 | Seven Springs MS | 1995 | IS | CS&CC |  |  |  | 83000 | 830000057 | Technology Infrastructure Upgrades | 1 | [5 empty] | 650000 | 650000 |  |  | IS needs to prioritze
0057 | Seven Springs MS | 1995 | FNS | FNS |  |  |  | 84070 | 840700057 | Cooler / Freezer | 1 | 13/14 | 3709 | 18819 |  |  | 184638 | 184638 |  | Summer
0057 | Seven Springs MS | 1995 | ATH | MAINT |  |  |  | 82050 | 820500057 | Basketball Court/Tennis Overlay | 1 | 13/14 | 3711 | 18635 |  |  | 6366 | 6366 |  | Complete
0057 | Seven Springs MS | 1995 | PRT | MAINT |  |  |  | 84048 | 840480057 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 125000 | 125000 |  | Complete
0601 | Shady Hills ES | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000601 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3709 3710 | 49972 |  |  | 28577 | 28577 |  | Design
0601 | Shady Hills ES | 1973 | PRT | CS&CC | Yes |  |  | 86100 | 861000601 | Remodel School - Kelley School + Add Capacity | 1 | 13/14 | 3921 | 10670000 |  | Penny | 11500000 | 11500000
0601 | Shady Hills ES | 1973 | PRT | MAINT |  |  |  | 85200 | 852000601 | Roof Replacement | 1 | [5 empty] | 300000 | 300000 |  | Not needed. Maintenance will find out when needs to be done. | Roll Funds into Remodel
0101 | Sunlake HS | 2007 | ATH | MAINT |  |  |  | 82020 | 820200101 | Add Air Conditioning To Field House | 1 | 13/14 | 3708 3710 3711 3713 | 109416 |  |  | 6108 | 6108 |  | Complete
0072 | Sunray ES | 2000 | PRT | MAINT |  |  |  | 84045 | 840450072 | TV Installation in Classrooms | 1 | 14/15 |  |  |  |  | 100000 | 100000 |  | On Hold
0461 | Thomas E. Weightman MS | 1990 | PRT | MAINT |  |  |  | 84045 | 840450461 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 125000 | 125000 |  | Roll
9035 | Transportation NW | 1979 | PRT | CS&CC |  |  |  | 86110 | 861109035 | Retention Pond and Flooding Repairs | 1 | 13/14 | 3713 | 56662 |  |  | 18891 | 18891 |  | Complete | Flooding issue as a result of Tropical Storm Debby. Need additional money another $90,000
9038 | Transportation SE |  | PRT | CS&CC |  |  |  | 86110 | 861109038 | Retention Pond and Flooding Repairs | 1 | 13/14 | 3713 | 58745 |  |  | 48713 | 48713 |  | Complete | Retention pond overflowing to neighboring property
9039 | Transportation SW |  | PRT | CS&CC |  |  |  | 86110 | 861109039 | Pre-Installation of Utilities | 1 | 13/14 | 3611 | 195000 |  |  | 218000 | 218000 |  | Roll | Install Utilities while Interlaken Road being constructed
0032 | Trinity ES | 2000 | MAINT | MAINT |  |  |  | 85200 | 852000032 | Replace Gutters | 1 | 13/14 | 3103 | 50000 |  |  | 50000 | 50000 |  | Roll
0032 | Trinity ES | 2000 | PRT | MAINT |  |  |  | 84045 | 840450032 | TV Installation in Classrooms | 1 | 14/15 |  |  |  |  | 100000 | 100000 |  | On Hold
0032 | Trinity ES | 2000 | FNS | MAINT |  |  |  | 85250 | 852500032 | Renovate Kitchen Floors | 1 | 13/14 | 3709 3711 | 84881 |  |  | 57881 | 57881 |  | Roll
0085 | Trinity Oaks ES | 2007 | PRT | CS&CC |  |  |  | 85110 | 851100085 | Add Dehumidification | 1 | 13/14 | 3709 3711 | 74148 |  |  | 1006 | 1006 |  | Complete
0063 | Wesley Chapel HS | 1998 | ATH | ATH |  |  |  | 82040 | 820400063 | Scoreboard Replacement(s) | 1 | [5 empty] | 75000 | 75000
0063 | Wesley Chapel HS | 1998 | CCTE | CS&CC |  |  |  | 85240 | 852400063 | Career Academy - Automotive | 1 | 13/14 | 3712 | 43499 |  |  | 16416 | 16416 |  | Complete | Carry Forward from 12/13
0063 | Wesley Chapel HS | 1998 | PRT | CS&CC |  |  |  | 85140 | 851400063 | Maintenance of Drainage Canal behind school complex | 1 | [5 empty] | 0 | 0
0063 | Wesley Chapel HS | 1998 | PRT | FOSM |  |  |  | 85110 | 851100063 | HVAC controls replacement phase 2 | 1 | 14/15 |  |  |  |  | 350000 | 350000
0063 | Wesley Chapel HS | 1998 | ATH | MAINT |  |  |  | 82050 | 820500063 | Overlay Courts | 1 | [5 empty] | 150000 | 150000
0063 | Wesley Chapel HS | 1998 | ATH | MAINT |  |  |  | 82020 | 820200063 | Add Air Conditioning To Field House | 1 | 13/14 | 3709 33710 3711 | 106499 |  |  | 6053 | 6053 |  | Complete
0091 | West Zephyrhills ES | 1958 | IS | CS&CC |  |  |  | 83000 | 830000091 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0091 | West Zephyrhills ES | 1958 | MAINT | MAINT |  |  |  | 85200 | 852000091 | Roof Replacement - Cafeteria and Media | 1 | 13/14 | 3101 | 301220 |  |  | 301220 | 301220 |  | Roll
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC | Yes |  |  | 86110 | 861100090 | Traffic Light @ Mansfield | 1 | 13/14 | 3611 | 125000 |  |  | 125000 | 125000 |  | Roll | Waiting on Developer
0090 | Wiregrass Ranch HS | 2006 | PRT | MAINT |  |  |  | 84045 | 840450090 | TV Installation in Classrooms - audio only | 1 | 14/15 |  |  |  |  | 51000 | 51000 |  | On Hold
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT |  |  |  | 82020 | 820200090 | Add Air Conditioning To Field House | 1 | 13/14 | 3708 3710 3711 | 106607 |  |  | 6162 | 6162 |  | Complete
0132 | Woodland ES | 1977 | PRT | MAINT |  |  |  | 83260 | 832600132 | Fencing - Install Aluminum Weld Fence at Front Entrance and to Clinic Safety Issue | 1 | 13/14 | 3611 |  |  |  | 21000 | 21000 |  | Complete
0132 | Woodland ES | 1977 | PRT | MAINT |  |  |  | 84045 | 840450132 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000 |  | Complete
0131 | Zephyrhills HS | 1973 | ATH | CS&CC | Yes |  |  | 82020 | 820200131 | Weight Room Renovation/Expansion | 1 | 13/14 | 3712 3903 |  |  |  | 468257 | 468257 |  | In Progress
0131 | Zephyrhills HS | 1973 | PRT | MAINT |  |  |  | 85110 | 851100131 | Rebuild Gym Air Handlers | 1 | 13/14 | 3900 |  |  |  | 89671 | 89671 |  | Summer
0901 | Anclote ES | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000901 | Remodel School - Kelley School + Add Capacity | 2 | 13/14 | 3921 | 11500000 |  |  | 11500000 | 12011750
0901 | Anclote ES | 1973 | IS | IS |  |  |  | 83000 | 830000901 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5 |  | Part of Renovation
0342 | Bayonet Point MS | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500342 | Cooler / Freezer with Renovations (Stock Room) | 2 | [5 empty] | 203963 | 213039.3535 |  | Part of Remodel
0342 | Bayonet Point MS | 1973 | ATH | MAINT |  |  |  | 85000 | 850000342 | Renovate Girls & Boys Locker Rooms | 2 | [5 empty] | 100000 | 104450 |  | Part of Renovation
0932 | Calusa ES | 1979 | FNS | CS&CC |  |  |  | 85250 | 852500932 | Cooler / Freezer with Renovations | 2 | [5 empty] | 203963 | 213039.3535
0932 | Calusa ES | 1979 | FNS | CS&CC |  |  |  | 85250 | 852500932 | Serving Line Renovation | 2 | [5 empty] | 286815 | 299578.2675
0932 | Calusa ES | 1979 | FNS | FNS |  |  |  | 85250 | 852500932 | Kitchen Hood | 2 | [5 empty] | 60775 | 63479.4875
0069 | Chasco MS | 2001 | FNS | FNS |  |  |  | 84070 | 840700069 | Cooler / Freezer | 2 | [5 empty] | 66701.25 | 69669.4556
0060 | Chester Taylor ES | 1996 | PRT | MAINT |  |  |  | 85200 | 852000060 | Roof Maintenance | 2 | [5 empty] | 80000 | 83560
0311 | Cotee River ES | 1993 | IS | IS |  |  |  | 83000 | 830000311 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0701 | Cypress ES | 1973 | FNS | FNS |  |  |  | 84070 | 840700701 | Cooler / Freezer | 2 | [5 empty] | 66701 | 69669.1945
9430 | District Wide |  | ATH | ATH |  |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 2 | [5 empty] | 120000 | 125340
9019 | District Wide |  | PRT | CS&CC |  |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 2 | [5 empty] | 1000000 | 1044500
0000 | District Wide |  | FIN | FIN |  |  |  | 00000 | 000000000 | Annual Debt Service Payments | 2 | 14/15 |  |  |  |  | 62938379 | 62938379
9031 | District Wide |  | FIN | FIN |  |  |  | 84210 | 842109031 | Annual Buses & Other Vehicles | 2 | 14/15 |  |  |  |  | 4225402 | 4413432.389
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 2 | 14/15 |  |  |  |  | 420322 | 439026.329
9061 | District Wide |  | FIN | FIN |  |  |  | 83260 | 832609061 | Annual Compliance with ADA | 2 | 14/15 |  |  |  |  | 300000 | 313350 |  |  | Added at the request of CS&CC
9061 | District Wide |  | FIN | FIN |  |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 2 | [5 empty] | 2521930 | 2634155.885
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 2 | [5 empty] | 420322 | 439026.329
9421 | District Wide |  | FIN | FIN |  |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 2 | [5 empty] | 1730736 | 1807753.752
9420 | District Wide |  | IS | IS |  |  |  | 84080 | 840809420 | Annual Technology and Equipment (Admin Computers) | 2 | 14/15
9420 | District Wide |  | IS | IS |  |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 2 | [5 empty] | 8532701 | 8912406.1945
9420 | District Wide |  | IS | IS |  |  |  | 84080 | 840809420 | Annual Technology and Equipment (Admin Computers) | 2 | [5 empty] | 8532702 | 8912407.239
9002 | District Wide |  | PRT | MAINT |  |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 2 | [5 empty] | 30000 | 31335
9061 | District Wide |  | ATH | MAINT |  |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 2 | 14/15 |  |  |  |  | 200000 | 208900
9061 | District Wide |  | PRT | MAINT |  |  |  | 86160 | 861609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 2 | [5 empty] | 1700000 | 1775650
9061 | District Wide |  | PRT | MAINT |  |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 2 | [5 empty] | 400000 | 417800
9061 | District Wide |  | PRT | MAINT |  |  |  | 85120 | 851209061 | Annual Flooring Replacement | 2 | [5 empty] | 600000 | 626700
9061 | District Wide |  | PRT | MAINT |  |  |  | 85110 | 851109061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 2 | [5 empty] | 500000 | 522250
9061 | District Wide |  | PRT | MAINT |  |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 2 | [5 empty] | 200000 | 208900
9061 | District Wide |  | PRT | MAINT |  |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 2 | [5 empty] | 1000000 | 1044500
9061 | District Wide |  | PRT | MAINT |  |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 2 |  | 3913 |  |  |  | 400000 | 417800
9061 | District Wide |  | PRT | MAINT |  |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 2 | [5 empty] | 200000 | 208900
9061 | District Wide |  | PRT | MAINT |  |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms | 2 | [5 empty] | 200000 | 208900
9430 | District Wide |  | ATH | MAINT |  |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 2 | 14/15 |  |  |  |  | 300000 | 313350
9430 | District Wide |  | ATH | MAINT |  |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 2 | [5 empty] | 150000 | 156675
0084 | Double Branch ES | 2007 | PRT | CS&CC |  |  |  | 86150 | 861500084 | Traffic Safety and Parking Improvements - Add Turn Lane to Chauncey | 2 | 14/15 |  |  | 1 |  | 500000 | 522250 |  | Design is funded | County beginning design of extension
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel Automotive Technology | 2 | 13/14 | 3921 |  | 1 |  | 1500000 | 1566750
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel Carpentry & Vet Assisting Program to HVAC Program | 2 | 13/14 | 3921 |  | 1 |  | 700000 | 731150
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel Commercial Art Room | 2 | 13/14 | 3921 |  | 1 |  | 110000 | 114895
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel Cosmetology Room | 2 | 13/14 | 3921 |  | 1 |  | 1007000 | 1051811.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel Culinary Arts Room | 2 | 13/14 | 3921 |  | 1 |  | 1200000 | 1253400
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel Electricity Room | 2 | 13/14 | 3921 |  | 1 |  | 415000 | 433467.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel HVAC Program Room | 2 | 13/14 | 3921 |  | 1 |  | 530000 | 553585
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel Marine Service Technology Program | 2 | 13/14 | 3921 |  | 1 |  | 300000 | 313350
0991 | Fred K. Marchman EC | 1984 | PRT | CS&CC |  |  |  | 86100 | 861000991 | Remodel School | 2 | 13/14 | 3921 |  | 1 |  | 518529 | 541603.5405
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Remodel TV Production Space | 2 | 13/14 | 3921 |  | 1 |  | 80000 | 83560
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Renovate Autobody Repair Bld., New Paint Booth, Paint Mixing Room, Frame Straightener, Welding Booth | 2 | 13/14 | 3921 |  | 1 |  | 500000 | 522250
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  |  | 86100 | 861000991 | Sign - New Marquee | 2 | 13/14 | 3921 |  | 1 |  | 7000 | 7311.5
0331 | Gulf HS | 1971 | ATH | ATH |  |  |  | 82040 | 820400331 | Scoreboard Replacement(s) | 2 | 13/14 | 3709 3713 |  |  |  | 40000 | 41780
0261 | Gulf MS | 1964 | PRT | MAINT |  |  |  | 85000 | 850000261 | Renovate Restroom Bld #17 | 2 | [5 empty] | 100000 | 104450
0911 | Gulfside ES | 1977 | IS | IS |  |  |  | 83000 | 830000911 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0301 | Hudson ES | 1966 | PRT | CS&CC |  |  |  | 85000 | 850000301 | Remodel Restrooms ADA | 2 |  |  |  | 1 |  | 700000 | 731150
0301 | Hudson ES | 1966 | IS | IS |  |  |  | 83000 | 830000301 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0301 | Hudson ES | 1966 | FNS | MAINT |  |  |  | 85250 | 852500301 | Kitchen Floor Renovation | 2 | [5 empty] | 35280 | 36849.96
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  |  | 82020 | 820200521 | Concession Stand Bathrooms - Baseball/Softball | 2 | [5 empty] | 250000 | 261125
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  |  | 82020 | 820200521 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 2 | [5 empty] | 2500000 | 2611250
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  |  | 82020 | 820200521 | Renovate/Build Athletic Field House | 2 | [5 empty] | 1000000 | 1044500
0951 | Hudson MS | 1984 | IS | IS |  |  |  | 83000 | 830000951 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 650000 | 678925
0321 | Lacoochee ES | 1971 | FNS | CS&CC |  |  |  | 85250 | 852500321 | Kitchen Renovation | 2 | [5 empty] | 708852 | 740395.914
0321 | Lacoochee ES | 1971 | FNS | FNS |  |  |  | 85250 | 852500321 | Kitchen Hood | 2 | [5 empty] | 60775 | 63479.4875
0321 | Lacoochee ES | 1971 | IS | IS |  |  |  | 83000 | 830000321 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500801 | Cooler / Freezer with Renovations | 2 | [5 empty] | 203963 | 213039.3535
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500801 | Serving Line Renovation | 2 | [5 empty] | 981708.9975 | 1025395.0479
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  |  | 82050 | 820500801 | Baseball and Dugout Reconstruction | 2 | [5 empty] | 100000 | 104450
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  |  | 82050 | 820500801 | Lighting - Replace Baseball Field | 2 | [5 empty] | 100000 | 104450
0451 | Mary Giella ES | 1989 | PRT | FOSM |  |  |  | 85110 | 851100451 | HVAC Replace Air Handlers & Controls | 2 | [5 empty] | 2500000 | 2611250
0211 | Mittye P. Locke ES | 1966 | FNS | CS&CC |  |  |  | 85250 | 852500211 | Kitchen Renovation | 2 |  |  |  | 3 |  | 708852 | 740395.914
0941 | Moon Lake ES | 1982 | FNS | CS&CC |  |  |  | 85110 | 851100941 | A/C Renovation To Kitchen | 2 | [5 empty] | 204750 | 213861.375
0941 | Moon Lake ES | 1982 | FNS | CS&CC |  |  |  | 85250 | 852500941 | Serving Line Renovation | 2 | [5 empty] | 286815 | 299578.2675
0081 | Moore Mickens EC | 1952 | PRT | MAINT |  |  |  | 85000 | 850000081 | Remodel School | 2 | [5 empty] | 445419 | 465240.1455
0501 | Northwest ES | 1973 | FNS | MAINT |  |  |  | 85250 | 852500501 | Kitchen Floor Renovation | 2 | [5 empty] | 35280 | 36849.96
0061 | Pasco ES | 1954 | PRT | CS&CC |  |  |  | 86100 | 861000061 | Renovate Bld #1-7, #9, #20, #21, #41 | 2 | 13/14 | 3921 | 5614560 | 1 |  | 5614560 | 5864407.92 |  |  | added Bld 9 to include cafeteria serving line renovation
0031 | Pasco HS | 1964 | ATH | CS&CC |  |  |  | 82050 | 820500031 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 2 |  |  |  | 1 |  | 2500000 | 2611250
0031 | Pasco HS | 1964 | ATH | MAINT |  |  |  | 82050 | 820500031 | Lighting - Replace Baseball Field | 2 | [5 empty] | 100000 | 104450
0921 | Pine View MS | 1977 | ATH | ATH |  |  |  | 82050 | 820500921 | Track Overlay | 2 | [5 empty] | 40000 | 41780
0921 | Pine View MS | 1977 | ATH | MAINT |  |  |  | 82050 | 820500921 | Overlay Outdoor Courts | 2 | [5 empty] | 30000 | 31335
0021 | R. B. Cox ES | 1925 | PRT | CS&CC |  |  |  | 86100 | 861000021 | Remodel School - Build New Cafeteria, Tear Down Old Cafeteria, Remove Concrete Portables, Traffic And Parking Improvements, Replace Remaining Old Windows, Install Securtiy System | 2 | 13/14 | 3921 | 7500000 | 1 |  | 6510441 | 6800155.6245
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  |  | 82040 | 820400931 | Scoreboard Replacement(s) | 2 | [5 empty] | 25000 | 26112.5
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  |  | 82050 | 820500931 | Lighting - Replace Baseball Field | 2 | [5 empty] | 100000 | 104450
0471 | River Ridge HS | 1990 | PRT | CS&CC |  |  |  | 85000 | 850000471 | Remodel Restrooms ADA | 2 |  |  |  | 1 |  | 700000 | 731150
0472 | River Ridge MS | 1990 | PRT | CS&CC |  |  |  | 85000 | 850000472 | Remodel Restrooms ADA | 2 |  |  |  | 1 |  | 700000 | 731150
0472 | River Ridge MS | 1990 | CCTE | CS&CC |  |  |  | 85000 | 850000472 | Remodel Technology Education Space for PLTW Curriculum | 2 |  | 3913 |  | 1 |  | 160000 | 167120
0251 | San Antonio ES | 1981 | PRT | FOSM |  |  |  | 85110 | 851100251 | HVAC Upgrade - Phase 2 | 2 | [5 empty] | 1300000 | 1357850
2061 | Sand Pine ES | 1998 | IS | IS |  |  |  | 83000 | 830002061 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0411 | Seven Springs ES | 1987 | PRT | FOSM |  |  |  | 85110 | 851100411 | HVAC Replace 200 Ton Chiller | 2 | [5 empty] | 40000 | 41780
0057 | Seven Springs MS | 1995 | ATH | MAINT |  |  |  | 82040 | 820400057 | Sound Panel Refurb In Gym | 2 | 13/14 | 3710 3711 |  |  |  | 75000 | 78337.5 |  | Completed
0601 | Shady Hills ES | 1973 | FNS | FNS |  |  |  | 85250 | 852500601 | Stock Room Renovation | 2 | [5 empty] | 10000 | 10445
0601 | Shady Hills ES | 1973 | IS | IS |  |  |  | 83000 | 830000601 | Technology Infrastructure Upgrades | 2 |  | 3913 |  | 1 |  | 425000 | 443912.5 |  | Part of Renovation
0461 | Thomas E. Weightman MS | 1990 | PRT | FOSM |  |  |  | 85110 | 851100461 | HVAC Replace (2) 200 Ton Chillers | 2 | [5 empty] | 400000 | 417800
0063 | Wesley Chapel HS | 1998 | IS | IS |  |  |  | 83000 | 830000063 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 800000 | 835600
0091 | West Zephyrhills ES | 1958 | PRT | CS&CC |  |  |  | 86100 | 861000091 | Remodel School - Tear Down Or Remodel Cafeteria Bld #2 Into Classrooms, Renovate Bld #1,3,4,5,8,9,14 | 2 |  |  |  | 5 |  | 8226665 | 8592751.5925
0090 | Wiregrass Ranch HS | 2006 | CCTE | CS&CC |  |  |  | 85240 | 852400090 | Remodel/Expand Culinary Classroom | 2 | [5 empty] | 420000 | 438690
0131 | Zephyrhills HS | 1973 | IS | IS |  |  |  | 83000 | 830000131 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 800000 | 835600
0901 | Anclote ES | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500901 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0901 | Anclote ES | 1973 | FNS | FNS |  |  |  | 85250 | 852500901 | Kitchen Hood | 3 | [5 empty] | 66853 | 72929.9377
0342 | Bayonet Point MS | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500342 | Serving Line Renovation | 3 | [5 empty] | 120329 | 131266.9061
0060 | Chester Taylor ES | 1996 | FNS | CS&CC |  |  |  | 85110 | 851100060 | A/C Renovation To Kitchen | 3 | [5 empty] | 195000 | 212725.5
0060 | Chester Taylor ES | 1996 | FNS | CS&CC |  |  |  | 85250 | 852500060 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0060 | Chester Taylor ES | 1996 | IS | IS |  |  |  | 83000 | 830000060 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0311 | Cotee River ES | 1993 | PRT | CS&CC |  |  |  | 86150 | 861500311 | Traffic Safety and Parking Improvements | 3 |  | 3913 |  |  |  | 1000000 | 1090900
0701 | Cypress ES | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000701 | Remodel School - Kelley School + Add Capacity | 3 | [5 empty] | 8500000 | 9272650
0701 | Cypress ES | 1973 | IS | IS |  |  |  | 83000 | 830000701 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0059 | Denham Oaks ES | 1994 | FNS | CS&CC |  |  |  | 85250 | 852500059 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0059 | Denham Oaks ES | 1994 | IS | IS |  |  |  | 83000 | 830000059 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0059 | Denham Oaks ES | 1994 | PRT | MAINT |  |  |  | 85200 | 852000059 | Roof Maintenance and Internal Gutters | 3 | [5 empty] | 50000 | 54545
9430 | District Wide |  | ATH | ATH |  |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 3 | [5 empty] | 120000 | 130908
9019 | District Wide |  | PRT | CS&CC |  |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 3 | [5 empty] | 1000000 | 1090900
0000 | District Wide |  | FIN | FIN |  |  |  | 00000 | 000000000 | Annual Debt Service Payments | 3 | [5 empty] | 50340588 | 50340588
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 3 | [5 empty] | 437303 | 477053.8427
9061 | District Wide |  | FIN | FIN |  |  |  | 83260 | 832609061 | Annual Compliance with ADA | 3 | [5 empty] | 300000 | 327270 |  |  | Added at the request of CS&CC
9061 | District Wide |  | FIN | FIN |  |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 3 | [5 empty] | 2623816 | 2862320.8744
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 3 | [5 empty] | 437303 | 477053.8427
9421 | District Wide |  | FIN | FIN |  |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 3 | [5 empty] | 1800658 | 1964337.8122
9999 | District Wide |  | FIN | FIN |  |  |  | 84210 | 842109999 | Annual Buses & Other Vehicles | 3 | [5 empty] | 4667428 | 5091697.2052
9420 | District Wide |  | IS | IS |  |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 3 | [5 empty] | 9053343 | 9876291.8787
9420 | District Wide |  | IS | IS |  |  |  | 84080 | 840809420 | Annual Technology and Equipment (Admin Computers) | 3 | [5 empty] | 9053343 | 9876291.8787
9002 | District Wide |  | PRT | MAINT |  |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 3 | [5 empty] | 30000 | 32727
9061 | District Wide |  | ATH | MAINT |  |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 3 | [5 empty] | 200000 | 218180
9061 | District Wide |  | PRT | MAINT |  |  |  | 86160 | 861609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 3 | [5 empty] | 1700000 | 1854530
9061 | District Wide |  | PRT | MAINT |  |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 3 | [5 empty] | 400000 | 436360
9061 | District Wide |  | PRT | MAINT |  |  |  | 85120 | 851209061 | Annual Flooring Replacement | 3 | [5 empty] | 600000 | 654540
9061 | District Wide |  | PRT | MAINT |  |  |  | 85110 | 851109061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 3 | [5 empty] | 500000 | 545450
9061 | District Wide |  | PRT | MAINT |  |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 3 | [5 empty] | 200000 | 218180
9061 | District Wide |  | PRT | MAINT |  |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 3 | [5 empty] | 1000000 | 1090900
9061 | District Wide |  | PRT | MAINT |  |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 3 |  | 3913 |  |  |  | 400000 | 436360
9061 | District Wide |  | PRT | MAINT |  |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 3 | [5 empty] | 200000 | 218180
9061 | District Wide |  | PRT | MAINT |  |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms | 3 | [5 empty] | 200000 | 218180
9430 | District Wide |  | ATH | MAINT |  |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 3 | [5 empty] | 300000 | 327270
9430 | District Wide |  | ATH | MAINT |  |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 3 | [5 empty] | 150000 | 163635
9012 | District Wide |  | PLAN | PLAN |  |  |  | 89990 | 899909012 | Property Acquisition - Middle/High Site in River Landing (Wesley Chapel) | 3 | [5 empty] | 4000000 | 4363600
0086 | Dr. John Long MS | 2006 | ATH | ATH |  |  |  | 82000 | 820000086 | Sand & Paint Gym Floors | 3 | [5 empty] | 25000 | 27272.5
0086 | Dr. John Long MS | 2006 | PRT | CS&CC |  |  |  | 86100 | 861000086 | Addition - Classroom Wing | 3 | [5 empty] | 4000000 | 4363600
0331 | Gulf HS | 1971 | ATH | MAINT |  |  |  | 85170 | 851700331 | Fencing - Baseball Field | 3 | [5 empty] | 20000 | 21818
0331 | Gulf HS | 1971 | ATH | MAINT |  |  |  | 85170 | 851700331 | Fencing - Tennis Court Fence | 3 | [5 empty] | 15000 | 16363.5 |  |  | Phil will check to see if need to move up in priority
0261 | Gulf MS | 1964 | PRT | CS&CC |  |  |  | 86100 | 861000261 | Remodel School Bld 1, 2, 3, 9. 10, 11, 14 | 3 | [5 empty] | 8653000 | 9439557.7
0261 | Gulf MS | 1964 | FNS | MAINT |  |  |  | 85250 | 852500261 | Kitchen Renovation Flooring, Paint, Ovens, Steamers | 3 | [5 empty] | 120329 | 131266.9061
0301 | Hudson ES | 1966 | FNS | CS&CC |  |  |  | 85250 | 852500301 | Remodel Kitchen And Serving Line | 3 | [5 empty] | 779738 | 850616.1842
0302 | Hudson ES | 1967 | PRT | CS&CC |  |  |  | 85000 | 850000302 | Remodel Bld #1 | 3 |  | 3913 |  |  |  | 400000 | 436360
0521 | Hudson HS | 1973 | ATH | MAINT |  |  |  | 85170 | 851700521 | Fencing - Perimeter | 3 | [5 empty] | 20000 | 21818
0073 | J.W. Mitchell HS | 2000 | ATH | CS&CC |  |  |  | 82050 | 820500073 | Refurbish Football Field Elevation and Field Drainage | 3 | [5 empty] | 320000 | 349088
0065 | James M. Marlowe ES | 1999 | IS | IS |  |  |  | 83000 | 830000065 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0065 | James M. Marlowe ES | 1999 | PRT | MAINT |  |  |  | 85200 | 852000065 | Roof Maintenance | 3 | [5 empty] | 80000 | 87272
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  |  | 85170 | 851700801 | Fencing - Tennis | 3 | [5 empty] | 15000 | 16363.5
0211 | Mittye P. Locke ES | 1966 | PRT | CS&CC |  |  |  | 86100 | 861000211 | Remodel School, Replace Covered Walks, Traffic Improvements | 3 |  | 3913 |  |  |  | 8000000 | 8727200
0501 | Northwest ES | 1973 | IS | IS |  |  |  | 83000 | 830000501 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0089 | Paul R. Smith MS | 2006 | ATH | ATH |  |  |  | 82000 | 820000089 | Sand & Paint Gym Floors | 3 | [5 empty] | 25000 | 27272.5
0361 | Quail Hollow ES | 1975 | IS | IS |  |  |  | 83000 | 830000361 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0021 | R. B. Cox ES | 1925 | IS | IS |  |  |  | 83000 | 830000021 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  |  | 82040 | 820400931 | Scoreboard Replacement(s) | 3 | [5 empty] | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  |  | 85000 | 850000931 | Replace Wall Tile In PE Locker Room | 3 | [5 empty] | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  |  | 82050 | 820500931 | Tennis Court Renovation | 3 | [5 empty] | 250000 | 272725
0471 | River Ridge HS | 1990 | IS | IS |  |  |  | 83000 | 830000471 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 800000 | 872720
0471 | River Ridge HS | 1990 | ATH | MAINT |  |  |  | 85170 | 851700471 | Fencing - Tennis | 3 | [5 empty] | 30000 | 32727
0472 | River Ridge MS | 1990 | IS | IS |  |  |  | 83000 | 830000472 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 650000 | 709085
0341 | Schrader ES | 1972 | IS | IS |  |  |  | 83000 | 830000341 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0072 | Sunray ES | 2000 | PRT | MAINT |  |  |  | 85200 | 852000072 | Roof Maintenance | 3 | [5 empty] | 80000 | 87272
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT |  |  |  | 85170 | 851700461 | Fencing - Tennis Court Fence | 3 | [5 empty] | 20000 | 21818 |  |  | Phil Bell will check to see if need to move up in priority
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT |  |  |  | 82050 | 820500461 | Overlay Courts | 3 | [5 empty] | 80000 | 87272
0063 | Wesley Chapel HS | 1998 | PRT | FOSM |  |  |  | 85110 | 851100063 | HVAC Replace 400 Ton Chiller | 3 | [5 empty] | 300000 | 327270
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC |  |  |  | 86100 | 861000090 | Addition - Classroom Wing | 3 | [5 empty] | 4000000 | 4363600
0132 | Woodland ES | 1977 | PRT | FOSM |  |  |  | 85110 | 851100132 | HVAC Upgrade - Phase 2 | 3 | [5 empty] | 4447860 | 4852170.474
0131 | Zephyrhills HS | 1973 | CCTE | CS&CC |  |  |  | 85240 | 852400131 | Remodel Automotive Technology To Lab Space/Convert To Health Academy | 3 |  | 3913 |  |  |  | 560000 | 610904
0131 | Zephyrhills HS | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000131 | Remodel School - Kelley School + Add Capacity | 3 |  | 3913 |  |  |  | 20600000 | 22472540
0932 | Calusa ES | 1979 | IS | IS |  |  |  | 83000 | 830000932 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0401 | Centennial ES | 1986 | PRT | FOSM |  |  |  | 85110 | 851100401 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 40000 | 45580
0074 | Centennial MS | 2001 | FNS | CS&CC |  |  |  | 85250 | 852500074 | Serving Line Renovation | 4 | [5 empty] | 981709 | 1118657.4055
0074 | Centennial MS | 2001 | FNS | FNS |  |  |  | 86200 | 862000074 | Outside Dining Sun Shade | 4 | [5 empty] | 10000 | 11395
0074 | Centennial MS | 2001 | IS | IS |  |  |  | 83000 | 830000074 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 650000 | 740675
0074 | Centennial MS | 2001 | PRT | MAINT |  |  |  | 85200 | 852000074 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0070 | Chasco ES | 2000 | IS | IS |  |  |  | 83000 | 830000070 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0070 | Chasco ES | 2000 | PRT | MAINT |  |  |  | 85200 | 852000070 | Roof Maintenance | 4 | [5 empty] | 40000 | 45580
0069 | Chasco MS | 2000 | ATH | ATH |  |  |  | 82000 | 820000069 | Sand & Paint Gym Floors | 4 | [5 empty] | 25000 | 28487.5
0069 | Chasco MS | 2001 | IS | IS |  |  |  | 83000 | 830000069 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 650000 | 740675
0069 | Chasco MS | 2001 | PRT | MAINT |  |  |  | 85200 | 852000069 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0311 | Cotee River ES | 1993 | FNS | FNS |  |  |  | 84070 | 840700311 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0311 | Cotee River ES | 1993 | PRT | FOSM |  |  |  | 85110 | 851100311 | HVAC Replace (2) chillers & controls | 4 | [5 empty] | 80000 | 91160
0701 | Cypress ES | 1973 | FNS | FNS |  |  |  | 85250 | 852500701 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0421 | Deer Park ES | 1988 | FNS | CS&CC |  |  |  | 85250 | 852500421 | Serving Line Renovation | 4 | [5 empty] | 347047 | 395460.0565
0421 | Deer Park ES | 1988 | PRT | FOSM |  |  |  | 85110 | 851100421 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 40000 | 45580
0059 | Denham Oaks ES | 1994 | PRT | FOSM |  |  |  | 85110 | 851100059 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 40000 | 45580
9430 | District Wide |  | ATH | ATH |  |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 4 | [5 empty] | 120000 | 136740
9019 | District Wide |  | PRT | CS&CC |  |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 4 | [5 empty] | 1000000 | 1139500
0000 | District Wide |  | FIN | FIN |  |  |  | 00000 | 000000000 | Annual Debt Service Payments | 4 | [5 empty] | 54561680 | 54561680
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 4 | [5 empty] | 454970 | 518438.315
9061 | District Wide |  | FIN | FIN |  |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 4 | [5 empty] | 2729818 | 3110627.611
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 4 | [5 empty] | 454970 | 518438.315
9061 | District Wide |  | FIN | FIN |  |  |  | 83260 | 832609061 | Annual Compliance with ADA | 4 | [5 empty] | 300000 | 341850 |  |  | Added at the request of CS&CC
9421 | District Wide |  | FIN | FIN |  |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 4 | [5 empty] | 1873404 | 2134743.858
9999 | District Wide |  | FIN | FIN |  |  |  | 84210 | 842109999 | Annual Buses & Other Vehicles | 4 | [5 empty] | 4855992 | 5533402.884
9420 | District Wide |  | IS | IS |  |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 4 | [5 empty] | 9461705 | 10781612.8475
9420 | District Wide |  | IS | IS |  |  |  | 84080 | 840809420 | Annual Technology and Equipment (Admin Computers) | 4 | [5 empty] | 9461705 | 10781612.8475
9002 | District Wide |  | PRT | MAINT |  |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 4 | [5 empty] | 30000 | 34185
9061 | District Wide |  | ATH | MAINT |  |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 4 | [5 empty] | 200000 | 227900
9061 | District Wide |  | PRT | MAINT |  |  |  | 86160 | 861609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 4 | [5 empty] | 1700000 | 1937150
9061 | District Wide |  | PRT | MAINT |  |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 4 | [5 empty] | 400000 | 455800
9061 | District Wide |  | PRT | MAINT |  |  |  | 85120 | 851209061 | Annual Flooring Replacement | 4 | [5 empty] | 600000 | 683700
9061 | District Wide |  | PRT | MAINT |  |  |  | 85110 | 851109061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 4 | [5 empty] | 500000 | 569750
9061 | District Wide |  | PRT | MAINT |  |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 4 | [5 empty] | 200000 | 227900
9061 | District Wide |  | PRT | MAINT |  |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 4 | [5 empty] | 1000000 | 1139500
9061 | District Wide |  | PRT | MAINT |  |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 4 |  | 3913 |  |  |  | 400000 | 455800
9061 | District Wide |  | PRT | MAINT |  |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 4 | [5 empty] | 200000 | 227900
9061 | District Wide |  | PRT | MAINT |  |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms | 4 | [5 empty] | 200000 | 227900
9430 | District Wide |  | ATH | MAINT |  |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 4 | [5 empty] | 300000 | 341850
9430 | District Wide |  | ATH | MAINT |  |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 4 | [5 empty] | 150000 | 170925
0084 | Double Branch ES | 2007 | FNS | CS&CC |  |  |  | 85110 | 851100084 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0351 | Fox Hollow ES | 1990 | FNS | CS&CC |  |  |  | 85110 | 851100351 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  |  | 85110 | 851100991 | HVAC Replace 200 Ton Chiller | 4 | [5 empty] | 40000 | 45580
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  |  | 85110 | 851100991 | HVAC Replace Control System | 4 | [5 empty] | 400000 | 455800
0991 | Fred K. Marchman EC | 1984 | PRT | MAINT |  |  |  | 85200 | 852000991 | Roof Replacement | 4 |  | 3913 |  |  |  | 250000 | 284875
0083 | Gulf Highlands ES | 2006 | FNS | CS&CC |  |  |  | 85110 | 851100083 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0331 | Gulf HS | 1971 | PRT | CS&CC |  |  |  | 86100 | 861000331 | Remodel School Phase 1 - Bld #1 | 4 |  | 3913 |  |  |  | 9150000 | 10426425
0331 | Gulf HS | 1971 | PRT | CS&CC |  |  |  | 86100 | 861000331 | Remodel School Phase 2 | 4 |  | 3913 |  |  |  | 2514150 | 2864873.925
0331 | Gulf HS | 1971 | PRT | FOSM |  |  |  | 85110 | 851100331 | HVAC Replace (2) 200 Ton Chillers | 4 | [5 empty] | 120000 | 136740
0331 | Gulf HS | 1971 | ATH | MAINT |  |  |  | 85000 | 850000331 | Replace Wall Tile In PE Locker Room | 4 | [5 empty] | 15000 | 17092.5
0261 | Gulf MS | 1964 | ATH | ATH |  |  |  | 82000 | 820000261 | Sand & Paint Gym Floors | 4 | [5 empty] | 25000 | 28487.5
0911 | Gulfside ES | 1977 | PRT | CS&CC |  |  |  | 86100 | 861000911 | Remodel Bld #1 & 2 Parking And Traffic Improvements | 4 |  | 3913 |  |  |  | 2500000 | 2848750
0301 | Hudson ES | 1966 | FNS | FNS |  |  |  | 84070 | 840700301 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0521 | Hudson HS | 1973 | ATH | ATH |  |  |  | 82050 | 820500521 | Track Overlay | 4 | [5 empty] | 50000 | 56975
0521 | Hudson HS | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000521 | Remodel School - Kelley School | 4 |  | 3913 |  |  |  | 19100000 | 21764450
0521 | Hudson HS | 1973 | PRT | CS&CC |  |  |  | 86110 | 861100521 | Traffic Safety and Parking Improvements | 4 | [5 empty] | 860000 | 979970
0521 | Hudson HS | 1973 | PRT | FOSM |  |  |  | 85110 | 851100521 | HVAC Replace 200 Ton Chiller (Gym) | 4 | [5 empty] | 40000 | 45580
0521 | Hudson HS | 1973 | IS | IS |  |  |  | 83000 | 830000521 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 800000 | 911600
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT |  |  |  | 81150 | 811500073 | Storage Garage | 4 | [5 empty] | 25000 | 28487.5
0321 | Lacoochee ES | 1971 | PRT | CS&CC |  |  |  | 86100 | 861000321 | Remodel Classroom Bld #8,9,11,12,13 | 4 |  | 3913 |  |  |  | 1348655 | 1536792.3725
0961 | Lake Myrtle ES | 1984 | FNS | FNS |  |  |  | 85250 | 852500961 | Serving Line Update - from RES | 4 | [5 empty] | 7383 | 8412.9285
0961 | Lake Myrtle ES | 1984 | IS | IS |  |  |  | 83000 | 830000961 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0801 | Land O' Lakes HS | 1973 | PRT | FOSM |  |  |  | 85110 | 851100801 | HVAC Replace 200 Ton Chiller (Gym) | 4 | [5 empty] | 40000 | 45580
0801 | Land O' Lakes HS | 1973 | IS | IS |  |  |  | 83000 | 830000801 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 800000 | 911600
0801 | Land O' Lakes HS | 1973 | PRT | MAINT |  |  |  | 85200 | 852000801 | Roof Replacement | 4 | [5 empty] | 600000 | 683700
2081 | Longleaf ES | 2005 | FNS | CS&CC |  |  |  | 85110 | 851102081 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0941 | Moon Lake ES | 1982 | PRT | CS&CC |  |  |  | 86100 | 861000941 | Remodel Bld #1 | 4 | [5 empty] | 5539200 | 6311918.4
0941 | Moon Lake ES | 1982 | PRT | CS&CC |  |  |  | 86110 | 861100941 | Traffic Safety and Parking Improvements | 4 |  | 3913 |  |  |  | 758000 | 863741
0081 | Moore Mickens EC | 1952 | FNS | MAINT |  |  |  | 84070 | 840700081 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0092 | New River ES | 2007 | FNS | CS&CC |  |  |  | 85110 | 851100092 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0501 | Northwest ES | 1973 | FNS | FNS |  |  |  | 85250 | 852500501 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0082 | Oakstead ES | 2006 | FNS | CS&CC |  |  |  | 85110 | 851100082 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0902 | Pine View ES | 2003 | FNS | CS&CC |  |  |  | 85110 | 851100902 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  |  | 82000 | 820000931 | Sand & Paint Gym Floors | 4 | [5 empty] | 60000 | 68370
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  |  | 82050 | 820500931 | Track Overlay | 4 | [5 empty] | 50000 | 56975
0472 | River Ridge MS | 1990 | ATH | MAINT |  |  |  | 82050 | 820500472 | Overlay Middle School Track | 4 | [5 empty] | 50000 | 56975
2061 | Sand Pine ES | 1998 | PRT | FOSM |  |  |  | 85110 | 851102061 | HVAC Replace (2) 200 Ton Chillers | 4 | [5 empty] | 180000 | 205110
2091 | Seven Oaks ES | 2005 | FNS | CS&CC |  |  |  | 85110 | 851102091 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  |  | 85250 | 852500411 | Serving Line Renovation | 4 | [5 empty] | 347047 | 395460.0565
0411 | Seven Springs ES | 1987 | IS | IS |  |  |  | 83000 | 830000411 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0601 | Shady Hills ES | 1973 | FNS | FNS |  |  |  | 85250 | 852500601 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0032 | Trinity ES | 2000 | PRT | MAINT |  |  |  | 85200 | 852000032 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC |  |  |  | 85110 | 851100085 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
2071 | Wesley Chapel ES | 2002 | IS | IS |  |  |  | 83000 | 830002071 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0063 | Wesley Chapel HS | 1998 | PRT | MAINT |  |  |  | 85200 | 852000063 | Roof Maintenance | 4 | [5 empty] | 100000 | 113950
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT |  |  |  | 82050 | 820500090 | Overlay Courts - Basketball & Tennis | 4 | [5 empty] | 25000 | 28487.5
0132 | Woodland ES | 1977 | IS | IS |  |  |  | 83000 | 830000132 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0131 | Zephyrhills HS | 1973 | FNS | FNS |  |  |  | 84070 | 840700131 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0113 | Anclote HS | 2009 | ATH | ATH |  |  |  | 82000 | 820000113 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0342 | Bayonet Point MS | 1973 | IS | IS |  |  |  | 83000 | 830000342 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 650000 | 773630
0932 | Calusa ES | 1979 | PRT | CS&CC |  |  |  | 86110 | 861100932 | Traffic Safety and Parking Improvements | 5 |  | 3913 |  |  |  | 650000 | 773630
0401 | Centennial ES | 1986 | FNS | CS&CC |  |  |  | 85110 | 851100401 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0100 | Charles S. Rushe MS | 2007 | ATH | ATH |  |  |  | 82050 | 820500100 | Resurface Track Courts | 5 | [5 empty] | 50000 | 59510
0100 | Charles S. Rushe MS | 2007 | ATH | ATH |  |  |  | 82000 | 820000100 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0070 | Chasco ES | 2000 | FNS | CS&CC |  |  |  | 85110 | 851100070 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0070 | Chasco ES | 2000 | FNS | CS&CC |  |  |  | 85250 | 852500070 | Kitchen Renovation | 5 | [5 empty] | 943483 | 1122933.4666
0070 | Chasco ES | 2000 | PRT | FOSM |  |  |  | 85110 | 851100070 | HVAC (2) 300 ton chillers | 5 | [5 empty] | 600000 | 714120
0069 | Chasco MS | 2001 | FNS | CS&CC |  |  |  | 85250 | 852500069 | Serving Line Renovation | 5 | [5 empty] | 811329.75 | 965644.6684
0069 | Chasco MS | 2001 | FNS | FNS |  |  |  | 86200 | 862000069 | Outside Dining Sun Shade | 5 | [5 empty] | 8000 | 9521.6
0060 | Chester Taylor ES | 1996 | FNS | FNS |  |  |  | 84070 | 840700060 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0103 | Crews Lake MS | 2008 | ATH | ATH |  |  |  | 82050 | 820500103 | Resurface Track Courts | 5 | [5 empty] | 50000 | 59510
0103 | Crews Lake MS | 2008 | ATH | ATH |  |  |  | 82000 | 820000103 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0421 | Deer Park ES | 1988 | FNS | CS&CC |  |  |  | 85110 | 851100421 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0059 | Denham Oaks ES | 1994 | FNS | FNS |  |  |  | 84070 | 840700059 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
9430 | District Wide |  | ATH | ATH |  |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 5 | [5 empty] | 120000 | 142824
9019 | District Wide |  | PRT | CS&CC |  |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 5 | [5 empty] | 1000000 | 1190200
0000 | District Wide |  | FIN | FIN |  |  |  | 00000 | 000000000 | Annual Debt Service Payments | 5 | [5 empty] | 50647051 | 50647051
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 5 | [5 empty] | 473350 | 563381.17
9061 | District Wide |  | FIN | FIN |  |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 5 | [5 empty] | 2840102 | 3380289.4004
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 5 | [5 empty] | 473350 | 563381.17
9061 | District Wide |  | FIN | FIN |  |  |  | 83260 | 832609061 | Annual Compliance with ADA | 5 | [5 empty] | 300000 | 357060 |  |  | Added at the request of CS&CC
9421 | District Wide |  | FIN | FIN |  |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 5 | [5 empty] | 1949090 | 2319806.918
9999 | District Wide |  | FIN | FIN |  |  |  | 84210 | 842109999 | Annual Buses & Other Vehicles | 5 | [5 empty] | 5052174 | 6013097.4948
9420 | District Wide |  | IS | IS |  |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 5 | [5 empty] | 9745556 | 11599160.7512
9420 | District Wide |  | IS | IS |  |  |  | 84080 | 840809420 | Annual Technology and Equipment (Admin Computers) | 5 | [5 empty] | 9745557 | 11599161.9414
9002 | District Wide |  | PRT | MAINT |  |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 5 | [5 empty] | 30000 | 35706
9061 | District Wide |  | ATH | MAINT |  |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 5 | [5 empty] | 200000 | 238040
9061 | District Wide |  | PRT | MAINT |  |  |  | 86160 | 861609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 5 | [5 empty] | 1700000 | 2023340
9061 | District Wide |  | PRT | MAINT |  |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 5 | [5 empty] | 400000 | 476080
9061 | District Wide |  | PRT | MAINT |  |  |  | 85120 | 851209061 | Annual Flooring Replacement | 5 | [5 empty] | 600000 | 714120
9061 | District Wide |  | PRT | MAINT |  |  |  | 85110 | 851109061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 5 | [5 empty] | 500000 | 595100
9061 | District Wide |  | PRT | MAINT |  |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 5 | [5 empty] | 200000 | 238040
9061 | District Wide |  | PRT | MAINT |  |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 5 | [5 empty] | 1000000 | 1190200
9061 | District Wide |  | PRT | MAINT |  |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 5 |  | 3913 |  |  |  | 400000 | 476080
9061 | District Wide |  | PRT | MAINT |  |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 5 | [5 empty] | 200000 | 238040
9061 | District Wide |  | PRT | MAINT |  |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms | 5 | [5 empty] | 200000 | 238040
9430 | District Wide |  | ATH | MAINT |  |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 5 | [5 empty] | 300000 | 357060
9430 | District Wide |  | ATH | MAINT |  |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 5 | [5 empty] | 150000 | 178530
9012 | District Wide |  | PLAN | PLAN |  |  |  | 89990 | 899909012 | Property Acquisition - Elementary site #2 in Wiregrass | 5 | [5 empty] | 750000 | 892650
0331 | Gulf HS | 1971 | ATH | CS&CC |  |  |  | 82020 | 820200331 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0331 | Gulf HS | 1971 | IS | IS |  |  |  | 83000 | 830000331 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
0261 | Gulf MS | 1964 | IS | IS |  |  |  | 83000 | 830000261 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 650000 | 773630
0911 | Gulfside ES | 1977 | FNS | CS&CC |  |  |  | 85110 | 851100911 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC |  |  |  | 00000 | 000000242 | Determine Long Range Use | 5 | [6 empty] | 0
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC |  |  |  | 85000 | 850000242 | Remodel School | 5 | [5 empty] | 266999 | 317782.2098
0073 | J.W. Mitchell HS | 2000 | IS | IS |  |  |  | 83000 | 830000073 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
7071 | James Irvin EC | 1995 | CCTE | CS&CC |  |  |  | 86100 | 861007071 | Redevelopment of Campus | 5 | [5 empty] | 5000000 | 5951000
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC |  |  |  | 85110 | 851100065 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC |  |  |  | 85250 | 852500065 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0065 | James M. Marlowe ES | 1999 | FNS | FNS |  |  |  | 84070 | 840700065 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0961 | Lake Myrtle ES | 1984 | FNS | CS&CC |  |  |  | 85110 | 851100961 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  |  | 82020 | 820200801 | Concession Stand Bathrooms - Baseball/Softball | 5 | [5 empty] | 250000 | 297550
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  |  | 82020 | 820200801 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  |  | 82020 | 820200801 | Renovate/Build Athletic Field House | 5 | [5 empty] | 1500000 | 1785300
2081 | Longleaf ES | 2005 | IS | IS |  |  |  | 83000 | 830002081 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0451 | Mary Giella ES | 1989 | FNS | CS&CC |  |  |  | 85110 | 851100451 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0451 | Mary Giella ES | 1989 | IS | IS |  |  |  | 83000 | 830000451 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0081 | Moore Mickens EC | 1952 | PRT | CS&CC |  |  |  | 86100 | 861000081 | Redevelopment of Campus | 5 | [5 empty] | 5000000 | 5951000 |  | On Hold
9019 | New Elementary School |  | PLAN | CS&CC | Yes |  |  | 87045 | 870459019 | Elementary U - Northwood | 5 | [5 empty] | 18597372 | 22134592.1544
0501 | Northwest ES | 1973 | PRT | CS&CC |  |  |  | 86100 | 861000501 | Remodel School - Kelley School | 5 |  | 3913 |  |  |  | 7000000 | 8331400
0061 | Pasco ES | 1954 | FNS | FNS |  |  |  | 84070 | 840700061 | Cooler / Freezer | 5 | 13/14 | 3709 | 76103 |  |  | 80709 | 96059.8518
0031 | Pasco HS | 1964 | FNS | CS&CC |  |  |  | 85250 | 852500031 | Serving Line Renovation | 5 | [5 empty] | 1079880 | 1285273.176
0031 | Pasco HS | 1964 | FNS | FNS |  |  |  | 84070 | 840700031 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0031 | Pasco HS | 1964 | PRT | FOSM |  |  |  | 85110 | 851100031 | HVAC Replace 250 ton chiller | 5 | [5 empty] | 250000 | 297550
0071 | Pasco MS | 1946 | ATH | CS&CC |  |  |  | 82050 | 820500071 | Replace Gym Floor | 5 | [5 empty] | 175000 | 208285 |  |  | Gym Floor Synthetic Overlay just complete - does that replace this project?
0902 | Pine View ES | 2003 | IS | IS |  |  |  | 83000 | 830000902 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0902 | Pine View ES | 2003 | PRT | MAINT |  |  |  | 85200 | 852000902 | Roof Maintenance | 5 | [5 empty] | 80000 | 95216
0921 | Pine View MS | 1977 | PRT | CS&CC |  |  |  | 86100 | 861000921 | Remodel School | 5 | [5 empty] | 15930180 | 18960100.236
0921 | Pine View MS | 1977 | IS | IS |  |  |  | 83000 | 830000921 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
0361 | Quail Hollow ES | 1975 | PRT | MAINT |  |  |  | 85200 | 852000361 | Roof Replacement | 5 | [5 empty] | 600000 | 714120
0931 | Ridgewood HS | 1977 | PRT | CS&CC |  |  |  | 86100 | 861000931 | Remodel Bld #1 | 5 |  | 3913 |  |  |  | 9000000 | 10711800
0931 | Ridgewood HS | 1977 | CCTE | CS&CC |  |  |  | 83000 | 830000931 | Remodel Technology Lab - Room 404 | 5 |  | 3913 |  |  |  | 300000 | 357060
0931 | Ridgewood HS | 1977 | PRT | MAINT |  |  |  | 85200 | 852000931 | Roof Replacement | 5 | [5 empty] | 400000 | 476080
0251 | San Antonio ES | 1981 | PRT | CS&CC |  |  |  | 86100 | 861000251 | Remodel Bld #1 #2 #10 | 5 |  | 3913 |  |  |  | 3965541 | 4719786.8982
2061 | Sand Pine ES | 1998 | FNS | CS&CC |  |  |  | 85110 | 851102061 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
2061 | Sand Pine ES | 1998 | FNS | CS&CC |  |  |  | 85250 | 852502061 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  |  | 85110 | 851100411 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0601 | Shady Hills ES | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500601 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0101 | Sunlake HS | 2007 | ATH | ATH |  |  |  | 82000 | 820000101 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0072 | Sunray ES | 2000 | FNS | CS&CC |  |  |  | 85110 | 851100072 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0072 | Sunray ES | 2000 | FNS | CS&CC |  |  |  | 85250 | 852500072 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0072 | Sunray ES | 2000 | IS | IS |  |  |  | 83000 | 830000072 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0461 | Thomas E. Weightman MS | 1990 | FNS | FNS |  |  |  | 84070 | 840700461 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
9032 | Transportation E | 1972 | PRT | CS&CC |  |  |  | 85000 | 850009032 | Remodel Interior | 5 | [5 empty] | 250000 | 297550
9035 | Transportation NW | 1979 | PRT | CS&CC |  |  |  | 86100 | 861009035 | Remodel Office Interior, Add Parking | 5 | [5 empty] | 2500000 | 2975500
9019 | Transportation SW |  | PRT | CS&CC |  |  |  | 86100 | 861009019 | Construction of New Facility | 5 | [5 empty] | 5500000 | 6546100
9033 | Transportation W | 1971 | PRT | CS&CC |  |  |  | 85000 | 850009033 | Remodel Interior, Add Paint Booth, Expand Parking | 5 | [5 empty] | 650000 | 773630
0032 | Trinity ES | 2000 | IS | IS |  |  |  | 83000 | 830000032 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH |  |  |  | 82000 | 820000090 | Sand & Paint Gym Floors | 5 | [5 empty] | 40000 | 47608
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH |  |  |  | 82040 | 820400090 | Scoreboard Replacement(s) | 5 | [5 empty] | 75000 | 89265
0132 | Woodland ES | 1977 | PRT | CS&CC |  |  |  | 86100 | 861000132 | Remodel School, Expand Cafeteria | 5 |  | 3913 |  |  |  | 4514705 | 5373401.891
0131 | Zephyrhills HS | 1973 | ATH | CS&CC |  |  |  | 82020 | 820200131 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0131 | Zephyrhills HS | 1973 | ATH | MAINT |  |  |  | 82050 | 820500131 | Overlay Tennis Court | 5 | [5 empty] | 50000 | 59510
0901 | Anclote ES | 1973 | SCHOOL | CS&CC |  |  |  | 86190 | 861900901 | Covered Walkways | 6 | [5 empty] | 114696 | 142578.5976
0113 | Anclote HS | 2009 | FNS | CS&CC |  |  |  | 85250 | 852500113 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0342 | Bayonet Point MS | 1973 | SCHOOL | MAINT |  |  |  | 86190 | 861900342 | Covered Walkways | 6 | [5 empty] | 25000 | 31077.5
0932 | Calusa ES | 1979 | SCHOOL | CS&CC |  |  |  | 86190 | 861900932 | Covered Walkways | 6 | [5 empty] | 206000 | 256078.6
0074 | Centennial MS | 2001 | SCHOOL | CS&CC |  |  |  | 86190 | 861900074 | Covered Walkways | 6 | [5 empty] | 130000 | 161603
0074 | Centennial MS | 2001 | FNS | FNS |  |  |  | 84070 | 840700074 | Cooler / Freezer | 6 | 13/14 | 3709 | 89711 |  |  | 88779 | 110361.1749
0074 | Centennial MS | 2001 | PRT | FOSM |  |  |  | 85110 | 851100074 | HVAC Replace Control System | 6 | [5 empty] | 600000 | 745860
0100 | Charles S. Rushe MS | 2007 | FNS | CS&CC |  |  |  | 85250 | 852500100 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0070 | Chasco ES | 2000 | SCHOOL | CS&CC |  |  |  | 86190 | 861900070 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 100000 | 124310
0070 | Chasco ES | 2000 | SCHOOL | MAINT |  |  |  | 85000 | 850000070 | Restroom for PE Classes | 6 | [5 empty] | 300000 | 372930 |  | New | Evaluating
0060 | Chester Taylor ES | 1996 | PRT | FOSM |  |  |  | 85110 | 851100060 | HVAC Replace Control System | 6 | [5 empty] | 400000 | 497240
0311 | Cotee River ES | 1993 | SCHOOL | CS&CC |  |  |  | 86190 | 861900311 | Covered Walkways | 6 | [5 empty] | 162000 | 201382.2
0103 | Crews Lake MS | 2008 | FNS | CS&CC |  |  |  | 85250 | 852500103 | Serving Line Renovation | 6 | [5 empty] | 2314818 | 2877550.2558
0701 | Cypress ES | 1973 | SCHOOL | CS&CC |  |  |  | 86190 | 861900701 | Covered Walkways | 6 | [5 empty] | 475000 | 590472.5
0059 | Denham Oaks ES | 1994 | SCHOOL | CS&CC |  |  |  | 86190 | 861900059 | Covered Walkways | 6 | [5 empty] | 135000 | 167818.5
9053 | District Complex |  | PRT | FOSM |  |  |  | 85110 | 851109053 | District Complex - Bulding 4 HVAC Replace Control System | 6 | [5 empty] | 200000 | 248620
9430 | District Wide |  | ATH | ATH |  |  |  | 82000 | 820009430 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 6 | [5 empty] | 120000 | 149172
9019 | District Wide |  | PRT | CS&CC |  |  |  | 85180 | 851809019 | Annual Fire Loop / Hydrants ($500,000 Annually) | 6 | [5 empty] | 1000000 | 1243100
0000 | District Wide |  | FIN | FIN |  |  |  | 00000 | 000000000 | Annual Debt Service Payments | 6 | [5 empty] | 50936250 | 50936250
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Compliance w/Environmental Reg | 6 | [5 empty] | 514487 | 639558.7897
9061 | District Wide |  | FIN | FIN |  |  |  | 85100 | 851009061 | Annual Maintenance & Repairs Projects (Small) | 6 | [5 empty] | 3086924 | 3837355.2244
9061 | District Wide |  | FIN | FIN |  |  |  | 83240 | 832409061 | Annual Maintenance Health & Safety | 6 | [5 empty] | 514487 | 639558.7897
9061 | District Wide |  | FIN | FIN |  |  |  | 83260 | 832609061 | Annual Compliance with ADA | 6 | [5 empty] | 300000 | 372930 |  |  | Added at the request of CS&CC
9421 | District Wide |  | FIN | FIN |  |  |  | 83000 | 830009421 | Annual Telecommunications Repairs Projects (Small) | 6 | [5 empty] | 2118477 | 2633478.7587
9999 | District Wide |  | FIN | FIN |  |  |  | 84210 | 842109999 | Annual Buses & Other Vehicles | 6 | [5 empty] | 5491238 | 6826157.9578
9420 | District Wide |  | IS | IS |  |  |  | 84060 | 840609420 | Annual Technology and Equipment ( Student Computers) | 6 | [5 empty] | 10037923 | 12478142.0813
9420 | District Wide |  | IS | IS |  |  |  | 84080 | 840809420 | Annual Technology and Equipment (Admin Computers) | 6 | [5 empty] | 10037923 | 12478142.0813
9002 | District Wide |  | PRT | MAINT |  |  |  | 86110 | 861109002 | Annual Marquee Sign Replacements ($15,000 Annually) | 6 | [5 empty] | 30000 | 37293
9061 | District Wide |  | ATH | MAINT |  |  |  | 82010 | 820109061 | Annual Bleacher Repair ($100,000 Annually) | 6 | [5 empty] | 200000 | 248620
9061 | District Wide |  | PRT | MAINT |  |  |  | 86160 | 861609061 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 6 | [5 empty] | 1700000 | 2113270
9061 | District Wide |  | PRT | MAINT |  |  |  | 85180 | 851809061 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 6 | [5 empty] | 400000 | 497240
9061 | District Wide |  | PRT | MAINT |  |  |  | 85120 | 851209061 | Annual Flooring Replacement | 6 | [5 empty] | 600000 | 745860
9061 | District Wide |  | PRT | MAINT |  |  |  | 85110 | 851109061 | Annual HVAC Equipment Replacements ($250,000 Annually) | 6 | [5 empty] | 500000 | 621550
9061 | District Wide |  | PRT | MAINT |  |  |  | 86180 | 861809061 | Annual Lift Station Upgrades ($100,000 Annually) | 6 | [5 empty] | 200000 | 248620
9061 | District Wide |  | PRT | MAINT |  |  |  | 86140 | 861409061 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 6 | [5 empty] | 1000000 | 1243100
9061 | District Wide |  | PRT | MAINT |  |  |  | 85210 | 852109061 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 6 |  | 3913 |  |  |  | 400000 | 497240
9061 | District Wide |  | PRT | MAINT |  |  |  | 81000 | 810009061 | Annual Portable Maintenance & Moving ($100,000 Annually) | 6 | [5 empty] | 200000 | 248620
9061 | District Wide |  | PRT | MAINT |  |  |  | 85220 | 852209061 | Annual Security Cameras & Alarms | 6 | [5 empty] | 200000 | 248620
9430 | District Wide |  | ATH | MAINT |  |  |  | 82050 | 820509430 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 6 | [5 empty] | 300000 | 372930
9430 | District Wide |  | ATH | MAINT |  |  |  | 82040 | 820409430 | Annual Sound System Repairs ($75,000 Annually) | 6 | [5 empty] | 150000 | 186465
9012 | District Wide |  | PLAN | PLAN |  |  |  | 89990 | 899909012 | Property Acquisition - Elementary site #3 in Wiregrass | 6 | [5 empty] | 750000 | 932325
0084 | Double Branch ES | 2007 | FNS | FNS |  |  |  | 85250 | 852500084 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 583619 | 725496.7789
0086 | Dr. John Long MS | 2006 | FNS | CS&CC |  |  |  | 85250 | 852500086 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0114 | Fivay HS | 2010 | FNS | CS&CC |  |  |  | 85250 | 852500114 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0351 | Fox Hollow ES | 1990 | FNS | FNS |  |  |  | 84070 | 840700351 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0083 | Gulf Highlands ES | 2006 | FNS | FNS |  |  |  | 85250 | 852500083 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 583619 | 725496.7789
0331 | Gulf HS | 1971 | PRT | MAINT |  |  |  | 85120 | 851200331 | Replace Quarry Tile throughout campus | 6 | [5 empty] | 355000 | 441300.5
0261 | Gulf MS | 1964 | FNS | CS&CC |  |  |  | 85250 | 852500261 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0093 | Gulf Trace ES | 2008 | FNS | FNS |  |  |  | 85250 | 852500093 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 641980 | 798045.338
0911 | Gulfside ES | 1977 | SCHOOL | CS&CC |  |  |  | 86190 | 861900911 | Covered Walkways - 224' each side of school | 6 | [5 empty] | 0 | 0 |  | New
0242 | Harry Schwettman EC | 1923 | FNS | CS&CC |  |  |  | 85250 | 852500242 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0521 | Hudson HS | 1973 | CCTE | CS&CC |  |  |  | 85230 | 852300521 | Agriculture Barn for Vet Assisting Program | 6 | [5 empty] | 50000 | 62155
0521 | Hudson HS | 1973 | SCHOOL | CS&CC |  |  |  | 86190 | 861900521 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 100000 | 124310
0073 | J.W. Mitchell HS | 2000 | SCHOOL | CS&CC |  |  |  | 86190 | 861900073 | Covered Walkways | 6 | [5 empty] | 150000 | 186465
7071 | James Irvin EC | 1995 | SCHOOL | CS&CC |  |  |  | 86190 | 861907071 | Covered Walkways | 6 | [5 empty] | 135600 | 168564.36
2081 | Longleaf ES | 2005 | FNS | FNS |  |  |  | 85250 | 852502081 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 530562 | 659541.6222
0451 | Mary Giella ES | 1989 | SCHOOL | CS&CC |  |  |  | 86190 | 861900451 | Covered Walkways | 6 | [5 empty] | 110000 | 136741
9019 | New Elementary School |  | PLAN | CS&CC | Yes |  |  | 87099 | 870999019 | Elementary Q - 54 Corridor near Suncoast Parkway | 6 | [5 empty] | 20121372 | 25012877.5332
0092 | New River ES | 2007 | FNS | FNS |  |  |  | 85250 | 852500092 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 641980 | 798045.338
0501 | Northwest ES | 1973 | FNS | CS&CC |  |  |  | 85250 | 852500501 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0082 | Oakstead ES | 2006 | FNS | CS&CC |  |  |  | 85250 | 852500082 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0082 | Oakstead ES | 2006 | FNS | FNS |  |  |  | 84070 | 840700082 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0089 | Paul R. Smith MS | 2006 | FNS | CS&CC |  |  |  | 85250 | 852500089 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0089 | Paul R. Smith MS | 2006 | FNS | FNS |  |  |  | 86200 | 862000089 | Outside Dining Sun Shade | 6 | [5 empty] | 10000 | 12431
0902 | Pine View ES | 2003 | SCHOOL | CS&CC |  |  |  | 86190 | 861900902 | Covered Walkways | 6 | [5 empty] | 30000 | 37293
0902 | Pine View ES | 2003 | FNS | CS&CC |  |  |  | 85250 | 852500902 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0902 | Pine View ES | 2003 | FNS | FNS |  |  |  | 84070 | 840700902 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  |  | 86190 | 861900921 | Covered Walkways - ESE | 6 |  | 3913 |  |  |  | 406000 | 504698.6
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  |  | 86190 | 861900921 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 550000 | 683705
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  |  | 86190 | 861900921 | Covered Walkways - Car Loop | 6 | [5 empty] | 418000 | 519615.8
0921 | Pine View MS | 1977 | FNS | FNS |  |  |  | 84070 | 840700921 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0361 | Quail Hollow ES | 1975 | FNS | CS&CC |  |  |  | 85110 | 851100361 | A/C Renovation To Kitchen | 6 | [5 empty] | 204750 | 254524.725
0361 | Quail Hollow ES | 1975 | FNS | CS&CC |  |  |  | 85250 | 852500361 | Kitchen Renovation | 6 | [5 empty] | 1037831 | 1290127.7161
0361 | Quail Hollow ES | 1975 | PRT | CS&CC |  |  |  | 86150 | 861500361 | Traffic Safety and Parking Improvements | 6 | [5 empty] | 210000 | 261051
0361 | Quail Hollow ES | 1975 | FNS | FNS |  |  |  | 84070 | 840700361 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0361 | Quail Hollow ES | 1975 | SCHOOL | MAINT |  |  |  | 86190 | 861900361 | Covered Walkways | 6 | [5 empty] | 55000 | 68370.5
0102 | R.B. Stewart MS | 1926 | FNS | FNS |  |  |  | 84070 | 840700102 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0931 | Ridgewood HS | 1977 | ATH | CS&CC |  |  |  | 82020 | 820200931 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 6 | [5 empty] | 2500000 | 3107750
0471 | River Ridge HS | 1990 | SCHOOL | CS&CC |  |  |  | 86190 | 861900471 | Covered Walkways | 6 | [5 empty] | 300000 | 372930
0471 | River Ridge HS | 1990 | PRT | FOSM |  |  |  | 85110 | 851100471 | HVAC Replace 450 Ton & 250 Ton Chillers | 6 | [5 empty] | 500000 | 621550
0472 | River Ridge MS | 1990 | SCHOOL | CS&CC |  |  |  | 86190 | 861900472 | Covered Walkways | 6 | [5 empty] | 166000 | 206354.6
2061 | Sand Pine ES | 1998 | FNS | FNS |  |  |  | 84070 | 840702061 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
2061 | Sand Pine ES | 1998 | SCHOOL | MAINT |  |  |  | 86190 | 861902061 | Covered Walkways | 6 | [5 empty] | 13000 | 16160.3
2091 | Seven Oaks ES | 2005 | FNS | FNS |  |  |  | 85250 | 852502091 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 530562 | 659541.6222
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  |  | 85250 | 852500411 | Cooler / Freezer with Renovations | 6 | [5 empty] | 340000 | 422654
0411 | Seven Springs ES | 1987 | SCHOOL | MAINT |  |  |  | 86190 | 861900411 | Covered Walkways | 6 | [5 empty] | 28980 | 36025.038
0057 | Seven Springs MS | 1995 | SCHOOL | CS&CC |  |  |  | 86200 | 862000057 | Covered Walkways | 6 | [5 empty] | 80000 | 99448
0101 | Sunlake HS | 2007 | FNS | CS&CC |  |  |  | 85250 | 852500101 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0072 | Sunray ES | 2000 | SCHOOL | MAINT |  |  |  | 86190 | 861900072 | Covered Walkways | 6 | [5 empty] | 30000 | 37293
0461 | Thomas E. Weightman MS | 1990 | SCHOOL | CS&CC |  |  |  | 86190 | 861900461 | Covered Walkways | 6 | [5 empty] | 194400 | 241658.64
0461 | Thomas E. Weightman MS | 1990 | PRT | CS&CC |  |  |  | 86110 | 861100461 | Traffic Safety and Parking Improvements | 6 |  | 3913 |  |  |  | 540000 | 671274
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC |  |  |  | 85250 | 852500085 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0110 | Veterans ES | 2008 | FNS | FNS |  |  |  | 85250 | 852500110 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 706178 | 877849.8718
0063 | Wesley Chapel HS | 1998 | SCHOOL | MAINT |  |  |  | 86190 | 861900063 | Covered Walkways | 6 | [5 empty] | 20000 | 24862
0091 | West Zephyrhills ES | 1958 | SCHOOL | CS&CC |  |  |  | 86190 | 861900091 | Covered Walkways | 6 | [5 empty] | 220000 | 273482
0091 | West Zephyrhills ES | 1958 | PRT | FOSM |  |  |  | 85110 | 851100091 | HVAC Replace Control System | 6 | [5 empty] | 600000 | 745860
0090 | Wiregrass Ranch HS | 2006 | FNS | CS&CC |  |  |  | 85250 | 852500090 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0090 | Wiregrass Ranch HS | 2006 | FNS | FNS |  |  |  | 84070 | 840700090 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0132 | Woodland ES | 1977 | SCHOOL | CS&CC |  |  |  | 86190 | 861900132 | Covered Walkways | 6 | [5 empty] | 432000 | 537019.2
9032 | District Wide |  | FIN | FIN |  |  |  | 84220 | 842209032 | Annual Other Vehicles |  | 13/14 | 3715 | 200000
9420 | District Wide |  | IS | IS |  |  |  | 84080 | 840809420 | Administrative Computers |  | 13/14 | 3714 | 1430000
9420 | District Wide |  | IS | IS |  |  |  | 84060 | 840609420 | Student Teacher Computers |  | 13/14 | 3900 | 4000000
0031 | Pasco HS | 1964 | PRT | CS&CC |  |  |  | 85000 | 850000031 | Master Redevelopment |  | 1314 | 3903 | 129375
Priority Code | Year | Escalator | [7 empty] | Totals | All | [5 empty] | 1090750084.7225 | 1166898794.3553
1 | 12/13 - 13/14 | 0% | [7 empty] | Total for Priority 1 | 1 | [5 empty] | 292053206.725 | 292053206.725
2 | 14/15 - 15/16 | 4.45% | [7 empty] | Total for Priority 2 | 2 | [5 empty] | 159697302.2475 | 164003074.332
3 | 16/17 - 17/18 | 9.09% | [7 empty] | Total for Priority 3 | 3 | [5 empty] | 158333382 | 168149926.9746
4 | 18/19 - 19/20 | 13.95% | [7 empty] | Total for Priority 4 | 4 | [5 empty] | 144911533 | 157515337.4935
5 | 20/21 - 21/22 | 19.02% | [7 empty] | Total for Priority 5 | 5 | [5 empty] | 192508477.75 | 219490521.1178
6 | 22/23 - 23/24 | 24.31% | [7 empty] | Total for Priority 6 | 6 | [5 empty] | 143246183 | 165686727.7123
|  | = | 2013-2014 Budget Year Projects
|  | = | Penny for Pasco Projects

## Original 13 - 14
Cost Center | School Name | Year Open | Request Dept | Assigned Dept | Large Cap Project | In-House Maint Prj | MUNIS | Project Description | Priority | Bgt Yr | FUND | AMT | Revised | Type | Budget Estimate | Adjusted Estimate | Final Cost | Status | Notes
0000 | District Wide |  | FIN | FIN |  |  | 00000 | Annual Debt Service Payments | 1 | 13/14 | 3714 3903 3921 | 34821519 |  |  | 38816856 | 38816856
0000 | District Wide |  | FIN | FIN |  |  | 00000 | Property Insurance | 1 | 13/14 | 3714 | 827000 |  |  | 827000 | 827000
0000 | District Wide |  | FIN | FIN |  |  | 00000 | Annual Debt Service Payments | 2 | [5 empty] | 62938379 | 62938379
0000 | District Wide |  | FIN | FIN |  |  | 00000 | Annual Debt Service Payments | 3 | [5 empty] | 50340588 | 50340588
0000 | District Wide |  | FIN | FIN |  |  | 00000 | Annual Debt Service Payments | 4 | [5 empty] | 54561680 | 54561680
0000 | District Wide |  | FIN | FIN |  |  | 00000 | Annual Debt Service Payments | 5 | [5 empty] | 50647051 | 50647051
0000 | District Wide |  | FIN | FIN |  |  | 00000 | Annual Debt Service Payments | 6 | [5 empty] | 50936250 | 50936250
0021 | R. B. Cox ES | 1925 | PRT | CS&CC |  |  | 86100 | Remodel School - Build New Cafeteria, Tear Down Old Cafeteria, Remove Concrete Portables, Traffic And Parking Improvements, Replace Remaining Old Windows, Install Securtiy System | 2 | 13/14 | 3921 | 7500000 |  |  | 6510441 | 6800155.6245
0021 | R. B. Cox ES | 1925 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0031 | Pasco HS | 1964 | ATH | MAINT | Yes |  | 82020 | Football Stadium Concession Stands, Etc. | 1 | [8 empty] | Community Project / Donation
0031 | Pasco HS | 1964 | PRT | CS&CC | Yes |  | 86100 | Master Plan Redevelopment - Finish Road/Retaining Wall | 1 | 13/14 | 3903 | 330487 |  | Penny/Intrl | 385148 | 385148 | 250000 | In Progress
0031 | Pasco HS | 1964 | PRT | CS&CC |  |  | 85000 | Master Redevelopment |  | 1314 | 3903 | 129375
0031 | Pasco HS | 1964 | ATH | MAINT |  |  | 82050 | Lighting - Replace Baseball Field | 2 | [5 empty] | 100000 | 104450
0031 | Pasco HS | 1964 | ATH | CS&CC |  |  | 82050 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 2 | [5 empty] | 2500000 | 2611250
0031 | Pasco HS | 1964 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0031 | Pasco HS | 1964 | PRT | FOSM |  |  | 85110 | HVAC Replace 250 ton chiller | 5 | [5 empty] | 250000 | 297550
0031 | Pasco HS | 1964 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 5 | [5 empty] | 1079880 | 1285273.176
0032 | Trinity ES | 2000 | FNS | MAINT |  |  | 85250 | Renovate Kitchen Floors | 1 | 13/14 | 3709 3711 | 84881 |  |  | 57881 | 57881 |  | Product Evaluation
0032 | Trinity ES | 2000 | MAINT | MAINT |  |  | 85200 | Replace Gutters | 1 | 13/14 | 3103 | 50000 |  |  | 50000 | 50000
0032 | Trinity ES | 2000 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0032 | Trinity ES | 2000 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0032 | Trinity ES | 2000 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0057 | Seven Springs MS | 1995 | ATH | MAINT |  |  | 82050 | Basketball Court/Tennis Overlay | 1 | 13/14 | 3711 | 18635 |  |  | 6366 | 6366 |  | Summer
0057 | Seven Springs MS | 1995 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 1 | 13/14 | 3709 | 18819 |  |  | 184638 | 184638 |  | Summer
0057 | Seven Springs MS | 1995 | PRT | CS&CC |  |  | 85110 | HVAC Chiller Pipe Replacement | 1 | 13/14 | 3611 | 721373 |  |  | 68774 | 68774 |  | In Progress
0057 | Seven Springs MS | 1995 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 650000 | 650000 |  |  | IS needs to prioritze
0057 | Seven Springs MS | 1995 | PRT | MAINT |  |  | 84048 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 125000 | 125000 |  | In Progress
0057 | Seven Springs MS | 1995 | ATH | MAINT |  |  | 82040 | Sound Panel Refurb In Gym | 2 | 13/14 | 3710 3711 |  |  |  | 75000 | 78337.5 |  | Completed
0057 | Seven Springs MS | 1995 | SCHOOL | CS&CC |  |  | 86200 | Covered Walkways | 6 | [5 empty] | 80000 | 99448
0059 | Denham Oaks ES | 1994 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000
0059 | Denham Oaks ES | 1994 | PRT | MAINT |  |  | 85200 | Roof Maintenance and Internal Gutters | 3 | [5 empty] | 50000 | 54545
0059 | Denham Oaks ES | 1994 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0059 | Denham Oaks ES | 1994 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0059 | Denham Oaks ES | 1994 | PRT | FOSM |  |  | 85110 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 40000 | 45580
0059 | Denham Oaks ES | 1994 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0059 | Denham Oaks ES | 1994 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 135000 | 167818.5
0060 | Chester Taylor ES | 1996 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0060 | Chester Taylor ES | 1996 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 2 | [5 empty] | 80000 | 83560
0060 | Chester Taylor ES | 1996 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 3 | [5 empty] | 195000 | 212725.5
0060 | Chester Taylor ES | 1996 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0060 | Chester Taylor ES | 1996 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0060 | Chester Taylor ES | 1996 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0060 | Chester Taylor ES | 1996 | PRT | FOSM |  |  | 85110 | HVAC Replace Control System | 6 | [5 empty] | 400000 | 497240
0061 | Pasco ES | 1954 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0061 | Pasco ES | 1954 | PRT | CS&CC |  |  | 86100 | Renovate Bld #1-7, #9, #20, #21, #41 | 2 | 13/14 | 3921 | 5614560 |  |  | 5614560 | 5864407.92 |  |  | added Bld 9 to include cafeteria serving line renovation
0061 | Pasco ES | 1954 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 5 | 13/14 | 3709 | 76103 |  |  | 80709 | 96059.8518
0063 | Wesley Chapel HS | 1998 | ATH | MAINT |  |  | 82020 | Add Air Conditioning To Field House | 1 | 13/14 | 3709 33710 3711 | 106499 |  |  | 6053 | 6053 |  | Complete
0063 | Wesley Chapel HS | 1998 | CCTE | CS&CC |  |  | 85240 | Career Academy - Automotive | 1 | 13/14 | 3712 | 43499 |  |  | 16416 | 16416 |  |  | Carry Forward from 12/13
0063 | Wesley Chapel HS | 1998 | PRT | FOSM |  |  | 85110 | HVAC controls replacement phase 2 | 1 | [5 empty] | 350000 | 350000
0063 | Wesley Chapel HS | 1998 | PRT | CS&CC |  |  | 85140 | Maintenance of Drainage Canal behind school complex | 1 | [5 empty] | 0 | 0
0063 | Wesley Chapel HS | 1998 | ATH | MAINT |  |  | 82050 | Overlay Courts | 1 | [5 empty] | 150000 | 150000
0063 | Wesley Chapel HS | 1998 | ATH | ATH |  |  | 82040 | Scoreboard Replacement(s) | 1 | [5 empty] | 75000 | 75000
0063 | Wesley Chapel HS | 1998 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 800000 | 835600
0063 | Wesley Chapel HS | 1998 | PRT | FOSM |  |  | 85110 | HVAC Replace 400 Ton Chiller | 3 | [5 empty] | 300000 | 327270
0063 | Wesley Chapel HS | 1998 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 4 | [5 empty] | 100000 | 113950
0063 | Wesley Chapel HS | 1998 | SCHOOL | MAINT |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 20000 | 24862
0065 | James M. Marlowe ES | 1998 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0065 | James M. Marlowe ES | 1999 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 3 | [5 empty] | 80000 | 87272
0065 | James M. Marlowe ES | 1999 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0065 | James M. Marlowe ES | 1999 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0069 | Centennial MS | 2001 | FNS | MAINT |  |  | 84070 | Cooler/Freezer Flooding | 1 | [5 empty] | 70000 | 70000
0069 | Centennial MS | 2001 | PRT | CS&CC |  |  | 85190 | EHPA Generator Shelter | 1 | 13/14 | 3712 | 50000 |  |  | 60000 | 60000 |  |  | Well and Sanitary Lift coded to Centennial ES 0401
0069 | Chasco MS | 2001 | PRT | MAINT |  |  | 85200 | Replace Gutters | 1 | 13/14 | 3101 | 91776 |  |  | 91250 | 91250 |  | Purchasing
0069 | Centennial MS | 2001 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | On Hold
0069 | Chasco MS | 2001 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 2 | [5 empty] | 66701.25 | 69669.4556
0069 | Chasco MS | 2001 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0069 | Chasco MS | 2000 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 4 | [5 empty] | 25000 | 28487.5
0069 | Chasco MS | 2001 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 650000 | 740675
0069 | Chasco MS | 2001 | FNS | FNS |  |  | 86200 | Outside Dining Sun Shade | 5 | [5 empty] | 8000 | 9521.6
0069 | Chasco MS | 2001 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 5 | [5 empty] | 811329.75 | 965644.6684
0070 | Chasco ES | 2000 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 4 | [5 empty] | 40000 | 45580
0070 | Chasco ES | 2000 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0070 | Chasco ES | 2000 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0070 | Chasco ES | 2000 | PRT | FOSM |  |  | 85110 | HVAC (2) 300 ton chillers | 5 | [5 empty] | 600000 | 714120
0070 | Chasco ES | 2000 | FNS | CS&CC |  |  | 85250 | Kitchen Renovation | 5 | [5 empty] | 943483 | 1122933.4666
0070 | Chasco ES | 2000 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 100000 | 124310
0070 | Chasco ES | 2000 | SCHOOL | MAINT |  |  | 85000 | Restroom for PE Classes | 6 | [5 empty] | 300000 | 372930 |  | New | Evaluating
0071 | Pasco MS | 1946 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms - CCTE Building | 1 | [5 empty] | 10000 | 10000 |  | On Hold
0071 | Pasco MS | 1946 | ATH | CS&CC |  |  | 82050 | Replace Gym Floor | 5 | [5 empty] | 175000 | 208285 |  |  | Gym Floor Synthetic Overlay just complete - does that replace this project?
0072 | Sunray ES | 2000 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0072 | Sunray ES | 2000 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 3 | [5 empty] | 80000 | 87272
0072 | Sunray ES | 2000 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
0072 | Sunray ES | 2000 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0072 | Sunray ES | 2000 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0072 | Sunray ES | 2000 | SCHOOL | MAINT |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 30000 | 37293
0073 | J.W. Mitchell HS | 2000 | FNS | CS&CC |  |  | 85250 | Kitchen Renovation - Phase 2 | 1 | 13/14 | 3611 3709 | 1859973 |  |  | 1343003 | 1343003 |  | Summer
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT |  |  | 82050 | Overlay Courts - Tennis | 1 | 13/14 | 3711 | 35000 |  |  | 35000 | 35000
0073 | J.W. Mitchell HS | 2000 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 150000 | 150000 |  | On Hold
0073 | J.W. Mitchell HS | 2000 | ATH | CS&CC |  |  | 82050 | Refurbish Football Field Elevation and Field Drainage | 3 | [5 empty] | 320000 | 349088
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT |  |  | 81150 | Storage Garage | 4 | [5 empty] | 25000 | 28487.5
0073 | J.W. Mitchell HS | 2000 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
0073 | J.W. Mitchell HS | 2000 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 150000 | 186465
0074 | Centennial MS | 2001 | FNS | FNS |  |  | 86200 | Outside Dining Sun Shade | 4 | [5 empty] | 10000 | 11395
0074 | Centennial MS | 2001 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 4 | [5 empty] | 80000 | 91160
0074 | Centennial MS | 2001 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 4 | [5 empty] | 981709 | 1118657.4055
0074 | Centennial MS | 2001 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 650000 | 740675
0074 | Centennial MS | 2001 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | 13/14 | 3709 | 89711 |  |  | 88779 | 110361.1749
0074 | Centennial MS | 2001 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 130000 | 161603
0074 | Centennial MS | 2001 | PRT | FOSM |  |  | 85110 | HVAC Replace Control System | 6 | [5 empty] | 600000 | 745860
0081 | Moore Mickens EC | 1952 | CTE | MAINT |  |  | 85000 | Remodel CNA Room | 1 | [5 empty] | 108000 | 108000
0081 | Moore Mickens EC | 1952 | CTE | MAINT |  |  | 85000 | Remodel Or Build New Space For Cosmetology | 1 | [5 empty] | 600000 | 600000
0081 | Moore Mickens EC | 1952 | MAINT | MAINT |  |  | 85200 | Roof Repair - Building 1 Metal Roof | 1 | 13/14 | 3101 | 60000 |  |  | 60000 | 60000
0081 | Moore Mickens EC | 1952 | PRT | MAINT |  |  | 85000 | Remodel School | 2 | [5 empty] | 445419 | 465240.1455
0081 | Moore Mickens EC | 1952 | FNS | MAINT |  |  | 84070 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0081 | Moore Mickens EC | 1952 | PRT | CS&CC |  |  | 86100 | Redevelopment of Campus | 5 | [5 empty] | 5000000 | 5951000 |  | On Hold
0082 | Oakstead ES | 2006 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0082 | Oakstead ES | 2006 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0082 | Oakstead ES | 2006 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0083 | Gulf Highlands ES | 2006 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0083 | Gulf Highlands ES | 2006 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0083 | Gulf Highlands ES | 2006 | FNS | FNS |  |  | 85250 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 583619 | 725496.7789
0084 | Double Branch ES | 2007 | PRT | CS&CC |  |  | 86150 | Traffic Safety and Parking Improvements - Add Turn Lane to Chauncey | 2 | 14/15 |  |  |  |  | 500000 | 522250 |  |  | County beginning design of extension
0084 | Double Branch ES | 2007 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0084 | Double Branch ES | 2007 | FNS | FNS |  |  | 85250 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 583619 | 725496.7789
0085 | Trinity Oaks ES | 2007 | PRT | CS&CC |  |  | 85110 | Add Dehumidification | 1 | 13/14 | 3709 3711 | 74148 |  |  | 1006 | 1006 |  | In Progress
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0086 | Dr. John Long MS | 2006 | PRT | CS&CC |  |  | 86100 | Addition - Classroom Wing | 3 | [5 empty] | 4000000 | 4363600
0086 | Dr. John Long MS | 2006 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 3 | [5 empty] | 25000 | 27272.5
0086 | Dr. John Long MS | 2006 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0089 | Paul R. Smith MS | 2006 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 3 | [5 empty] | 25000 | 27272.5
0089 | Paul R. Smith MS | 2006 | FNS | FNS |  |  | 86200 | Outside Dining Sun Shade | 6 | [5 empty] | 10000 | 12431
0089 | Paul R. Smith MS | 2006 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT |  |  | 82020 | Add Air Conditioning To Field House | 1 | 13/14 | 3708 3710 3711 | 106607 |  |  | 6162 | 6162 |  | Complete
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC | Yes |  | 86110 | Traffic Light @ Mansfield | 1 | 13/14 | 3611 | 125000 |  |  | 125000 | 125000 |  |  | Need to add to 5-Year Work Plan Infrastructure
0090 | Wiregrass Ranch HS | 2006 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms - audio only | 1 | [5 empty] | 51000 | 51000 |  | On Hold
0090 | Wiregrass Ranch HS | 2006 | CCTE | CS&CC |  |  | 85240 | Remodel/Expand Culinary Classroom | 2 | [5 empty] | 420000 | 438690
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC |  |  | 86100 | Addition - Classroom Wing | 3 | [5 empty] | 4000000 | 4363600
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT |  |  | 82050 | Overlay Courts - Basketball & Tennis | 4 | [5 empty] | 25000 | 28487.5
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 5 | [5 empty] | 40000 | 47608
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH |  |  | 82040 | Scoreboard Replacement(s) | 5 | [5 empty] | 75000 | 89265
0090 | Wiregrass Ranch HS | 2006 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0090 | Wiregrass Ranch HS | 2006 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0091 | West Zephyrhills ES | 1958 | MAINT | MAINT |  |  | 85200 | Roof Replacement - Cafeteria and Media | 1 | 13/14 | 3101 | 301220 |  |  | 301220 | 301220 |  | Design Complete
0091 | West Zephyrhills ES | 1958 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0091 | West Zephyrhills ES | 1958 | PRT | CS&CC |  |  | 86100 | Remodel School - Tear Down Or Remodel Cafeteria Bld #2 Into Classrooms, Renovate Bld #1,3,4,5,8,9,14 | 2 | [5 empty] | 8226665 | 8592751.5925
0091 | West Zephyrhills ES | 1958 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 220000 | 273482
0091 | West Zephyrhills ES | 1958 | PRT | FOSM |  |  | 85110 | HVAC Replace Control System | 6 | [5 empty] | 600000 | 745860
0092 | New River ES | 2007 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0092 | New River ES | 2007 | FNS | FNS |  |  | 85250 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 641980 | 798045.338
0093 | Gulf Trace ES | 2008 | PRT | CS&CC |  |  | 86110 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3710 3711 3712 3713 3902 | 582703 |  |  | 90576 | 90576 |  | In Progress | Need addl funding - $165,000 more than original $490,000
0093 | Gulf Trace ES | 2008 | FNS | FNS |  |  | 85250 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 641980 | 798045.338
0100 | Charles S. Rushe MS | 2007 | ATH | ATH |  |  | 82050 | Resurface Track Courts | 5 | [5 empty] | 50000 | 59510
0100 | Charles S. Rushe MS | 2007 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0100 | Charles S. Rushe MS | 2007 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0101 | Sunlake HS | 2007 | ATH | MAINT |  |  | 82020 | Add Air Conditioning To Field House | 1 | 13/14 | 3708 3710 3711 3713 | 109416 |  |  | 6108 | 6108 |  | Complete
0101 | Sunlake HS | 2007 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0101 | Sunlake HS | 2007 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  | 86100 | Remodel Bld #4 #5 (Media And ESE) | 1 | 13/14 | 3903 |  |  |  | 1496472 | 1496472 |  |  | Combined with Gym Replacement in Priority 1
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  | 86100 | Replace Gym Bld #3 - Phase 1 | 1 | 13/14 | 3903 | 5547405 |  |  | 1400000 | 1400000 |  | In Progress
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Yes |  | 86100 | Replace Gym Bld #3 - Phase 2 | 1 | 13/14 | 3903 |  |  |  | 1750000 | 1750000 |  | Funding | Need $1.4 million additional
0102 | R.B. Stewart MS | 1926 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | On Hold
0102 | R.B. Stewart MS | 1926 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0103 | Crews Lake MS | 2008 | ATH | ATH |  |  | 82050 | Resurface Track Courts | 5 | [5 empty] | 50000 | 59510
0103 | Crews Lake MS | 2008 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0103 | Crews Lake MS | 2008 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 2314818 | 2877550.2558
0110 | Veterans ES | 2008 | FNS | FNS |  |  | 85250 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 706178 | 877849.8718
0113 | Anclote HS | 2009 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 5 | [5 empty] | 25000 | 29755
0113 | Anclote HS | 2009 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0114 | Fivay HS | 2010 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0131 | Zephyrhills HS | 1973 | PRT | MAINT |  |  | 85110 | Rebuild Gym Air Handlers | 1 | 13/14 | 3900 |  |  |  | 89671 | 89671 |  | Summer
0131 | Zephyrhills HS | 1973 | ATH | CS&CC | Yes |  | 82020 | Weight Room Renovation/Expansion | 1 | 13/14 | 3712 3903 |  |  |  | 468257 | 468257
0131 | Zephyrhills HS | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 800000 | 835600
0131 | Zephyrhills HS | 1973 | CCTE | CS&CC |  |  | 85240 | Remodel Automotive Technology To Lab Space/Convert To Health Academy | 3 |  | 3913 |  |  |  | 560000 | 610904
0131 | Zephyrhills HS | 1973 | PRT | CS&CC |  |  | 86100 | Remodel School - Kelley School + Add Capacity | 3 |  | 3913 |  |  |  | 20600000 | 22472540
0131 | Zephyrhills HS | 1973 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0131 | Zephyrhills HS | 1973 | ATH | CS&CC |  |  | 82020 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0131 | Zephyrhills HS | 1973 | ATH | MAINT |  |  | 82050 | Overlay Tennis Court | 5 | [5 empty] | 50000 | 59510
0132 | Woodland ES | 1977 | PRT | MAINT |  |  | 83260 | Fencing - Install Aluminum Weld Fence at Front Entrance and to Clinic Safety Issue | 1 | 13/14 | 3611 |  |  |  | 21000 | 21000 |  | Complete
0132 | Woodland ES | 1977 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000
0132 | Woodland ES | 1977 | PRT | FOSM |  |  | 85110 | HVAC Upgrade - Phase 2 | 3 | [5 empty] | 4447860 | 4852170.474
0132 | Woodland ES | 1977 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0132 | Woodland ES | 1977 | PRT | CS&CC |  |  | 86100 | Remodel School, Expand Cafeteria | 5 |  | 3913 |  |  |  | 4514705 | 5373401.891
0132 | Woodland ES | 1977 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 432000 | 537019.2
0201 | Sanders Memorial ES | 1944 | PRT | CS&CC | Yes |  | 86100 | Campus Redevelopment | 1 | 13/14 | 3900 3904 | 15718272 |  |  | 16902130 | 16902130 |  | Open 2015 | Site Work Completed
0211 | Mittye P. Locke ES | 1966 | PRT | CS&CC |  |  | 83260 | Fire Egress Remodeling to Pre-K Building | 1 | [5 empty] | 20000 | 20000 |  | TBD | Pre-K moving to Richey Elem?
0211 | Mittye P. Locke ES | 1966 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0211 | Mittye P. Locke ES | 1966 | FNS | CS&CC |  |  | 85250 | Kitchen Renovation | 2 | [5 empty] | 708852 | 740395.914
0211 | Mittye P. Locke ES | 1966 | PRT | CS&CC |  |  | 86100 | Remodel School, Replace Covered Walks, Traffic Improvements | 3 |  | 3913 |  |  |  | 8000000 | 8727200
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC |  |  | 85200 | Roof Coating | 1 | 13/14 | 3101 | 40000 |  |  | 40000 | 40000
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC |  |  | 00000 | Determine Long Range Use | 5 | [6 empty] | 0
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC |  |  | 85000 | Remodel School | 5 | [5 empty] | 266999 | 317782.2098
0242 | Harry Schwettman EC | 1923 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0251 | San Antonio ES | 1981 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0251 | San Antonio ES | 1981 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0251 | San Antonio ES | 1981 | PRT | FOSM |  |  | 85110 | HVAC Upgrade - Phase 2 | 2 | [5 empty] | 1300000 | 1357850
0251 | San Antonio ES | 1981 | PRT | CS&CC |  |  | 86100 | Remodel Bld #1 #2 #10 | 5 |  | 3913 |  |  |  | 3965541 | 4719786.8982
0261 | Gulf MS | 1964 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 125000 | 125000 |  | On Hold
0261 | Gulf MS | 1964 | PRT | MAINT |  |  | 85000 | Renovate Restroom Bld #17 | 2 | [5 empty] | 100000 | 104450
0261 | Gulf MS | 1964 | FNS | MAINT |  |  | 85250 | Kitchen Renovation Flooring, Paint, Ovens, Steamers | 3 | [5 empty] | 120329 | 131266.9061
0261 | Gulf MS | 1964 | PRT | CS&CC |  |  | 86100 | Remodel School Bld 1, 2, 3, 9. 10, 11, 14 | 3 | [5 empty] | 8653000 | 9439557.7
0261 | Gulf MS | 1964 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 4 | [5 empty] | 25000 | 28487.5
0261 | Gulf MS | 1964 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 650000 | 773630
0261 | Gulf MS | 1964 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 1187868 | 1476638.7108
0271 | Richey ES | 1958 | PRT | CS&CC |  |  | 86100 | Campus Redevelopment - Master Plan | 1 | 13/14 | 3900 3904 | 1761576 |  | Imp/Intrl | 760236 | 760236 |  | Close Out
0301 | Hudson ES | 1966 | FNS | MAINT |  |  | 85250 | Kitchen Floor Renovation | 2 | [5 empty] | 35280 | 36849.96
0301 | Hudson ES | 1966 | PRT | CS&CC |  |  | 85000 | Remodel Restrooms ADA | 2 | [5 empty] | 700000 | 731150
0301 | Hudson ES | 1966 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0301 | Hudson ES | 1966 | FNS | CS&CC |  |  | 85250 | Remodel Kitchen And Serving Line | 3 | [5 empty] | 779738 | 850616.1842
0301 | Hudson ES | 1966 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0302 | Hudson ES | 1967 | PRT | CS&CC |  |  | 85000 | Remodel Bld #1 | 3 |  | 3913 |  |  |  | 400000 | 436360
0311 | Cotee River ES | 1993 | PRT | MAINT |  |  | 85250 | Roof Replacement | 1 | 13/14 | 3611 | 700000 |  |  | 700000 | 700000
0311 | Cotee River ES | 1993 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000
0311 | Cotee River ES | 1993 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0311 | Cotee River ES | 1993 | PRT | CS&CC |  |  | 86150 | Traffic Safety and Parking Improvements | 3 |  | 3913 |  |  |  | 1000000 | 1090900
0311 | Cotee River ES | 1993 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 4 | [5 empty] | 73371 | 83606.2545
0311 | Cotee River ES | 1993 | PRT | FOSM |  |  | 85110 | HVAC Replace (2) chillers & controls | 4 | [5 empty] | 80000 | 91160
0311 | Cotee River ES | 1993 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 162000 | 201382.2
0321 | Lacoochee ES | 1971 | FNS | FNS |  |  | 86100 | Remodel - Add Multi-purpose Space | 1 | 13/14 | 3709 | 10000 |  |  | 10000 | 10000
0321 | Lacoochee ES | 1971 | FNS | FNS |  |  | 85250 | Kitchen Hood | 2 | [5 empty] | 60775 | 63479.4875
0321 | Lacoochee ES | 1971 | FNS | CS&CC |  |  | 85250 | Kitchen Renovation | 2 | [5 empty] | 708852 | 740395.914
0321 | Lacoochee ES | 1971 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0321 | Lacoochee ES | 1971 | PRT | CS&CC |  |  | 86100 | Remodel Classroom Bld #8,9,11,12,13 | 4 |  | 3913 |  |  |  | 1348655 | 1536792.3725
0331 | Gulf HS | 1971 | FNS | CS&CC |  |  | 84070 | Cooler / Freezer | 1 | 13/14 | 3709 |  |  |  | 9879 | 9879 |  | Summer
0331 | Gulf HS | 1971 | PRT | MAINT | Yes |  | 85110 | HVAC Hydronic Boiler Replacement | 1 | 13/14 | 3709 3711 | 322281 |  |  | 330203 | 330203 | 150000 | Design
0331 | Gulf HS | 1971 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 150000 | 150000
0331 | Gulf HS | 1971 | ATH | ATH |  |  | 82040 | Scoreboard Replacement(s) | 2 | 13/14 | 3709 3713 |  |  |  | 40000 | 41780
0331 | Gulf HS | 1971 | ATH | MAINT |  |  | 85170 | Fencing - Baseball Field | 3 | [5 empty] | 20000 | 21818
0331 | Gulf HS | 1971 | ATH | MAINT |  |  | 85170 | Fencing - Tennis Court Fence | 3 | [5 empty] | 15000 | 16363.5 |  |  | Phil will check to see if need to move up in priority
0331 | Gulf HS | 1971 | PRT | FOSM |  |  | 85110 | HVAC Replace (2) 200 Ton Chillers | 4 | [5 empty] | 120000 | 136740
0331 | Gulf HS | 1971 | PRT | CS&CC |  |  | 86100 | Remodel School Phase 1 - Bld #1 | 4 |  | 3913 |  |  |  | 9150000 | 10426425
0331 | Gulf HS | 1971 | PRT | CS&CC |  |  | 86100 | Remodel School Phase 2 | 4 |  | 3913 |  |  |  | 2514150 | 2864873.925
0331 | Gulf HS | 1971 | ATH | MAINT |  |  | 85000 | Replace Wall Tile In PE Locker Room | 4 | [5 empty] | 15000 | 17092.5
0331 | Gulf HS | 1971 | ATH | CS&CC |  |  | 82020 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0331 | Gulf HS | 1971 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
0331 | Gulf HS | 1971 | PRT | MAINT |  |  | 85120 | Replace Quarry Tile throughout campus | 6 | [5 empty] | 355000 | 441300.5
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  | 86100 | Replacement Bldg #1 - Phase 1 | 1 | 13/14 | 3900 |  |  | Interlocal | 6984000 | 6984000 |  | Summer
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  | 86100 | Replacement Bldg #1 - Phase 2 | 1 | 13/14 | 3900 | 13793027 |  |  | 6520000 | 6520000 |  | Summer
0341 | Schrader ES | 1972 | PRT | CS&CC | Yes |  | 86100 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3900 | 432000 |  |  | 432000 | 432000 |  | Summer
0341 | Schrader ES | 1972 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms - Bld #9 | 1 | [5 empty] | 40000 | 40000 |  | On Hold
0341 | Schrader ES | 1972 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0342 | Bayonet Point MS | 1973 | PRT | MAINT |  |  | 85200 | Roof Replacement | 1 | [5 empty] | 1000000 | 1000000
0342 | Bayonet Point MS | 1973 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | On Hold
0342 | Bayonet Point MS | 1973 | FNS | CS&CC |  |  | 85250 | Cooler / Freezer with Renovations (Stock Room) | 2 | [5 empty] | 203963 | 213039.3535
0342 | Bayonet Point MS | 1973 | PRT | CS&CC |  |  | 86100 | Remodel School - Kelley School | 2 | 13/14 | 3921 | 15145250 |  | Penny | 15150000 | 15824175
0342 | Bayonet Point MS | 1973 | ATH | MAINT |  |  | 85000 | Renovate Girls & Boys Locker Rooms | 2 | [5 empty] | 100000 | 104450
0342 | Bayonet Point MS | 1973 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 3 | [5 empty] | 120329 | 131266.9061
0342 | Bayonet Point MS | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 650000 | 773630
0342 | Bayonet Point MS | 1973 | SCHOOL | MAINT |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 25000 | 31077.5
0351 | Fox Hollow ES | 1990 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 1 | 13/14 | 3713 | 194596 |  |  | 194596 | 194596 |  | In Progress
0351 | Fox Hollow ES | 1990 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0351 | Fox Hollow ES | 1990 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0351 | Fox Hollow ES | 1990 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0351 | Fox Hollow ES | 1990 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0361 | Quail Hollow ES | 1975 | FNS | FNS |  |  | 85250 | Kitchen Hood - Code Violations | 1 | [5 empty] | 57881 | 57881 |  | On Hold
0361 | Quail Hollow ES | 1975 | PRT | CS&CC | Yes |  | 86100 | Remodel School - Kelley School + Add Capacity | 1 | 13/14 | 3921 | 10360000 |  | Penny | 11500000 | 11500000 |  | In Design
0361 | Quail Hollow ES | 1975 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0361 | Quail Hollow ES | 1975 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0361 | Quail Hollow ES | 1975 | PRT | MAINT |  |  | 85200 | Roof Replacement | 5 | [5 empty] | 600000 | 714120
0361 | Quail Hollow ES | 1975 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 6 | [5 empty] | 204750 | 254524.725
0361 | Quail Hollow ES | 1975 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0361 | Quail Hollow ES | 1975 | SCHOOL | MAINT |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 55000 | 68370.5
0361 | Quail Hollow ES | 1975 | FNS | CS&CC |  |  | 85250 | Kitchen Renovation | 6 | [5 empty] | 1037831 | 1290127.7161
0361 | Quail Hollow ES | 1975 | PRT | CS&CC |  |  | 86150 | Traffic Safety and Parking Improvements | 6 | [5 empty] | 210000 | 261051
0401 | Centennial ES | 1986 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0401 | Centennial ES | 1986 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0401 | Centennial ES | 1986 | PRT | FOSM |  |  | 85110 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 40000 | 45580
0401 | Centennial ES | 1986 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0411 | Seven Springs ES | 1987 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0411 | Seven Springs ES | 1987 | PRT | FOSM |  |  | 85110 | HVAC Replace 200 Ton Chiller | 2 | [5 empty] | 40000 | 41780
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 4 | [5 empty] | 347047 | 395460.0565
0411 | Seven Springs ES | 1987 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0411 | Seven Springs ES | 1987 | FNS | CS&CC |  |  | 85250 | Cooler / Freezer with Renovations | 6 | [5 empty] | 340000 | 422654
0411 | Seven Springs ES | 1987 | SCHOOL | MAINT |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 28980 | 36025.038
0421 | Deer Park ES | 1988 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0421 | Deer Park ES | 1988 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0421 | Deer Park ES | 1988 | PRT | FOSM |  |  | 85110 | HVAC Replace Chiller & Controls | 4 | [5 empty] | 40000 | 45580
0421 | Deer Park ES | 1988 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 4 | [5 empty] | 347047 | 395460.0565
0421 | Deer Park ES | 1988 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0451 | Mary Giella ES | 1989 | SCHOOL | MAINT |  |  | 85170 | Fencing - Installl 6' Chain Link Fence on Bus Loop Side | 1 | [5 empty] | 25000 | 25000 |  | New
0451 | Mary Giella ES | 1989 | PRT | CS&CC | Yes |  | 86110 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3611 3713 | 381786 |  | Penny | 355826 | 355826 |  |  | Need to do in conjunction with Offsite Infrastructure Project
0451 | Mary Giella ES | 1989 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000
0451 | Mary Giella ES | 1989 | PRT | FOSM |  |  | 85110 | HVAC Replace Air Handlers & Controls | 2 | [5 empty] | 2500000 | 2611250
0451 | Mary Giella ES | 1989 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0451 | Mary Giella ES | 1989 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0451 | Mary Giella ES | 1989 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 110000 | 136741
0461 | Thomas E. Weightman MS | 1990 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 125000 | 125000
0461 | Thomas E. Weightman MS | 1990 | PRT | FOSM |  |  | 85110 | HVAC Replace (2) 200 Ton Chillers | 2 | [5 empty] | 400000 | 417800
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT |  |  | 85170 | Fencing - Tennis Court Fence | 3 | [5 empty] | 20000 | 21818 |  |  | Phil Bell will check to see if need to move up in priority
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT |  |  | 82050 | Overlay Courts | 3 | [5 empty] | 80000 | 87272
0461 | Thomas E. Weightman MS | 1990 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 5 | [5 empty] | 80709 | 96059.8518
0461 | Thomas E. Weightman MS | 1990 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 194400 | 241658.64
0461 | Thomas E. Weightman MS | 1990 | PRT | CS&CC |  |  | 86110 | Traffic Safety and Parking Improvements | 6 |  | 3913 |  |  |  | 540000 | 671274
0471 | River Ridge HS | 1990 | FNS | CS&CC |  |  | 85250 | Cafeteria Renovation - Phase 2 | 1 | 13/14 | 3611 3713 | 1866305 |  |  | 1086115 | 1086115 |  | Summer
0471 | River Ridge HS | 1990 | ATH | CS&CC |  |  | 82020 | Concession Stand Bathrooms - Baseball/Softball | 1 | 13/14 | 3710 | 280102 |  |  | 100000 | 100000 |  | Design
0471 | River Ridge HS | 1990 | PRT | CS&CC | Yes |  | 85110 | HVAC Renovation (controls) | 1 | 13/14 | 3900 | 493880 |  |  | 493880 | 493880 |  | In Progress
0471 | River Ridge HS | 1990 | CCTE | MAINT |  |  | 85000 | Open Doorway Between Engineering Rooms | 1 | [5 empty] | 50000 | 50000 |  | Hold | Olga will speak with Rob
0471 | River Ridge HS | 1990 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 150000 | 150000 |  | On Hold
0471 | River Ridge HS | 1990 | PRT | CS&CC |  |  | 85000 | Remodel Restrooms ADA | 2 | [5 empty] | 700000 | 731150
0471 | River Ridge HS | 1990 | ATH | MAINT |  |  | 85170 | Fencing - Tennis | 3 | [5 empty] | 30000 | 32727
0471 | River Ridge HS | 1990 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 800000 | 872720
0471 | River Ridge HS | 1990 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 300000 | 372930
0471 | River Ridge HS | 1990 | PRT | FOSM |  |  | 85110 | HVAC Replace 450 Ton & 250 Ton Chillers | 6 | [5 empty] | 500000 | 621550
0472 | River Ridge MS | 1990 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | On Hold
0472 | River Ridge MS | 1990 | PRT | CS&CC |  |  | 85000 | Remodel Restrooms ADA | 2 | [5 empty] | 700000 | 731150
0472 | River Ridge MS | 1990 | CCTE | CS&CC |  |  | 85000 | Remodel Technology Education Space for PLTW Curriculum | 2 |  | 3913 |  |  |  | 160000 | 167120
0472 | River Ridge MS | 1990 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 650000 | 709085
0472 | River Ridge MS | 1990 | ATH | MAINT |  |  | 82050 | Overlay Middle School Track | 4 | [5 empty] | 50000 | 56975
0472 | River Ridge MS | 1990 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 166000 | 206354.6
0501 | Northwest ES | 1973 | PRT | FOSM |  |  | 85110 | HVAC Redesign/Replacement Fan Coil Units | 1 | 13/14 | 3714 | 400000 |  |  | 400000 | 400000
0501 | Northwest ES | 1973 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0501 | Northwest ES | 1973 | FNS | MAINT |  |  | 85250 | Kitchen Floor Renovation | 2 | [5 empty] | 35280 | 36849.96
0501 | Northwest ES | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0501 | Northwest ES | 1973 | FNS | FNS |  |  | 85250 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0501 | Northwest ES | 1973 | PRT | CS&CC |  |  | 86100 | Remodel School - Kelley School | 5 |  | 3913 |  |  |  | 7000000 | 8331400
0501 | Northwest ES | 1973 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0521 | Hudson HS | 1973 | FNS | CS&CC |  |  | 85250 | Kitchen Renovation - Phase 1 | 1 |  |  |  |  | LCIF | 50000 | 50000 |  | On Hold | Pending Kelley School Renovation
0521 | Hudson HS | 1973 | FNS | CS&CC |  |  | 85250 | Kitchen Renovation - Phase 2 | 1 | [5 empty] | 892462.725 | 892462.725 |  | On Hold | Pending Kelley School Renovation
0521 | Hudson HS | 1973 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 150000 | 150000 |  | On Hold
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  | 82020 | Concession Stand Bathrooms - Baseball/Softball | 2 | [5 empty] | 250000 | 261125
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  | 82020 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 2 | [5 empty] | 2500000 | 2611250
0521 | Hudson HS | 1973 | ATH | CS&CC |  |  | 82020 | Renovate/Build Athletic Field House | 2 | [5 empty] | 1000000 | 1044500
0521 | Hudson HS | 1973 | ATH | MAINT |  |  | 85170 | Fencing - Perimeter | 3 | [5 empty] | 20000 | 21818
0521 | Hudson HS | 1973 | PRT | FOSM |  |  | 85110 | HVAC Replace 200 Ton Chiller (Gym) | 4 | [5 empty] | 40000 | 45580
0521 | Hudson HS | 1973 | PRT | CS&CC |  |  | 86100 | Remodel School - Kelley School | 4 |  | 3913 |  |  |  | 19100000 | 21764450
0521 | Hudson HS | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 800000 | 911600
0521 | Hudson HS | 1973 | ATH | ATH |  |  | 82050 | Track Overlay | 4 | [5 empty] | 50000 | 56975
0521 | Hudson HS | 1973 | PRT | CS&CC |  |  | 86110 | Traffic Safety and Parking Improvements | 4 | [5 empty] | 860000 | 979970
0521 | Hudson HS | 1973 | CCTE | CS&CC |  |  | 85230 | Agriculture Barn for Vet Assisting Program | 6 | [5 empty] | 50000 | 62155
0521 | Hudson HS | 1973 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 100000 | 124310
0601 | Shady Hills ES | 1973 | PRT | CS&CC | Yes |  | 86100 | Remodel School - Kelley School + Add Capacity | 1 | 13/14 | 3921 | 10670000 |  | Penny | 11500000 | 11500000
0601 | Shady Hills ES | 1973 | PRT | MAINT |  |  | 85200 | Roof Replacement | 1 | [5 empty] | 300000 | 300000 |  | Not needed. Maintenance will find out when needs to be done. | Roll Funds into Remodel
0601 | Shady Hills ES | 1973 | PRT | CS&CC |  |  | 86100 | Traffic Safety and Parking Improvements | 1 | 13/14 | 3709 3710 | 49972 |  |  | 28577 | 28577 |  | Design
0601 | Shady Hills ES | 1973 | FNS | FNS |  |  | 85250 | Stock Room Renovation | 2 | [5 empty] | 10000 | 10445
0601 | Shady Hills ES | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0601 | Shady Hills ES | 1973 | FNS | FNS |  |  | 85250 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0601 | Shady Hills ES | 1973 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
0701 | Cypress ES | 1973 | PRT | MAINT |  |  | 85200 | Roof Replacement | 1 | 15/16 |  |  |  |  | 300000 | 300000
0701 | Cypress ES | 1973 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0701 | Cypress ES | 1973 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 2 | [5 empty] | 66701 | 69669.1945
0701 | Cypress ES | 1973 | PRT | CS&CC |  |  | 86100 | Remodel School - Kelley School + Add Capacity | 3 | [5 empty] | 8500000 | 9272650
0701 | Cypress ES | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 3 |  | 3913 |  |  |  | 425000 | 463632.5
0701 | Cypress ES | 1973 | FNS | FNS |  |  | 85250 | Kitchen Hood | 4 | [5 empty] | 73538 | 83796.551
0701 | Cypress ES | 1973 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 475000 | 590472.5
0801 | Land O' Lakes HS | 1973 | PRT | CS&CC |  |  | 86100 | Remodel School - Kelley School + Add Capacity | 1 |  | 3913 |  |  | Penny | 20600000 | 20600000
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82050 | Replace Gym Floor | 1 | 13/14 | 3708 | 71605 |  |  | 16093 | 16093 |  | Summer
0801 | Land O' Lakes HS | 1973 | PRT | MAINT |  |  | 85200 | Roof Maintenance - SMS | 1 | 13/14 | 3101 | 100000 |  |  | 100000 | 100000 |  | Design Requisition
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  | 82050 | Baseball and Dugout Reconstruction | 2 | [5 empty] | 100000 | 104450
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC |  |  | 85250 | Cooler / Freezer with Renovations | 2 | [5 empty] | 203963 | 213039.3535
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  | 82050 | Lighting - Replace Baseball Field | 2 | [5 empty] | 100000 | 104450
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 2 | [5 empty] | 981708.9975 | 1025395.0479
0801 | Land O' Lakes HS | 1973 | ATH | MAINT |  |  | 85170 | Fencing - Tennis | 3 | [5 empty] | 15000 | 16363.5
0801 | Land O' Lakes HS | 1973 | PRT | FOSM |  |  | 85110 | HVAC Replace 200 Ton Chiller (Gym) | 4 | [5 empty] | 40000 | 45580
0801 | Land O' Lakes HS | 1973 | PRT | MAINT |  |  | 85200 | Roof Replacement | 4 | [5 empty] | 600000 | 683700
0801 | Land O' Lakes HS | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 800000 | 911600
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82020 | Concession Stand Bathrooms - Baseball/Softball | 5 | [5 empty] | 250000 | 297550
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82020 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 | [5 empty] | 2500000 | 2975500
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC |  |  | 82020 | Renovate/Build Athletic Field House | 5 | [5 empty] | 1500000 | 1785300
0901 | Anclote ES | 1973 | PRT | MAINT |  |  | 85200 | Roof Replacement | 1 | 13/14 | 3101 3611 | 405000 |  |  | 405000 | 405000 |  | Design Requisition
0901 | Anclote ES | 1973 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0901 | Anclote ES | 1973 | PRT | CS&CC |  |  | 86100 | Remodel School - Kelley School + Add Capacity | 2 | 13/14 | 3921 | 11500000 |  |  | 11500000 | 12011750
0901 | Anclote ES | 1973 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0901 | Anclote ES | 1973 | FNS | FNS |  |  | 85250 | Kitchen Hood | 3 | [5 empty] | 66853 | 72929.9377
0901 | Anclote ES | 1973 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 3 | [5 empty] | 315497 | 344175.6773
0901 | Anclote ES | 1973 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 114696 | 142578.5976
0902 | Pine View ES | 2003 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0902 | Pine View ES | 2003 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
0902 | Pine View ES | 2003 | PRT | MAINT |  |  | 85200 | Roof Maintenance | 5 | [5 empty] | 80000 | 95216
0902 | Pine View ES | 2003 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
0902 | Pine View ES | 2003 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0902 | Pine View ES | 2003 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 30000 | 37293
0902 | Pine View ES | 2003 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 6 | [5 empty] | 419926 | 522010.0106
0911 | Gulfside ES | 1977 | PRT | MAINT |  |  | 85200 | Roofing Maintenance | 1 | 13/14 | 3101 | 60000 |  |  | 60000 | 60000 |  | Material Bid @ Purchasing
0911 | Gulfside ES | 1977 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0911 | Gulfside ES | 1977 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
0911 | Gulfside ES | 1977 | PRT | CS&CC |  |  | 86100 | Remodel Bld #1 & 2 Parking And Traffic Improvements | 4 |  | 3913 |  |  |  | 2500000 | 2848750
0911 | Gulfside ES | 1977 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0911 | Gulfside ES | 1977 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways - 224' each side of school | 6 | [5 empty] | 0 | 0 |  | New
0921 | Pine View MS | 1977 | PRT | FOSM | Yes |  | 85110 | HVAC Renovation | 1 | 14/15 |  |  |  |  | 2800000 | 2800000
0921 | Pine View MS | 1977 | PRT | FOSM | Yes |  | 85110 | HVAC Renovation Design | 1 | 13/14 | 3611 | 200000 |  |  | 200000 | 200000
0921 | Pine View MS | 1977 | PRT | MAINT |  |  | 85200 | Roof Replacement | 1 | 14/15 |  |  |  |  | 900000 | 900000 |  | Re-allocate funds to CRES & PVMS HVAC Design | Schedule after HVAC Renovation
0921 | Pine View MS | 1977 | ATH | MAINT |  |  | 82050 | Overlay Outdoor Courts | 2 | [5 empty] | 30000 | 31335
0921 | Pine View MS | 1977 | ATH | ATH |  |  | 82050 | Track Overlay | 2 | [5 empty] | 40000 | 41780
0921 | Pine View MS | 1977 | PRT | CS&CC |  |  | 86100 | Remodel School | 5 | [5 empty] | 15930180 | 18960100.236
0921 | Pine View MS | 1977 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 800000 | 952160
0921 | Pine View MS | 1977 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways - ESE | 6 |  | 3913 |  |  |  | 406000 | 504698.6
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways - Bus Loop | 6 |  | 3913 |  |  |  | 550000 | 683705
0921 | Pine View MS | 1977 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways - Car Loop | 6 | [5 empty] | 418000 | 519615.8
0931 | Ridgewood HS | 1977 | PRT | FOSM |  |  | 85110 | HVAC Renovation | 1 | 14/15 |  |  |  |  | 2200000 | 2200000 |  | Design | Will do in 13/14 if money available
0931 | Ridgewood HS | 1977 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 |  | 3913 |  |  |  | 800000 | 800000 |  |  | IS needs to prioritze
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  | 82050 | Lighting - Replace Baseball Field | 2 | [5 empty] | 100000 | 104450
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  | 82040 | Scoreboard Replacement(s) | 2 | [5 empty] | 25000 | 26112.5
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  | 85000 | Replace Wall Tile In PE Locker Room | 3 | [5 empty] | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  | 82040 | Scoreboard Replacement(s) | 3 | [5 empty] | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | MAINT |  |  | 82050 | Tennis Court Renovation | 3 | [5 empty] | 250000 | 272725
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  | 82000 | Sand & Paint Gym Floors | 4 | [5 empty] | 60000 | 68370
0931 | Ridgewood HS | 1977 | ATH | ATH |  |  | 82050 | Track Overlay | 4 | [5 empty] | 50000 | 56975
0931 | Ridgewood HS | 1977 | PRT | CS&CC |  |  | 86100 | Remodel Bld #1 | 5 |  | 3913 |  |  |  | 9000000 | 10711800
0931 | Ridgewood HS | 1977 | CCTE | CS&CC |  |  | 83000 | Remodel Technology Lab - Room 404 | 5 |  | 3913 |  |  |  | 300000 | 357060
0931 | Ridgewood HS | 1977 | PRT | MAINT |  |  | 85200 | Roof Replacement | 5 | [5 empty] | 400000 | 476080
0931 | Ridgewood HS | 1977 | ATH | CS&CC |  |  | 82020 | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 6 | [5 empty] | 2500000 | 3107750
0932 | Calusa ES | 1979 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | 13/14 | 3714 |  |  |  | 100000 | 100000
0932 | Calusa ES | 1979 | FNS | CS&CC |  |  | 85250 | Cooler / Freezer with Renovations | 2 | [5 empty] | 203963 | 213039.3535
0932 | Calusa ES | 1979 | FNS | FNS |  |  | 85250 | Kitchen Hood | 2 | [5 empty] | 60775 | 63479.4875
0932 | Calusa ES | 1979 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 2 | [5 empty] | 286815 | 299578.2675
0932 | Calusa ES | 1979 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0932 | Calusa ES | 1979 | PRT | CS&CC |  |  | 86110 | Traffic Safety and Parking Improvements | 5 |  | 3913 |  |  |  | 650000 | 773630
0932 | Calusa ES | 1979 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 206000 | 256078.6
0941 | Moon Lake ES | 1982 | PRT | MAINT |  |  | 85200 | Roof Replacement | 1 | 14/15 |  |  |  |  | 500000 | 500000
0941 | Moon Lake ES | 1982 | IS | CS&CC |  |  | 83000 | Technology Infrastructure Upgrades | 1 | [5 empty] | 425000 | 425000 |  |  | IS needs to prioritze
0941 | Moon Lake ES | 1982 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0941 | Moon Lake ES | 1982 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 2 | [5 empty] | 204750 | 213861.375
0941 | Moon Lake ES | 1982 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 2 | [5 empty] | 286815 | 299578.2675
0941 | Moon Lake ES | 1982 | PRT | CS&CC |  |  | 86100 | Remodel Bld #1 | 4 | [5 empty] | 5539200 | 6311918.4
0941 | Moon Lake ES | 1982 | PRT | CS&CC |  |  | 86110 | Traffic Safety and Parking Improvements | 4 |  | 3913 |  |  |  | 758000 | 863741
0951 | Hudson MS | 1984 | FNS | CS&CC |  |  | 85250 | Kitchen & Serving Line Renovation | 1 | 13/14 | 3108 3713 | 995273 |  |  | 222769 | 222769 |  | Summer
0951 | Hudson MS | 1984 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 125000 | 125000 |  | On Hold
0951 | Hudson MS | 1984 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 650000 | 678925
0961 | Lake Myrtle ES | 1984 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
0961 | Lake Myrtle ES | 1984 | FNS | FNS |  |  | 85250 | Serving Line Update - from RES | 4 | [5 empty] | 7383 | 8412.9285
0961 | Lake Myrtle ES | 1984 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
0961 | Lake Myrtle ES | 1984 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 204750 | 243693.45
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  | 85110 | HVAC Redesign/Replacement Fan Coil Units | 1 | [5 empty] | 1000000 | 1000000 |  |  | Added 9/23/13 Part of redevelopment?
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel Automotive Technology | 2 | 13/14 | 3921 |  |  |  | 1500000 | 1566750
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel Carpentry & Vet Assisting Program to HVAC Program | 2 | 13/14 | 3921 |  |  |  | 700000 | 731150
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel Commercial Art Room | 2 | 13/14 | 3921 |  |  |  | 110000 | 114895
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel Cosmetology Room | 2 | 13/14 | 3921 |  |  |  | 1007000 | 1051811.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel Culinary Arts Room | 2 | 13/14 | 3921 |  |  |  | 1200000 | 1253400
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel Electricity Room | 2 | 13/14 | 3921 |  |  |  | 415000 | 433467.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel HVAC Program Room | 2 | 13/14 | 3921 |  |  |  | 530000 | 553585
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel Marine Service Technology Program | 2 | 13/14 | 3921 |  |  |  | 300000 | 313350
0991 | Fred K. Marchman EC | 1984 | PRT | CS&CC |  |  | 86100 | Remodel School | 2 | 13/14 | 3921 |  |  |  | 518529 | 541603.5405
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Remodel TV Production Space | 2 | 13/14 | 3921 |  |  |  | 80000 | 83560
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Renovate Autobody Repair Bld., New Paint Booth, Paint Mixing Room, Frame Straightener, Welding Booth | 2 | 13/14 | 3921 |  |  |  | 500000 | 522250
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC |  |  | 86100 | Sign - New Marquee | 2 | 13/14 | 3921 |  |  |  | 7000 | 7311.5
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  | 85110 | HVAC Replace 200 Ton Chiller | 4 | [5 empty] | 40000 | 45580
0991 | Fred K. Marchman EC | 1984 | MAINT | FOSM |  |  | 85110 | HVAC Replace Control System | 4 | [5 empty] | 400000 | 455800
0991 | Fred K. Marchman EC | 1984 | PRT | MAINT |  |  | 85200 | Roof Replacement | 4 |  | 3913 |  |  |  | 250000 | 284875
2061 | Sand Pine ES | 1998 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
2061 | Sand Pine ES | 1998 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 2 |  | 3913 |  |  |  | 425000 | 443912.5
2061 | Sand Pine ES | 1998 | PRT | FOSM |  |  | 85110 | HVAC Replace (2) 200 Ton Chillers | 4 | [5 empty] | 180000 | 205110
2061 | Sand Pine ES | 1998 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 5 | [5 empty] | 195000 | 232089
2061 | Sand Pine ES | 1998 | FNS | CS&CC |  |  | 85250 | Serving Line Renovation | 5 | [5 empty] | 381751 | 454360.0402
2061 | Sand Pine ES | 1998 | FNS | FNS |  |  | 84070 | Cooler / Freezer | 6 | [5 empty] | 88779 | 110361.1749
2061 | Sand Pine ES | 1998 | SCHOOL | MAINT |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 13000 | 16160.3
2071 | Wesley Chapel ES | 2002 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 4 |  | 3913 |  |  |  | 425000 | 484287.5
2081 | Longleaf ES | 2005 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
2081 | Longleaf ES | 2005 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
2081 | Longleaf ES | 2005 | IS | IS |  |  | 83000 | Technology Infrastructure Upgrades | 5 |  | 3913 |  |  |  | 425000 | 505835
2081 | Longleaf ES | 2005 | FNS | FNS |  |  | 85250 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 530562 | 659541.6222
2091 | Seven Oaks ES | 2005 | PRT | MAINT |  |  | 84045 | TV Installation in Classrooms | 1 | [5 empty] | 100000 | 100000 |  | On Hold
2091 | Seven Oaks ES | 2005 | FNS | CS&CC |  |  | 85110 | A/C Renovation To Kitchen | 4 | [5 empty] | 195000 | 222202.5
2091 | Seven Oaks ES | 2005 | FNS | FNS |  |  | 85250 | Cooler / Freezer & Serving Line | 6 | [5 empty] | 530562 | 659541.6222
6997 | Energy Marine Center |  | MAINT | MAINT |  |  | 85200 | Roof Maintenance | 1 | 13/14 | 3101 | 60000 |  |  | 60000 | 60000 |  | Material Bid @ Purchasing
7071 | James Irvin EC | 1995 | PRT | MAINT |  |  | 86110 | Sign Relocation/Replacement | 1 | 14/15 |  |  | 4/18/14 | [5 empty] | Due to SR 52 DOT work
7071 | James Irvin EC | 1995 | CCTE | CS&CC |  |  | 86100 | Redevelopment of Campus | 5 | [5 empty] | 5000000 | 5951000
7071 | James Irvin EC | 1995 | SCHOOL | CS&CC |  |  | 86190 | Covered Walkways | 6 | [5 empty] | 135600 | 168564.36
9002 | District Wide |  | ATH | MAINT |  |  | 83240 | Annual ADA Compliance/Bleacher Retrofit | 1 | 13/14 | 3611 | 50000 |  |  | 50000 | 50000
9002 | District Wide |  | MAINT | MAINT |  |  | 85000 | Annual Emergency Renovations & Remodeling | 1 | 13/14 | 3714 | 500000 |  |  | 500000 | 500000
9002 | District Wide |  | PRT | MAINT |  |  | 85110 | Annual HVAC Equipment Replacements ($250,000 Annually) | 1 | 13/14 | 3712 | 250000 |  |  | 250000 | 250000
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | Annual Marquee Sign Replacements ($15,000 Annually) | 1 | 13/14 | 3711 | 15000 |  |  | 15000 | 15000
9002 | District Wide |  | MAINT | MAINT |  |  | 81150 | Annual Storage Buildings | 1 | 13/14 | 3712 | 15000 |  |  | 15000 | 15000
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | Property Acquisition - Elementary School Site in North Land O' Lakes area | 1 | 13/14 | 3904 | 750000 |  |  | 750000 | 750000
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | Property Acquisition - Elementary Site in 54 Corridor in Odessa Area | 1 | 13/14 | 3904 | 2200000 |  |  | 2200000 | 2200000 |  |  | Added for 2nd elementary site - Ashley Glen and Smith 54
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | Property Acquisition - Elementary Site in 54 Corridor in Odessa Area | 1 | 13/14 | 3904 | 2200000 |  |  | 2200000 | 2200000 |  | In Progress
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | Property Acquisition - High School Site in 54 Corridor in Odessa Area | 1 | 13/14 | 3904 | 2600000 |  |  | 2600000 | 2600000
9002 | District Wide |  | PLAN | PLAN |  |  | 86000 | Property Acquisition - If land becomes available next to existing school sites | 1 | 13/14 | 3904 | 250000 |  |  | 250000 | 250000
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | Annual Marquee Sign Replacements ($15,000 Annually) | 2 | [5 empty] | 30000 | 31335
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | Annual Marquee Sign Replacements ($15,000 Annually) | 3 | [5 empty] | 30000 | 32727
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | Annual Marquee Sign Replacements ($15,000 Annually) | 4 | [5 empty] | 30000 | 34185
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | Annual Marquee Sign Replacements ($15,000 Annually) | 5 | [5 empty] | 30000 | 35706
9002 | District Wide |  | PRT | MAINT |  |  | 86110 | Annual Marquee Sign Replacements ($15,000 Annually) | 6 | [5 empty] | 30000 | 37293
9009 | District Wide |  | FIN | FIN |  |  | 84500 | ERP System | 1 | 13/14 | 3900 | 8854577 |  |  | 4777563 | 4777563
9012 | District Wide |  | FIN | FIN |  |  | 83240 | Annual FISH Signage | 1 | 13/14 | 3711 | 10000 |  |  | 10000 | 10000
9012 | District Wide |  | PLAN | PLAN |  |  | 89990 | Property Acquisition - Middle/High Site in River Landing (Wesley Chapel) | 3 | [5 empty] | 4000000 | 4363600
9012 | District Wide |  | PLAN | PLAN |  |  | 89990 | Property Acquisition - Elementary site #2 in Wiregrass | 5 | [5 empty] | 750000 | 892650
9012 | District Wide |  | PLAN | PLAN |  |  | 89990 | Property Acquisition - Elementary site #3 in Wiregrass | 6 | [5 empty] | 750000 | 932325
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | Annual Fire Loop / Hydrants ($500,000 Annually) | 1 | 13/14 | 3709 | 250000 |  |  | 500000 | 500000
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | Annual Fire Loop / Hydrants ($500,000 Annually) | 2 | [5 empty] | 1000000 | 1044500
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | Annual Fire Loop / Hydrants ($500,000 Annually) | 3 | [5 empty] | 1000000 | 1090900
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | Annual Fire Loop / Hydrants ($500,000 Annually) | 4 | [5 empty] | 1000000 | 1139500
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | Annual Fire Loop / Hydrants ($500,000 Annually) | 5 | [5 empty] | 1000000 | 1190200
9019 | Transportation SW |  | PRT | CS&CC |  |  | 86100 | Construction of New Facility | 5 | [5 empty] | 5500000 | 6546100
9019 | New Elementary School |  | PLAN | CS&CC | Yes |  | 87045 | Elementary U - Northwood | 5 | [5 empty] | 18597372 | 22134592.1544
9019 | District Wide |  | PRT | CS&CC |  |  | 85180 | Annual Fire Loop / Hydrants ($500,000 Annually) | 6 | [5 empty] | 1000000 | 1243100
9019 | New Elementary School |  | PLAN | CS&CC | Yes |  | 87099 | Elementary Q - 54 Corridor near Suncoast Parkway | 6 | [5 empty] | 20121372 | 25012877.5332
9021 | District Wide |  | FIN | FIN |  |  | 80010 | Annual Habitat for Humanity | 1 | 13/14 | 3904 | 100000 |  |  | 100000 | 100000
9031 | District Wide |  | FIN | FIN |  |  | 84210 | Annual Buses | 1 | 13/14 | 3714 | 1500000 |  |  | 1700000 | 1700000
9031 | District Wide |  | FIN | FIN |  |  | 84210 | Annual Buses & Other Vehicles | 2 | [5 empty] | 4225402 | 4413432.389
9032 | Transportation E | 1972 | PRT | CS&CC |  |  | 85000 | Remodel Interior | 5 | [5 empty] | 250000 | 297550
9032 | District Wide |  | FIN | FIN |  |  | 84220 | Annual Other Vehicles |  | 13/14 | 3715 | 200000
9033 | Transportation W | 1971 | PRT | CS&CC |  |  | 85000 | Remodel Interior, Add Paint Booth, Expand Parking | 5 | [5 empty] | 650000 | 773630
9035 | Transportation NW | 1979 | PRT | CS&CC |  |  | 86110 | Retention Pond and Flooding Repairs | 1 | 13/14 | 3713 | 56662 |  |  | 18891 | 18891 |  |  | Flooding issue as a result of Tropical Storm Debby. Need additional money another $90,000
9035 | Transportation NW | 1979 | PRT | CS&CC |  |  | 86100 | Remodel Office Interior, Add Parking | 5 | [5 empty] | 2500000 | 2975500
9038 | Transportation SE |  | PRT | CS&CC |  |  | 86110 | Retention Pond and Flooding Repairs | 1 | 13/14 | 3713 | 58745 |  |  | 48713 | 48713 |  |  | Retention pond overflowing to neighboring property
9039 | Transportation SW |  | PRT | CS&CC |  |  | 86110 | Pre-Installation of Utilities | 1 | 13/14 | 3611 | 195000 |  |  | 218000 | 218000 |  |  | Install Utilities while Interlaken Road being constructed
9053 | District Complex | 1974 | PRT | CS&CC | Yes |  | 86100 | District Complex - Building 2 Architectural Design | 1 | 13/14 | 3900 | 300000 |  |  | 300000 | 300000
9053 | District Complex |  | PRT | CS&CC | Yes |  | 86100 | District Complex - Building 4 Remodel/Expansion | 1 | 13/14 | 3900 | 6748473 |  |  | 6511000 | 6511000 |  | In Design
9053 | District Complex |  | PRT | FOSM |  |  | 85110 | District Complex - Bulding 4 HVAC Replace Control System | 6 | [5 empty] | 200000 | 248620
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | Annual Bleacher Repair ($100,000 Annually) | 1 | 13/14 | 3710 | 100000 |  |  | 100000 | 100000
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Compliance w/Environmental Reg | 1 | 13/14 | 3709 | 202000 |  |  | 202000 | 202000
9061 | District Wide |  | MAINT | MAINT |  |  | 85500 | Annual Energy Retrofits | 1 | 13/14 | 3611 | 100000 |  |  | 100000 | 100000
9061 | District Wide |  | PRT | MAINT |  |  | 85160 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 1 | 13/14 | 3709 | 725000 |  |  | 725000 | 725000
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 1 | 13/14 | 3709 | 200000 |  |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | Annual Flooring Replacement ($300,000 Annually) | 1 | 13/14 | 3713 | 150000 |  |  | 150000 | 150000
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | Annual Lift Station Upgrades ($100,000 Annually) | 1 | 13/14 | 3709 | 100000 |  |  | 100000 | 100000
9061 | District Wide |  | FIN | FIN |  |  | 85100 | Annual Maintenance & Repairs Projects (Small) | 1 | 13/14 | 3709 | 1212000 |  |  | 1212000 | 1212000
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Maintenance Health & Safety | 1 | 13/14 | 3709 | 202000 |  |  | 202000 | 202000
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 1 | 13/14 | 3712 | 350000 |  |  | 350000 | 350000
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 1 | 13/14 | 3714 | 200000 |  |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | Annual Portable Maintenance & Moving ($100,000 Annually) | 1 | 13/14 | 3709 | 295000 |  |  | 200000 | 200000
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | Annual Security Cameras & Alarms ($100,000 Annually) | 1 | 13/14 | 3708 | 100000 |  |  | 100000 | 100000
9061 | Maintenance Dept Building |  | PRT | MAINT |  |  | 85200 | Roofing Maintenance | 1 | 13/14 | 3713 | 25000 |  |  | 25000 | 25000 |  | Not Started
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | Annual Bleacher Repair ($100,000 Annually) | 2 | [5 empty] | 200000 | 208900
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Compliance w/Environmental Reg | 2 | [5 empty] | 420322 | 439026.329
9061 | District Wide |  | FIN | FIN |  |  | 83260 | Annual Compliance with ADA | 2 | [5 empty] | 300000 | 313350 |  |  | Added at the request of CS&CC
9061 | District Wide |  | PRT | MAINT |  |  | 86160 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 2 | [5 empty] | 1700000 | 1775650
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 2 | [5 empty] | 400000 | 417800
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | Annual Flooring Replacement | 2 | [5 empty] | 600000 | 626700
9061 | District Wide |  | PRT | MAINT |  |  | 85110 | Annual HVAC Equipment Replacements ($250,000 Annually) | 2 | [5 empty] | 500000 | 522250
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | Annual Lift Station Upgrades ($100,000 Annually) | 2 | [5 empty] | 200000 | 208900
9061 | District Wide |  | FIN | FIN |  |  | 85100 | Annual Maintenance & Repairs Projects (Small) | 2 | [5 empty] | 2521930 | 2634155.885
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Maintenance Health & Safety | 2 | [5 empty] | 420322 | 439026.329
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 2 | [5 empty] | 1000000 | 1044500
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 2 |  | 3913 |  |  |  | 400000 | 417800
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | Annual Portable Maintenance & Moving ($100,000 Annually) | 2 | [5 empty] | 200000 | 208900
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | Annual Security Cameras & Alarms | 2 | [5 empty] | 200000 | 208900
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | Annual Bleacher Repair ($100,000 Annually) | 3 | [5 empty] | 200000 | 218180
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Compliance w/Environmental Reg | 3 | [5 empty] | 437303 | 477053.8427
9061 | District Wide |  | FIN | FIN |  |  | 83260 | Annual Compliance with ADA | 3 | [5 empty] | 300000 | 327270 |  |  | Added at the request of CS&CC
9061 | District Wide |  | PRT | MAINT |  |  | 86160 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 3 | [5 empty] | 1700000 | 1854530
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 3 | [5 empty] | 400000 | 436360
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | Annual Flooring Replacement | 3 | [5 empty] | 600000 | 654540
9061 | District Wide |  | PRT | MAINT |  |  | 85110 | Annual HVAC Equipment Replacements ($250,000 Annually) | 3 | [5 empty] | 500000 | 545450
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | Annual Lift Station Upgrades ($100,000 Annually) | 3 | [5 empty] | 200000 | 218180
9061 | District Wide |  | FIN | FIN |  |  | 85100 | Annual Maintenance & Repairs Projects (Small) | 3 | [5 empty] | 2623816 | 2862320.8744
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Maintenance Health & Safety | 3 | [5 empty] | 437303 | 477053.8427
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 3 | [5 empty] | 1000000 | 1090900
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 3 |  | 3913 |  |  |  | 400000 | 436360
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | Annual Portable Maintenance & Moving ($100,000 Annually) | 3 | [5 empty] | 200000 | 218180
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | Annual Security Cameras & Alarms | 3 | [5 empty] | 200000 | 218180
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | Annual Bleacher Repair ($100,000 Annually) | 4 | [5 empty] | 200000 | 227900
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Compliance w/Environmental Reg | 4 | [5 empty] | 454970 | 518438.315
9061 | District Wide |  | FIN | FIN |  |  | 83260 | Annual Compliance with ADA | 4 | [5 empty] | 300000 | 341850 |  |  | Added at the request of CS&CC
9061 | District Wide |  | PRT | MAINT |  |  | 86160 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 4 | [5 empty] | 1700000 | 1937150
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 4 | [5 empty] | 400000 | 455800
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | Annual Flooring Replacement | 4 | [5 empty] | 600000 | 683700
9061 | District Wide |  | PRT | MAINT |  |  | 85110 | Annual HVAC Equipment Replacements ($250,000 Annually) | 4 | [5 empty] | 500000 | 569750
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | Annual Lift Station Upgrades ($100,000 Annually) | 4 | [5 empty] | 200000 | 227900
9061 | District Wide |  | FIN | FIN |  |  | 85100 | Annual Maintenance & Repairs Projects (Small) | 4 | [5 empty] | 2729818 | 3110627.611
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Maintenance Health & Safety | 4 | [5 empty] | 454970 | 518438.315
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 4 | [5 empty] | 1000000 | 1139500
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 4 |  | 3913 |  |  |  | 400000 | 455800
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | Annual Portable Maintenance & Moving ($100,000 Annually) | 4 | [5 empty] | 200000 | 227900
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | Annual Security Cameras & Alarms | 4 | [5 empty] | 200000 | 227900
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | Annual Bleacher Repair ($100,000 Annually) | 5 | [5 empty] | 200000 | 238040
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Compliance w/Environmental Reg | 5 | [5 empty] | 473350 | 563381.17
9061 | District Wide |  | FIN | FIN |  |  | 83260 | Annual Compliance with ADA | 5 | [5 empty] | 300000 | 357060 |  |  | Added at the request of CS&CC
9061 | District Wide |  | PRT | MAINT |  |  | 86160 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 5 | [5 empty] | 1700000 | 2023340
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 5 | [5 empty] | 400000 | 476080
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | Annual Flooring Replacement | 5 | [5 empty] | 600000 | 714120
9061 | District Wide |  | PRT | MAINT |  |  | 85110 | Annual HVAC Equipment Replacements ($250,000 Annually) | 5 | [5 empty] | 500000 | 595100
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | Annual Lift Station Upgrades ($100,000 Annually) | 5 | [5 empty] | 200000 | 238040
9061 | District Wide |  | FIN | FIN |  |  | 85100 | Annual Maintenance & Repairs Projects (Small) | 5 | [5 empty] | 2840102 | 3380289.4004
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Maintenance Health & Safety | 5 | [5 empty] | 473350 | 563381.17
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 5 | [5 empty] | 1000000 | 1190200
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 5 |  | 3913 |  |  |  | 400000 | 476080
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | Annual Portable Maintenance & Moving ($100,000 Annually) | 5 | [5 empty] | 200000 | 238040
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | Annual Security Cameras & Alarms | 5 | [5 empty] | 200000 | 238040
9061 | District Wide |  | ATH | MAINT |  |  | 82010 | Annual Bleacher Repair ($100,000 Annually) | 6 | [5 empty] | 200000 | 248620
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Compliance w/Environmental Reg | 6 | [5 empty] | 514487 | 639558.7897
9061 | District Wide |  | FIN | FIN |  |  | 83260 | Annual Compliance with ADA | 6 | [5 empty] | 300000 | 372930 |  |  | Added at the request of CS&CC
9061 | District Wide |  | PRT | MAINT |  |  | 86160 | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 6 | [5 empty] | 1700000 | 2113270
9061 | District Wide |  | PRT | MAINT |  |  | 85180 | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 6 | [5 empty] | 400000 | 497240
9061 | District Wide |  | PRT | MAINT |  |  | 85120 | Annual Flooring Replacement | 6 | [5 empty] | 600000 | 745860
9061 | District Wide |  | PRT | MAINT |  |  | 85110 | Annual HVAC Equipment Replacements ($250,000 Annually) | 6 | [5 empty] | 500000 | 621550
9061 | District Wide |  | PRT | MAINT |  |  | 86180 | Annual Lift Station Upgrades ($100,000 Annually) | 6 | [5 empty] | 200000 | 248620
9061 | District Wide |  | FIN | FIN |  |  | 85100 | Annual Maintenance & Repairs Projects (Small) | 6 | [5 empty] | 3086924 | 3837355.2244
9061 | District Wide |  | FIN | FIN |  |  | 83240 | Annual Maintenance Health & Safety | 6 | [5 empty] | 514487 | 639558.7897
9061 | District Wide |  | PRT | MAINT |  |  | 86140 | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 6 | [5 empty] | 1000000 | 1243100
9061 | District Wide |  | PRT | MAINT |  |  | 85210 | Annual Physical Education Equipment Replacements ($200,000 Annually) | 6 |  | 3913 |  |  |  | 400000 | 497240
9061 | District Wide |  | PRT | MAINT |  |  | 81000 | Annual Portable Maintenance & Moving ($100,000 Annually) | 6 | [5 empty] | 200000 | 248620
9061 | District Wide |  | PRT | MAINT |  |  | 85220 | Annual Security Cameras & Alarms | 6 | [5 empty] | 200000 | 248620
9099 | New Elementary School |  | PLAN | CS&CC | Yes |  | 87055 | Elementary W - Wiregrass | 1 | 13/14 | 3903 3921 | 17691000 |  | Penny & Other | 18801000 | 18801000
9099 | New High School |  | PLAN | CS&CC | Yes |  | 89020 | High School GGG - Old Pasco Road | 1 | 13/14 | 3904 | 28956000 |  | Impact Fees | 62700000 | 62700000
9420 | District Wide |  | FIN | FIN |  |  | 84060 | Annual Technology and Equipment (Incl Student Computers) | 1 | [5 empty] | 7785000 | 7785000
9420 | District Wide | [5 empty] | 84080 | Annual Technology and Equipment (Incl Student Computers) | 2 | 14/15
9420 | District Wide |  | FIN | FIN |  |  | 84060 84080 | Annual Technology and Equipment (Incl Student Computers) | 2 | [5 empty] | 17065403 | 17824813.4335
9420 | District Wide |  | FIN | FIN |  |  | 84060 84080 | Annual Technology and Equipment (Incl Student Computers) | 3 | [5 empty] | 18104686 | 19750401.9574
9420 | District Wide |  | FIN | FIN |  |  | 84060 84080 | Annual Technology and Equipment (Incl Student Computers) | 4 | [5 empty] | 18923410 | 21563225.695
9420 | District Wide |  | FIN | FIN |  |  | 84060 84080 | Annual Technology and Equipment (Incl Student Computers) | 5 | [5 empty] | 19491113 | 23198322.6926
9420 | District Wide |  | FIN | FIN |  |  | 84060 84080 | Annual Technology and Equipment (Incl Student Computers) | 6 | [5 empty] | 20075846 | 24956284.1626
9420 | District Wide | [5 empty] | 84080 | Administrative Computers |  | 13/14 | 3714 | 1430000
9420 | District Wide | [5 empty] | 84060 | Student Teacher Computers |  | 13/14 | 3900 | 4000000
9421 | District Wide |  | FIN | FIN |  |  | 83000 | Annual Telecommunications Repairs Projects (Small) | 1 | 13/14 | 3713 | 800000 |  |  | 800000 | 800000
9421 | District Wide |  | FIN | FIN |  |  | 83000 | Annual Telecommunications Repairs Projects (Small) | 2 | [5 empty] | 1730736 | 1807753.752
9421 | District Wide |  | FIN | FIN |  |  | 83000 | Annual Telecommunications Repairs Projects (Small) | 3 | [5 empty] | 1800658 | 1964337.8122
9421 | District Wide |  | FIN | FIN |  |  | 83000 | Annual Telecommunications Repairs Projects (Small) | 4 | [5 empty] | 1873404 | 2134743.858
9421 | District Wide |  | FIN | FIN |  |  | 83000 | Annual Telecommunications Repairs Projects (Small) | 5 | [5 empty] | 1949090 | 2319806.918
9421 | District Wide |  | FIN | FIN |  |  | 83000 | Annual Telecommunications Repairs Projects (Small) | 6 | [5 empty] | 2118477 | 2633478.7587
9426 | District Wide |  | FIN | FIN |  |  | 84510 | Quest Student Information System | 1 | 13/14 | 3921 | 11277535 |  |  | 11277535 | 11277535
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 1 | 13/14 | 3709 | 150000 |  |  | 150000 | 150000
9430 | District Wide |  | ATH | MAINT |  |  | 82000 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 1 | 13/14 | 3708 | 60000 |  |  | 60000 | 60000
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | Annual Sound System Repairs ($75,000 Annually) | 1 | 13/14 | 3713 | 75000 |  |  | 75000 | 75000
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 2 | [5 empty] | 300000 | 313350
9430 | District Wide |  | ATH | ATH |  |  | 82000 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 2 | [5 empty] | 120000 | 125340
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | Annual Sound System Repairs ($75,000 Annually) | 2 | [5 empty] | 150000 | 156675
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 3 | [5 empty] | 300000 | 327270
9430 | District Wide |  | ATH | ATH |  |  | 82000 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 3 | [5 empty] | 120000 | 130908
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | Annual Sound System Repairs ($75,000 Annually) | 3 | [5 empty] | 150000 | 163635
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 4 | [5 empty] | 300000 | 341850
9430 | District Wide |  | ATH | ATH |  |  | 82000 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 4 | [5 empty] | 120000 | 136740
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | Annual Sound System Repairs ($75,000 Annually) | 4 | [5 empty] | 150000 | 170925
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 5 | [5 empty] | 300000 | 357060
9430 | District Wide |  | ATH | ATH |  |  | 82000 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 5 | [5 empty] | 120000 | 142824
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | Annual Sound System Repairs ($75,000 Annually) | 5 | [5 empty] | 150000 | 178530
9430 | District Wide |  | ATH | MAINT |  |  | 82050 | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 6 | [5 empty] | 300000 | 372930
9430 | District Wide |  | ATH | ATH |  |  | 82000 | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 6 | [5 empty] | 120000 | 149172
9430 | District Wide |  | ATH | MAINT |  |  | 82040 | Annual Sound System Repairs ($75,000 Annually) | 6 | [5 empty] | 150000 | 186465
9999 | District Wide |  | FIN | FIN |  |  | 84210 | Annual Buses & Other Vehicles | 3 | [5 empty] | 4667428 | 5091697.2052
9999 | District Wide |  | FIN | FIN |  |  | 84210 | Annual Buses & Other Vehicles | 4 | [5 empty] | 4855992 | 5533402.884
9999 | District Wide |  | FIN | FIN |  |  | 84210 | Annual Buses & Other Vehicles | 5 | [5 empty] | 5052174 | 6013097.4948
9999 | District Wide |  | FIN | FIN |  |  | 84210 | Annual Buses & Other Vehicles | 6 | [5 empty] | 5491238 | 6826157.9578
Priority Code | Year | Escalator | [5 empty] | Totals | All | [5 empty] | 1090748084.7225 | 1167570787.5553
1 | 12/13 - 13/14 | 0% | [5 empty] | Total for Priority 1 | 1 | [5 empty] | 276903206.725 | 276903206.725
2 | 14/15 - 15/16 | 4.45% | [5 empty] | Total for Priority 2 | 2 | [5 empty] | 174847302.2475 | 179827249.332
3 | 16/17 - 17/18 | 9.09% | [5 empty] | Total for Priority 3 | 3 | [5 empty] | 158331382 | 168147745.1746
4 | 18/19 - 19/20 | 13.95% | [5 empty] | Total for Priority 4 | 4 | [5 empty] | 144911533 | 157515337.4935
5 | 20/21 - 21/22 | 19.02% | [5 empty] | Total for Priority 5 | 5 | [5 empty] | 192508477.75 | 219490521.1179
6 | 22/23 - 23/24 | 24.31% | [5 empty] | Total for Priority 6 | 6 | [5 empty] | 143246183 | 165686727.7123
|  | = | 2013-2014 Budget Year Projects
|  | = | Penny for Pasco Projects

## Test 1
Priority | 1
Bgt Yr | (Multiple Items)
FUND | (All)
Sum of Adjusted Estimate | Column Labels
Row Labels | 0031 | 0032 | 0057 | 0060 | 0061 | 0063 | 0065 | 0069 | 0071 | 0072 | 0073 | 0081 | 0083 | 0090 | 0091 | 0102 | 0211 | 0251 | 0341 | 0342 | 0351 | 0361 | 0401 | 0411 | 0421 | 0451 | 0471 | 0472 | 0501 | 0521 | 0601 | 0701 | 0801 | 0901 | 0902 | 0911 | 0921 | 0931 | 0941 | 0951 | 0961 | 0991 | 2061 | 2081 | 2091 | 7071 | 9420 | Grand Total
82020
82040 | [5 empty] | 75000 | [41 empty] | 75000
82050 | [5 empty] | 150000 | [41 empty] | 150000
83000 |  |  | 650000 |  | 425000 | [9 empty] | 425000 |  | 425000 | 425000 |  |  | 425000 |  | 425000 |  | 425000 | [12 empty] | 800000 | 425000 | [8 empty] | 4850000
83260 | [16 empty] | 20000 | [30 empty] | 20000
84045 |  | 100000 |  | 100000 |  |  | 100000 | 125000 | 10000 | 100000 | 150000 |  | 100000 | 51000 |  | 125000 |  | 100000 | 40000 | 125000 | 100000 | 100000 | 100000 | 100000 | 100000 |  | 150000 | 125000 | 100000 | 150000 |  | 100000 |  | 100000 | 100000 | 100000 |  |  | 100000 | 125000 | 100000 |  | 100000 | 100000 | 100000 |  |  | 3276000
84060 | [46 empty] | 7785000 | 7785000
84070 | [7 empty] | 70000 | [39 empty] | 70000
85000 | [11 empty] | 708000 | [14 empty] | 50000 | [20 empty] | 758000
85110 | [5 empty] | 350000 | [30 empty] | 2800000 | 2200000 |  |  |  | 1000000 | [5 empty] | 6350000
85140 | [5 empty] | 0 | [41 empty] | 0
85170 | [25 empty] | 25000 | [21 empty] | 25000
85200 | [19 empty] | 1000000 | [10 empty] | 300000 | 300000 |  |  |  |  | 900000 |  | 500000 | [8 empty] | 3000000
85250 | [21 empty] | 57881 | [7 empty] | 942462.725 | [17 empty] | 1000343.725
86100 | [32 empty] | 20600000 | [14 empty] | 20600000
86110
Grand Total |  | 100000 | 650000 | 100000 | 425000 | 575000 | 100000 | 195000 | 10000 | 100000 | 150000 | 708000 | 100000 | 51000 | 425000 | 125000 | 445000 | 525000 | 40000 | 1125000 | 525000 | 157881 | 525000 | 100000 | 525000 | 25000 | 200000 | 125000 | 100000 | 1092462.725 | 300000 | 400000 | 20600000 | 100000 | 100000 | 100000 | 3700000 | 3000000 | 1025000 | 125000 | 100000 | 1000000 | 100000 | 100000 | 100000 |  | 7785000 | 47959343.725

## Sheet2
Assigned Dept | (All)
Type | (All)
Priority | (All)
Sum of Budget Estimate |  |  | Cost Center
MUNIS | Bgt Yr | FUND | 0000 | 0021 | 0031 | 0032 | 0057 | 0059 | 0061 | 0063 | 0069 | 0073 | 0074 | 0081 | 0085 | 0090 | 0091 | 0093 | 0101 | 0102 | 0131 | 0132 | 0201 | 0242 | 0261 | 0271 | 0311 | 0321 | 0331 | 0341 | 0342 | 0351 | 0361 | 0451 | 0461 | 0471 | 0501 | 0601 | 0801 | 0901 | 0911 | 0921 | 0932 | 0951 | 0991 | 6997 | 9002 | 9009 | 9012 | 9019 | 9021 | 9031 | 9032 | 9035 | 9038 | 9039 | 9053 | 9061 | 9099 | 9420 | 9421 | 9426 | 9430 | Grand Total
00000 | 13/14 | 3714 | 827000 | [60 empty] | 827000
|  | 3714 3903 3921 | 38816856 | [60 empty] | 38816856
| 13/14 Total |  | 39643856 | [60 empty] | 39643856
00000 Total |  |  | 39643856 | [60 empty] | 39643856
80010 | 13/14 | 3904 | [48 empty] | 100000 | [12 empty] | 100000
| 13/14 Total | [49 empty] | 100000 | [12 empty] | 100000
80010 Total | [50 empty] | 100000 | [12 empty] | 100000
81000 | 13/14 | 3709 | [55 empty] | 200000 | [5 empty] | 200000
| 13/14 Total | [56 empty] | 200000 | [5 empty] | 200000
81000 Total | [57 empty] | 200000 | [5 empty] | 200000
81150 | 13/14 | 3712 | [44 empty] | 15000 | [16 empty] | 15000
| 13/14 Total | [45 empty] | 15000 | [16 empty] | 15000
81150 Total | [46 empty] | 15000 | [16 empty] | 15000
82000 | 13/14 | 3708 | [60 empty] | 60000 | 60000
| 13/14 Total | [61 empty] | 60000 | 60000
82000 Total | [62 empty] | 60000 | 60000
82010 | 13/14 | 3710 | [55 empty] | 100000 | [5 empty] | 100000
| 13/14 Total | [56 empty] | 100000 | [5 empty] | 100000
82010 Total | [57 empty] | 100000 | [5 empty] | 100000
82020 | 13/14 | 3708 3710 3711 3713 | [16 empty] | 6108 | [44 empty] | 6108
|  | 3708 3710 3711 | [13 empty] | 6162 | [47 empty] | 6162
|  | 3709 33710 3711 | [7 empty] | 6053 | [53 empty] | 6053
|  | 3710 | [33 empty] | 100000 | [27 empty] | 100000
|  | 3712 3903 | [18 empty] | 468257 | [42 empty] | 468257
| 13/14 Total | [8 empty] | 6053 | [5 empty] | 6162 |  |  | 6108 |  | 468257 | [14 empty] | 100000 | [27 empty] | 586580
82020 Total | [9 empty] | 6053 | [5 empty] | 6162 |  |  | 6108 |  | 468257 | [14 empty] | 100000 | [27 empty] | 586580
82040 | 13/14 | 3709 3713 | [26 empty] | 40000 | [34 empty] | 40000
|  | 3710 3711 |  |  |  |  | 75000 | [56 empty] | 75000
|  | 3713 | [60 empty] | 75000 | 75000
| 13/14 Total | [5 empty] | 75000 | [21 empty] | 40000 | [33 empty] | 75000 | 190000
82040 Total | [6 empty] | 75000 | [21 empty] | 40000 | [33 empty] | 75000 | 190000
82050 | 13/14 | 3708 | [36 empty] | 16093 | [24 empty] | 16093
|  | 3709 | [60 empty] | 150000 | 150000
|  | 3711 |  |  |  |  | 6366 |  |  |  |  | 35000 | [51 empty] | 41366
| 13/14 Total | [5 empty] | 6366 |  |  |  |  | 35000 | [26 empty] | 16093 | [23 empty] | 150000 | 207459
82050 Total | [6 empty] | 6366 |  |  |  |  | 35000 | [26 empty] | 16093 | [23 empty] | 150000 | 207459
83000 | 13/14 | 3713 | [58 empty] | 800000 |  |  | 800000
| 13/14 Total | [59 empty] | 800000 |  |  | 800000
83000 Total | [60 empty] | 800000 |  |  | 800000
83240 | 13/14 | 3611 | [44 empty] | 50000 | [16 empty] | 50000
|  | 3709 | [55 empty] | 404000 | [5 empty] | 404000
|  | 3711 | [46 empty] | 10000 | [14 empty] | 10000
| 13/14 Total | [45 empty] | 50000 |  | 10000 | [8 empty] | 404000 | [5 empty] | 464000
83240 Total | [46 empty] | 50000 |  | 10000 | [8 empty] | 404000 | [5 empty] | 464000
83260 | 13/14 | 3611 | [19 empty] | 21000 | [41 empty] | 21000
| 13/14 Total | [20 empty] | 21000 | [41 empty] | 21000
83260 Total | [21 empty] | 21000 | [41 empty] | 21000
84045 | 13/14 | 3714 | [5 empty] | 100000 | [13 empty] | 100000 |  |  | 125000 |  | 100000 |  | 150000 |  |  |  |  | 100000 | 125000 | [7 empty] | 100000 | [20 empty] | 900000
| 13/14 Total | [6 empty] | 100000 | [13 empty] | 100000 |  |  | 125000 |  | 100000 |  | 150000 |  |  |  |  | 100000 | 125000 | [7 empty] | 100000 | [20 empty] | 900000
84045 Total | [7 empty] | 100000 | [13 empty] | 100000 |  |  | 125000 |  | 100000 |  | 150000 |  |  |  |  | 100000 | 125000 | [7 empty] | 100000 | [20 empty] | 900000
84048 | 13/14 | 3714 |  |  |  |  | 125000 | [56 empty] | 125000
| 13/14 Total | [5 empty] | 125000 | [56 empty] | 125000
84048 Total | [6 empty] | 125000 | [56 empty] | 125000
84060 | 13/14 | 3900
13/14 Total
84060 Total
84070 | 13/14 | 3709 |  |  |  |  | 184638 |  | 80709 |  |  |  | 88779 | [15 empty] | 9879 | [34 empty] | 364005
| 13/14 Total | [5 empty] | 184638 |  | 80709 |  |  |  | 88779 | [15 empty] | 9879 | [34 empty] | 364005
84070 Total | [6 empty] | 184638 |  | 80709 |  |  |  | 88779 | [15 empty] | 9879 | [34 empty] | 364005
84080 | 13/14 | 3714
13/14 Total
84080 Total
84210 | 13/14 | 3714 | [49 empty] | 1700000 | [11 empty] | 1700000
| 13/14 Total | [50 empty] | 1700000 | [11 empty] | 1700000
84210 Total | [51 empty] | 1700000 | [11 empty] | 1700000
84220 | 13/14 | 3715
13/14 Total
84220 Total
84500 | 13/14 | 3900 | [45 empty] | 4777563 | [15 empty] | 4777563
| 13/14 Total | [46 empty] | 4777563 | [15 empty] | 4777563
84500 Total | [47 empty] | 4777563 | [15 empty] | 4777563
84510 | 13/14 | 3921 | [59 empty] | 11277535 |  | 11277535
| 13/14 Total | [60 empty] | 11277535 |  | 11277535
84510 Total | [61 empty] | 11277535 |  | 11277535
85000 | 13/14 | 3714 | [44 empty] | 500000 | [16 empty] | 500000
| 13/14 Total | [45 empty] | 500000 | [16 empty] | 500000
85000 Total | [46 empty] | 500000 | [16 empty] | 500000
85100 | 13/14 | 3709 | [55 empty] | 1212000 | [5 empty] | 1212000
| 13/14 Total | [56 empty] | 1212000 | [5 empty] | 1212000
85100 Total | [57 empty] | 1212000 | [5 empty] | 1212000
85110 | 13/14 | 3611 |  |  |  |  | 68774 | [34 empty] | 200000 | [21 empty] | 268774
|  | 3709 3711 | [12 empty] | 1006 | [13 empty] | 330203 | [34 empty] | 331209
|  | 3712 | [44 empty] | 250000 | [16 empty] | 250000
|  | 3714 | [34 empty] | 400000 | [26 empty] | 400000
|  | 3900 | [18 empty] | 89671 | [14 empty] | 493880 | [27 empty] | 583551
| 13/14 Total | [5 empty] | 68774 | [7 empty] | 1006 | [5 empty] | 89671 | [7 empty] | 330203 | [6 empty] | 493880 | 400000 |  |  |  |  | 200000 |  |  |  |  | 250000 | [16 empty] | 1833534
85110 Total | [6 empty] | 68774 | [7 empty] | 1006 | [5 empty] | 89671 | [7 empty] | 330203 | [6 empty] | 493880 | 400000 |  |  |  |  | 200000 |  |  |  |  | 250000 | [16 empty] | 1833534
85120 | 13/14 | 3713 | [55 empty] | 150000 | [5 empty] | 150000
| 13/14 Total | [56 empty] | 150000 | [5 empty] | 150000
85120 Total | [57 empty] | 150000 | [5 empty] | 150000
85160 | 13/14 | 3709 | [55 empty] | 725000 | [5 empty] | 725000
| 13/14 Total | [56 empty] | 725000 | [5 empty] | 725000
85160 Total | [57 empty] | 725000 | [5 empty] | 725000
85180 | 13/14 | 3709 | [47 empty] | 500000 | [7 empty] | 200000 | [5 empty] | 700000
| 13/14 Total | [48 empty] | 500000 | [7 empty] | 200000 | [5 empty] | 700000
85180 Total | [49 empty] | 500000 | [7 empty] | 200000 | [5 empty] | 700000
85190 | 13/14 | 3712 | [8 empty] | 60000 | [52 empty] | 60000
| 13/14 Total | [9 empty] | 60000 | [52 empty] | 60000
85190 Total | [10 empty] | 60000 | [52 empty] | 60000
85200 | 13/14 | 3101 | [8 empty] | 91250 |  |  | 60000 |  |  | 301220 | [6 empty] | 40000 | [14 empty] | 100000 |  | 60000 |  |  |  |  | 60000 | [17 empty] | 712470
|  | 3101 3611 | [37 empty] | 405000 | [23 empty] | 405000
|  | 3103 |  |  |  | 50000 | [57 empty] | 50000
|  | 3713 | [55 empty] | 25000 | [5 empty] | 25000
| 13/14 Total |  |  |  |  | 50000 |  |  |  |  | 91250 |  |  | 60000 |  |  | 301220 | [6 empty] | 40000 | [14 empty] | 100000 | 405000 | 60000 |  |  |  |  | 60000 | [11 empty] | 25000 | [5 empty] | 1192470
85200 Total | [5 empty] | 50000 |  |  |  |  | 91250 |  |  | 60000 |  |  | 301220 | [6 empty] | 40000 | [14 empty] | 100000 | 405000 | 60000 |  |  |  |  | 60000 | [11 empty] | 25000 | [5 empty] | 1192470
85210 | 13/14 | 3714 | [55 empty] | 200000 | [5 empty] | 200000
| 13/14 Total | [56 empty] | 200000 | [5 empty] | 200000
85210 Total | [57 empty] | 200000 | [5 empty] | 200000
85220 | 13/14 | 3708 | [55 empty] | 100000 | [5 empty] | 100000
| 13/14 Total | [56 empty] | 100000 | [5 empty] | 100000
85220 Total | [57 empty] | 100000 | [5 empty] | 100000
85240 | 13/14 | 3712 | [7 empty] | 16416 | [53 empty] | 16416
| 13/14 Total | [8 empty] | 16416 | [53 empty] | 16416
85240 Total | [9 empty] | 16416 | [53 empty] | 16416
85250 | 13/14 | 3108 3713 | [41 empty] | 222769 | [19 empty] | 222769
|  | 3611 | [24 empty] | 700000 | [36 empty] | 700000
|  | 3611 3709 | [9 empty] | 1343003 | [51 empty] | 1343003
|  | 3611 3713 | [33 empty] | 1086115 | [27 empty] | 1086115
|  | 3709 3711 |  |  |  | 57881 | [57 empty] | 57881
|  | 3713 | [29 empty] | 194596 | [31 empty] | 194596
| 13/14 Total |  |  |  |  | 57881 | [5 empty] | 1343003 | [14 empty] | 700000 |  |  |  |  | 194596 |  |  |  | 1086115 | [7 empty] | 222769 | [19 empty] | 3604364
85250 Total | [5 empty] | 57881 | [5 empty] | 1343003 | [14 empty] | 700000 |  |  |  |  | 194596 |  |  |  | 1086115 | [7 empty] | 222769 | [19 empty] | 3604364
85500 | 13/14 | 3611 | [55 empty] | 100000 | [5 empty] | 100000
| 13/14 Total | [56 empty] | 100000 | [5 empty] | 100000
85500 Total | [57 empty] | 100000 | [5 empty] | 100000
86000 | 13/14 | 3904 | [44 empty] | 8000000 | [16 empty] | 8000000
| 13/14 Total | [45 empty] | 8000000 | [16 empty] | 8000000
86000 Total | [46 empty] | 8000000 | [16 empty] | 8000000
86100 | 13/14 | 3709 | [25 empty] | 10000 | [35 empty] | 10000
|  | 3709 3710 | [35 empty] | 28577 | [25 empty] | 28577
|  | 3900 | [27 empty] | 13936000 | [26 empty] | 6811000 | [6 empty] | 20747000
|  | 3900 3904 | [20 empty] | 16902130 |  |  | 760236 | [37 empty] | 17662366
|  | 3903 | [17 empty] | 4646472 | [43 empty] | 4646472
|  | 3921 |  | 6510441 |  |  |  |  | 5614560 | [21 empty] | 15150000 |  | 11500000 |  |  |  |  | 11500000 |  | 11500000 |  |  |  |  | 6867529 | [18 empty] | 68642530
| 13/14 Total |  |  | 6510441 |  |  |  |  | 5614560 | [10 empty] | 4646472 |  |  | 16902130 |  |  | 760236 |  | 10000 |  | 13936000 | 15150000 |  | 11500000 |  |  |  |  | 11528577 |  | 11500000 |  |  |  |  | 6867529 | [11 empty] | 6811000 | [6 empty] | 111736945
86100 Total |  |  |  | 6510441 |  |  |  |  | 5614560 | [10 empty] | 4646472 |  |  | 16902130 |  |  | 760236 |  | 10000 |  | 13936000 | 15150000 |  | 11500000 |  |  |  |  | 11528577 |  | 11500000 |  |  |  |  | 6867529 | [11 empty] | 6811000 | [6 empty] | 111736945
86100 85000 | 13/14 | 3903 |  |  | 385148 | [58 empty] | 385148
| 13/14 Total |  |  |  | 385148 | [58 empty] | 385148
86100 85000 Total |  |  |  |  | 385148 | [58 empty] | 385148
86110 | 13/14 | 3611 | [13 empty] | 125000 | [39 empty] | 218000 | [7 empty] | 343000
|  | 3611 3713 | [31 empty] | 355826 | [29 empty] | 355826
|  | 3710 3711 3712 3713 3902 | [15 empty] | 90576 | [45 empty] | 90576
|  | 3711 | [44 empty] | 15000 | [16 empty] | 15000
|  | 3713 | [51 empty] | 18891 | 48713 | [8 empty] | 67604
| 13/14 Total | [14 empty] | 125000 |  | 90576 | [15 empty] | 355826 | [12 empty] | 15000 | [6 empty] | 18891 | 48713 | 218000 | [7 empty] | 872006
86110 Total | [15 empty] | 125000 |  | 90576 | [15 empty] | 355826 | [12 empty] | 15000 | [6 empty] | 18891 | 48713 | 218000 | [7 empty] | 872006
86140 | 13/14 | 3712 | [55 empty] | 350000 | [5 empty] | 350000
| 13/14 Total | [56 empty] | 350000 | [5 empty] | 350000
86140 Total | [57 empty] | 350000 | [5 empty] | 350000
86180 | 13/14 | 3709 | [55 empty] | 100000 | [5 empty] | 100000
| 13/14 Total | [56 empty] | 100000 | [5 empty] | 100000
86180 Total | [57 empty] | 100000 | [5 empty] | 100000
87055 | 13/14 | 3903 3921 | [56 empty] | 18801000 |  |  |  |  | 18801000
| 13/14 Total | [57 empty] | 18801000 |  |  |  |  | 18801000
87055 Total | [58 empty] | 18801000 |  |  |  |  | 18801000
89020 | 13/14 | 3904 | [56 empty] | 62700000 |  |  |  |  | 62700000
| 13/14 Total | [57 empty] | 62700000 |  |  |  |  | 62700000
89020 Total | [58 empty] | 62700000 |  |  |  |  | 62700000
Grand Total |  |  | 39643856 | 6510441 | 385148 | 107881 | 459778 | 100000 | 5695269 | 22469 | 151250 | 1378003 | 88779 | 60000 | 1006 | 131162 | 301220 | 90576 | 6108 | 4646472 | 557928 | 121000 | 16902130 | 40000 | 125000 | 760236 | 800000 | 10000 | 530082 | 13936000 | 15150000 | 194596 | 11500000 | 455826 | 125000 | 1679995 | 400000 | 11528577 | 116093 | 11905000 | 60000 | 200000 | 100000 | 222769 | 6867529 | 60000 | 8830000 | 4777563 | 10000 | 500000 | 100000 | 1700000 |  | 18891 | 48713 | 218000 | 6811000 | 3866000 | 81501000 |  | 800000 | 11277535 | 285000 | 274870881

## PivotNamePriority
Sum of Budget Estimate | Column Labels
Row Labels | 00000 | 80010 | 81000 | 81150 | 82000 | 82010 | 82020 | 82040 | 82050 | 83000 | 83240 | 83260 | 84045 | 84048 | 84060 | 84070 | 84080 | 84210 | 84220 | 84500 | 84510 | 85000 | 85100 | 85110 | 85120 | 85140 | 85160 | 85170 | 85180 | 85190 | 85200 | 85210 | 85220 | 85230 | 85240 | 85250 | 85500 | 86000 | 86100 | 86110 | 86140 | 86150 | 86160 | 86180 | 86190 | 86200 | 87045 | 87055 | 87099 | 89020 | 89990 | Grand Total
Anclote ES | [9 empty] | 425000 |  |  | 100000 | [17 empty] | 405000 |  |  |  |  | 382350 |  |  | 11500000 | [5 empty] | 114696 | [6 empty] | 12927046
1 | [12 empty] | 100000 | [17 empty] | 405000 | [20 empty] | 505000
2 | [9 empty] | 425000 | [28 empty] | 11500000 | [12 empty] | 11925000
3 | [35 empty] | 382350 | [15 empty] | 382350
6 | [44 empty] | 114696 | [6 empty] | 114696
Anclote HS |  |  |  |  | 25000 | [30 empty] | 1187868 | [15 empty] | 1212868
5 |  |  |  |  | 25000 | [46 empty] | 25000
6 | [35 empty] | 1187868 | [15 empty] | 1187868
Bayonet Point MS | [9 empty] | 650000 |  |  | 125000 | [8 empty] | 100000 | [8 empty] | 1000000 |  |  |  |  | 324292 |  |  | 15150000 | [5 empty] | 25000 | [6 empty] | 17374292
1 | [12 empty] | 125000 | [17 empty] | 1000000 | [20 empty] | 1125000
2 | [21 empty] | 100000 | [13 empty] | 203963 |  |  | 15150000 | [12 empty] | 15453963
3 | [35 empty] | 120329 | [15 empty] | 120329
5 | [9 empty] | 650000 | [41 empty] | 650000
6 | [44 empty] | 25000 | [6 empty] | 25000
Calusa ES | [9 empty] | 425000 |  |  | 100000 | [22 empty] | 551553 |  |  |  | 650000 |  |  |  |  | 206000 | [6 empty] | 1932553
1 | [12 empty] | 100000 | [38 empty] | 100000
2 | [35 empty] | 551553 | [15 empty] | 551553
4 | [9 empty] | 425000 | [41 empty] | 425000
5 | [39 empty] | 650000 | [11 empty] | 650000
6 | [44 empty] | 206000 | [6 empty] | 206000
Centennial ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 244750 | [27 empty] | 769750
1 | [9 empty] | 425000 |  |  | 100000 | [38 empty] | 525000
4 | [23 empty] | 40000 | [27 empty] | 40000
5 | [23 empty] | 204750 | [27 empty] | 204750
Centennial MS | [9 empty] | 650000 |  |  | 125000 |  |  | 158779 | [7 empty] | 600000 | [5 empty] | 60000 | 80000 |  |  |  |  | 981709 | [8 empty] | 130000 | 10000 | [5 empty] | 2795488
1 | [12 empty] | 125000 |  |  | 70000 | [13 empty] | 60000 | [21 empty] | 255000
4 | [9 empty] | 650000 | [20 empty] | 80000 |  |  |  |  | 981709 | [9 empty] | 10000 | [5 empty] | 1721709
6 | [15 empty] | 88779 | [7 empty] | 600000 | [20 empty] | 130000 | [6 empty] | 818779
Charles S. Rushe MS |  |  |  |  | 25000 |  |  |  | 50000 | [26 empty] | 1187868 | [15 empty] | 1262868
5 |  |  |  |  | 25000 |  |  |  | 50000 | [42 empty] | 75000
6 | [35 empty] | 1187868 | [15 empty] | 1187868
Chasco ES | [9 empty] | 425000 | [11 empty] | 300000 |  | 795000 | [6 empty] | 40000 |  |  |  |  | 943483 | [8 empty] | 100000 | [6 empty] | 2603483
4 | [9 empty] | 425000 | [20 empty] | 40000 | [20 empty] | 465000
5 | [23 empty] | 795000 | [11 empty] | 943483 | [15 empty] | 1738483
6 | [21 empty] | 300000 | [22 empty] | 100000 | [6 empty] | 400000
Chasco MS |  |  |  |  | 25000 |  |  |  |  | 650000 | [5 empty] | 66701.25 | [14 empty] | 171250 |  |  |  |  | 811329.75 | [9 empty] | 8000 | [5 empty] | 1732281
1 | [30 empty] | 91250 | [20 empty] | 91250
2 | [15 empty] | 66701.25 | [35 empty] | 66701.25
4 |  |  |  |  | 25000 |  |  |  |  | 650000 | [20 empty] | 80000 | [20 empty] | 755000
5 | [35 empty] | 811329.75 | [9 empty] | 8000 | [5 empty] | 819329.75
Chester Taylor ES | [9 empty] | 425000 |  |  | 100000 |  |  | 80709 | [7 empty] | 595000 | [6 empty] | 80000 |  |  |  |  | 315497 | [15 empty] | 1596206
1 | [12 empty] | 100000 | [38 empty] | 100000
2 | [30 empty] | 80000 | [20 empty] | 80000
3 | [9 empty] | 425000 | [13 empty] | 195000 | [11 empty] | 315497 | [15 empty] | 935497
5 | [15 empty] | 80709 | [35 empty] | 80709
6 | [23 empty] | 400000 | [27 empty] | 400000
Cotee River ES | [9 empty] | 425000 |  |  | 100000 |  |  | 73371 | [7 empty] | 80000 | [11 empty] | 700000 | [5 empty] | 1000000 |  |  | 162000 | [6 empty] | 2540371
1 | [12 empty] | 100000 | [22 empty] | 700000 | [15 empty] | 800000
2 | [9 empty] | 425000 | [41 empty] | 425000
3 | [41 empty] | 1000000 | [9 empty] | 1000000
4 | [15 empty] | 73371 | [7 empty] | 80000 | [27 empty] | 153371
6 | [44 empty] | 162000 | [6 empty] | 162000
Crews Lake MS |  |  |  |  | 25000 |  |  |  | 50000 | [26 empty] | 2314818 | [15 empty] | 2389818
5 |  |  |  |  | 25000 |  |  |  | 50000 | [42 empty] | 75000
6 | [35 empty] | 2314818 | [15 empty] | 2314818
Cypress ES | [9 empty] | 425000 |  |  | 100000 |  |  | 66701 | [14 empty] | 300000 |  |  |  |  | 73538 |  |  | 8500000 | [5 empty] | 475000 | [6 empty] | 9940239
1 | [12 empty] | 100000 | [17 empty] | 300000 | [20 empty] | 400000
2 | [15 empty] | 66701 | [35 empty] | 66701
3 | [9 empty] | 425000 | [28 empty] | 8500000 | [12 empty] | 8925000
4 | [35 empty] | 73538 | [15 empty] | 73538
6 | [44 empty] | 475000 | [6 empty] | 475000
Deer Park ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 244750 | [11 empty] | 347047 | [15 empty] | 1116797
1 | [9 empty] | 425000 |  |  | 100000 | [38 empty] | 525000
4 | [23 empty] | 40000 | [11 empty] | 347047 | [15 empty] | 387047
5 | [23 empty] | 204750 | [27 empty] | 204750
Denham Oaks ES | [9 empty] | 425000 |  |  | 100000 |  |  | 80709 | [7 empty] | 40000 | [6 empty] | 50000 |  |  |  |  | 315497 | [8 empty] | 135000 | [6 empty] | 1146206
1 | [12 empty] | 100000 | [38 empty] | 100000
3 | [9 empty] | 425000 | [20 empty] | 50000 |  |  |  |  | 315497 | [15 empty] | 790497
4 | [23 empty] | 40000 | [27 empty] | 40000
5 | [15 empty] | 80709 | [35 empty] | 80709
6 | [44 empty] | 135000 | [6 empty] | 135000
District Complex | [23 empty] | 200000 | [14 empty] | 6811000 | [12 empty] | 7011000
1 | [38 empty] | 6811000 | [12 empty] | 6811000
6 | [23 empty] | 200000 | [27 empty] | 200000
District Wide | 309067804 | 100000 | 1200000 | 15000 | 660000 | 1100000 |  | 825000 | 1650000 | 10272365 | 5064864 | 1500000 |  |  | 54616228 |  | 46831230 | 25992234 |  | 4777563 | 11277535 | 500000 | 15014590 | 2750000 | 3150000 |  | 725000 |  | 7700000 |  |  | 2200000 | 1100000 |  |  |  | 100000 | 8000000 |  | 165000 | 5350000 |  | 8500000 | 1100000 | [6 empty] | 5500000 | 536804413
1 | 39643856 | 100000 | 200000 | 15000 | 60000 | 100000 |  | 75000 | 150000 | 800000 | 464000 |  |  |  | 7785000 |  |  | 1700000 |  | 4777563 | 11277535 | 500000 | 1212000 | 250000 | 150000 |  | 725000 |  | 700000 |  |  | 200000 | 100000 |  |  |  | 100000 | 8000000 |  | 15000 | 350000 |  |  | 100000 | [7 empty] | 79549954
2 | 62938379 |  | 200000 |  | 120000 | 200000 |  | 150000 | 300000 | 1730736 | 840644 | 300000 |  |  | 8532701 |  | 8532702 | 4225402 |  |  |  |  | 2521930 | 500000 | 600000 |  |  |  | 1400000 |  |  | 400000 | 200000 | [6 empty] | 30000 | 1000000 |  | 1700000 | 200000 | [7 empty] | 96622494
3 | 50340588 |  | 200000 |  | 120000 | 200000 |  | 150000 | 300000 | 1800658 | 874606 | 300000 |  |  | 9053343 |  | 9053343 | 4667428 |  |  |  |  | 2623816 | 500000 | 600000 |  |  |  | 1400000 |  |  | 400000 | 200000 | [6 empty] | 30000 | 1000000 |  | 1700000 | 200000 | [6 empty] | 4000000 | 89713782
4 | 54561680 |  | 200000 |  | 120000 | 200000 |  | 150000 | 300000 | 1873404 | 909940 | 300000 |  |  | 9461705 |  | 9461705 | 4855992 |  |  |  |  | 2729818 | 500000 | 600000 |  |  |  | 1400000 |  |  | 400000 | 200000 | [6 empty] | 30000 | 1000000 |  | 1700000 | 200000 | [7 empty] | 91154244
5 | 50647051 |  | 200000 |  | 120000 | 200000 |  | 150000 | 300000 | 1949090 | 946700 | 300000 |  |  | 9745556 |  | 9745557 | 5052174 |  |  |  |  | 2840102 | 500000 | 600000 |  |  |  | 1400000 |  |  | 400000 | 200000 | [6 empty] | 30000 | 1000000 |  | 1700000 | 200000 | [6 empty] | 750000 | 88976230
6 | 50936250 |  | 200000 |  | 120000 | 200000 |  | 150000 | 300000 | 2118477 | 1028974 | 300000 |  |  | 10037923 |  | 10037923 | 5491238 |  |  |  |  | 3086924 | 500000 | 600000 |  |  |  | 1400000 |  |  | 400000 | 200000 | [6 empty] | 30000 | 1000000 |  | 1700000 | 200000 | [6 empty] | 750000 | 90787709
(blank)
Double Branch ES | [23 empty] | 195000 | [11 empty] | 583619 | [5 empty] | 500000 | [9 empty] | 1278619
2 | [41 empty] | 500000 | [9 empty] | 500000
4 | [23 empty] | 195000 | [27 empty] | 195000
6 | [35 empty] | 583619 | [15 empty] | 583619
Dr. John Long MS |  |  |  |  | 25000 | [30 empty] | 1187868 |  |  | 4000000 | [12 empty] | 5212868
3 |  |  |  |  | 25000 | [33 empty] | 4000000 | [12 empty] | 4025000
6 | [35 empty] | 1187868 | [15 empty] | 1187868
Energy Marine Center | [30 empty] | 60000 | [20 empty] | 60000
1 | [30 empty] | 60000 | [20 empty] | 60000
Fivay HS | [35 empty] | 1187868 | [15 empty] | 1187868
6 | [35 empty] | 1187868 | [15 empty] | 1187868
Fox Hollow ES | [9 empty] | 425000 |  |  | 100000 |  |  | 88779 | [7 empty] | 195000 | [11 empty] | 194596 | [15 empty] | 1003375
1 | [9 empty] | 425000 |  |  | 100000 | [22 empty] | 194596 | [15 empty] | 719596
4 | [23 empty] | 195000 | [27 empty] | 195000
6 | [15 empty] | 88779 | [35 empty] | 88779
Fred K. Marchman EC | [23 empty] | 1440000 | [6 empty] | 250000 | [7 empty] | 6867529 | [12 empty] | 8557529
1 | [23 empty] | 1000000 | [27 empty] | 1000000
2 | [38 empty] | 6867529 | [12 empty] | 6867529
4 | [23 empty] | 440000 | [6 empty] | 250000 | [20 empty] | 690000
Gulf Highlands ES | [12 empty] | 100000 | [10 empty] | 195000 | [11 empty] | 583619 | [15 empty] | 878619
1 | [12 empty] | 100000 | [38 empty] | 100000
4 | [23 empty] | 195000 | [27 empty] | 195000
6 | [35 empty] | 583619 | [15 empty] | 583619
Gulf HS | [6 empty] | 2500000 | 40000 |  | 800000 |  |  | 150000 |  |  | 9879 | [5 empty] | 15000 |  | 450203 | 355000 |  |  | 35000 | [10 empty] | 11664150 | [12 empty] | 16019232
1 | [12 empty] | 150000 |  |  | 9879 | [7 empty] | 330203 | [27 empty] | 490082
2 | [7 empty] | 40000 | [43 empty] | 40000
3 | [27 empty] | 35000 | [23 empty] | 35000
4 | [21 empty] | 15000 |  | 120000 | [14 empty] | 11664150 | [12 empty] | 11799150
5 | [6 empty] | 2500000 |  |  | 800000 | [41 empty] | 3300000
6 | [24 empty] | 355000 | [26 empty] | 355000
Gulf MS |  |  |  |  | 25000 |  |  |  |  | 650000 |  |  | 125000 | [8 empty] | 100000 | [13 empty] | 1308197 |  |  | 8653000 | [12 empty] | 10861197
1 | [12 empty] | 125000 | [38 empty] | 125000
2 | [21 empty] | 100000 | [29 empty] | 100000
3 | [35 empty] | 120329 |  |  | 8653000 | [12 empty] | 8773329
4 |  |  |  |  | 25000 | [46 empty] | 25000
5 | [9 empty] | 650000 | [41 empty] | 650000
6 | [35 empty] | 1187868 | [15 empty] | 1187868
Gulf Trace ES | [35 empty] | 641980 |  |  |  | 90576 | [11 empty] | 732556
1 | [39 empty] | 90576 | [11 empty] | 90576
6 | [35 empty] | 641980 | [15 empty] | 641980
Gulfside ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 204750 | [6 empty] | 60000 | [7 empty] | 2500000 | [5 empty] | 0 | [6 empty] | 3289750
1 | [12 empty] | 100000 | [17 empty] | 60000 | [20 empty] | 160000
2 | [9 empty] | 425000 | [41 empty] | 425000
4 | [38 empty] | 2500000 | [12 empty] | 2500000
5 | [23 empty] | 204750 | [27 empty] | 204750
6 | [44 empty] | 0 | [6 empty] | 0
Harry Schwettman EC | [21 empty] | 266999 | [8 empty] | 40000 |  |  |  |  | 1187868 | [15 empty] | 1494867
1 | [30 empty] | 40000 | [20 empty] | 40000
5 | [21 empty] | 266999 | [29 empty] | 266999
6 | [35 empty] | 1187868 | [15 empty] | 1187868
Hudson ES | [9 empty] | 425000 | [5 empty] | 73371 | [5 empty] | 1100000 | [13 empty] | 815018 | [15 empty] | 2413389
2 | [9 empty] | 425000 | [11 empty] | 700000 | [13 empty] | 35280 | [15 empty] | 1160280
3 | [21 empty] | 400000 | [13 empty] | 779738 | [15 empty] | 1179738
4 | [15 empty] | 73371 | [35 empty] | 73371
Hudson HS | [6 empty] | 3750000 |  | 50000 | 800000 |  |  | 150000 | [10 empty] | 40000 |  |  |  | 20000 | [5 empty] | 50000 |  | 942462.725 |  |  | 19100000 | 860000 |  |  |  |  | 100000 | [6 empty] | 25862462.725
1 | [12 empty] | 150000 | [22 empty] | 942462.725 | [15 empty] | 1092462.725
2 | [6 empty] | 3750000 | [44 empty] | 3750000
3 | [27 empty] | 20000 | [23 empty] | 20000
4 | [8 empty] | 50000 | 800000 | [13 empty] | 40000 | [14 empty] | 19100000 | 860000 | [11 empty] | 20850000
6 | [33 empty] | 50000 | [10 empty] | 100000 | [6 empty] | 150000
Hudson MS | [9 empty] | 650000 |  |  | 125000 | [22 empty] | 222769 | [15 empty] | 997769
1 | [12 empty] | 125000 | [22 empty] | 222769 | [15 empty] | 347769
2 | [9 empty] | 650000 | [41 empty] | 650000
J.W. Mitchell HS |  |  |  | 25000 |  |  |  |  | 355000 | 800000 |  |  | 150000 | [22 empty] | 1343003 | [8 empty] | 150000 | [6 empty] | 2823003
1 | [8 empty] | 35000 |  |  |  | 150000 | [22 empty] | 1343003 | [15 empty] | 1528003
3 | [8 empty] | 320000 | [42 empty] | 320000
4 |  |  |  | 25000 | [47 empty] | 25000
5 | [9 empty] | 800000 | [41 empty] | 800000
6 | [44 empty] | 150000 | [6 empty] | 150000
James Irvin EC | [38 empty] | 5000000 | [5 empty] | 135600 | [6 empty] | 5135600
1
5 | [38 empty] | 5000000 | [12 empty] | 5000000
6 | [44 empty] | 135600 | [6 empty] | 135600
James M. Marlowe ES | [9 empty] | 425000 |  |  | 100000 |  |  | 80709 | [7 empty] | 195000 | [6 empty] | 80000 |  |  |  |  | 381751 | [15 empty] | 1262460
1 | [12 empty] | 100000 | [38 empty] | 100000
3 | [9 empty] | 425000 | [20 empty] | 80000 | [20 empty] | 505000
5 | [15 empty] | 80709 | [7 empty] | 195000 | [11 empty] | 381751 | [15 empty] | 657460
Lacoochee ES | [9 empty] | 425000 | [25 empty] | 769627 |  |  | 1358655 | [12 empty] | 2553282
1 | [38 empty] | 10000 | [12 empty] | 10000
2 | [9 empty] | 425000 | [25 empty] | 769627 | [15 empty] | 1194627
4 | [38 empty] | 1348655 | [12 empty] | 1348655
Lake Myrtle ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 204750 | [11 empty] | 7383 | [15 empty] | 737133
1 | [12 empty] | 100000 | [38 empty] | 100000
4 | [9 empty] | 425000 | [25 empty] | 7383 | [15 empty] | 432383
5 | [23 empty] | 204750 | [27 empty] | 204750
Land O' Lakes HS | [6 empty] | 4250000 |  | 216093 | 800000 | [13 empty] | 40000 |  |  |  | 15000 |  |  | 700000 |  |  |  |  | 1185671.9975 |  |  | 20600000 | [12 empty] | 27806764.9975
1 | [8 empty] | 16093 | [21 empty] | 100000 | [7 empty] | 20600000 | [12 empty] | 20716093
2 | [8 empty] | 200000 | [26 empty] | 1185671.9975 | [15 empty] | 1385671.9975
3 | [27 empty] | 15000 | [23 empty] | 15000
4 | [9 empty] | 800000 | [13 empty] | 40000 | [6 empty] | 600000 | [20 empty] | 1440000
5 | [6 empty] | 4250000 | [44 empty] | 4250000
Longleaf ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 195000 | [11 empty] | 530562 | [15 empty] | 1250562
1 | [12 empty] | 100000 | [38 empty] | 100000
4 | [23 empty] | 195000 | [27 empty] | 195000
5 | [9 empty] | 425000 | [41 empty] | 425000
6 | [35 empty] | 530562 | [15 empty] | 530562
Maintenance Dept Building | [30 empty] | 25000 | [20 empty] | 25000
1 | [30 empty] | 25000 | [20 empty] | 25000
Mary Giella ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 2704750 |  |  |  | 25000 | [11 empty] | 355826 |  |  |  |  | 110000 | [6 empty] | 3720576
1 | [12 empty] | 100000 | [14 empty] | 25000 | [11 empty] | 355826 | [11 empty] | 480826
2 | [23 empty] | 2500000 | [27 empty] | 2500000
5 | [9 empty] | 425000 | [13 empty] | 204750 | [27 empty] | 629750
6 | [44 empty] | 110000 | [6 empty] | 110000
Mittye P. Locke ES | [9 empty] | 425000 |  | 20000 | [23 empty] | 708852 |  |  | 8000000 | [12 empty] | 9153852
1 | [9 empty] | 425000 |  | 20000 | [39 empty] | 445000
2 | [35 empty] | 708852 | [15 empty] | 708852
3 | [38 empty] | 8000000 | [12 empty] | 8000000
Moon Lake ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 204750 | [6 empty] | 500000 |  |  |  |  | 286815 |  |  | 5539200 | 758000 | [11 empty] | 7813765
1 | [9 empty] | 425000 |  |  | 100000 | [17 empty] | 500000 | [20 empty] | 1025000
2 | [23 empty] | 204750 | [11 empty] | 286815 | [15 empty] | 491565
4 | [38 empty] | 5539200 | 758000 | [11 empty] | 6297200
Moore Mickens EC | [15 empty] | 73371 | [5 empty] | 1153419 | [8 empty] | 60000 | [7 empty] | 5000000 | [12 empty] | 6286790
1 | [21 empty] | 708000 | [8 empty] | 60000 | [20 empty] | 768000
2 | [21 empty] | 445419 | [29 empty] | 445419
4 | [15 empty] | 73371 | [35 empty] | 73371
5 | [38 empty] | 5000000 | [12 empty] | 5000000
New Elementary School | [46 empty] | 18597372 | 18801000 | 20121372 |  |  | 57519744
1 | [47 empty] | 18801000 |  |  |  | 18801000
5 | [46 empty] | 18597372 |  |  |  |  | 18597372
6 | [48 empty] | 20121372 |  |  | 20121372
New High School | [49 empty] | 62700000 |  | 62700000
1 | [49 empty] | 62700000 |  | 62700000
New River ES | [23 empty] | 195000 | [11 empty] | 641980 | [15 empty] | 836980
4 | [23 empty] | 195000 | [27 empty] | 195000
6 | [35 empty] | 641980 | [15 empty] | 641980
Northwest ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 400000 | [11 empty] | 528744 |  |  | 7000000 | [12 empty] | 8453744
1 | [12 empty] | 100000 | [10 empty] | 400000 | [27 empty] | 500000
2 | [35 empty] | 35280 | [15 empty] | 35280
3 | [9 empty] | 425000 | [41 empty] | 425000
4 | [35 empty] | 73538 | [15 empty] | 73538
5 | [38 empty] | 7000000 | [12 empty] | 7000000
6 | [35 empty] | 419926 | [15 empty] | 419926
Oakstead ES | [15 empty] | 88779 | [7 empty] | 195000 | [11 empty] | 419926 | [15 empty] | 703705
4 | [23 empty] | 195000 | [27 empty] | 195000
6 | [15 empty] | 88779 | [19 empty] | 419926 | [15 empty] | 508705
Pasco ES | [9 empty] | 425000 | [5 empty] | 80709 | [22 empty] | 5614560 | [12 empty] | 6120269
1 | [9 empty] | 425000 | [41 empty] | 425000
2 | [38 empty] | 5614560 | [12 empty] | 5614560
5 | [15 empty] | 80709 | [35 empty] | 80709
Pasco HS | [8 empty] | 2600000 | [6 empty] | 80709 | [7 empty] | 250000 | [11 empty] | 1079880 |  |  | 385148 | [12 empty] | 4395737
1 | [38 empty] | 385148 | [12 empty] | 385148
2 | [8 empty] | 2600000 | [42 empty] | 2600000
5 | [15 empty] | 80709 | [7 empty] | 250000 | [11 empty] | 1079880 | [15 empty] | 1410589
(blank)
Pasco MS | [8 empty] | 175000 |  |  |  | 10000 | [38 empty] | 185000
1 | [12 empty] | 10000 | [38 empty] | 10000
5 | [8 empty] | 175000 | [42 empty] | 175000
Paul R. Smith MS |  |  |  |  | 25000 | [30 empty] | 1187868 | [9 empty] | 10000 | [5 empty] | 1222868
3 |  |  |  |  | 25000 | [46 empty] | 25000
6 | [35 empty] | 1187868 | [9 empty] | 10000 | [5 empty] | 1197868
Pine View ES | [9 empty] | 425000 |  |  | 100000 |  |  | 88779 | [7 empty] | 195000 | [6 empty] | 80000 |  |  |  |  | 419926 | [8 empty] | 30000 | [6 empty] | 1338705
1 | [12 empty] | 100000 | [38 empty] | 100000
4 | [23 empty] | 195000 | [27 empty] | 195000
5 | [9 empty] | 425000 | [20 empty] | 80000 | [20 empty] | 505000
6 | [15 empty] | 88779 | [19 empty] | 419926 | [8 empty] | 30000 | [6 empty] | 538705
Pine View MS | [8 empty] | 70000 | 800000 | [5 empty] | 88779 | [7 empty] | 3000000 | [6 empty] | 900000 | [7 empty] | 15930180 | [5 empty] | 1374000 | [6 empty] | 22162959
1 | [23 empty] | 3000000 | [6 empty] | 900000 | [20 empty] | 3900000
2 | [8 empty] | 70000 | [42 empty] | 70000
5 | [9 empty] | 800000 | [28 empty] | 15930180 | [12 empty] | 16730180
6 | [15 empty] | 88779 | [28 empty] | 1374000 | [6 empty] | 1462779
Quail Hollow ES | [9 empty] | 425000 |  |  | 100000 |  |  | 88779 | [7 empty] | 204750 | [6 empty] | 600000 |  |  |  |  | 1095712 |  |  | 11500000 |  |  | 210000 |  |  | 55000 | [6 empty] | 14279241
1 | [12 empty] | 100000 | [22 empty] | 57881 |  |  | 11500000 | [12 empty] | 11657881
3 | [9 empty] | 425000 | [41 empty] | 425000
5 | [30 empty] | 600000 | [20 empty] | 600000
6 | [15 empty] | 88779 | [7 empty] | 204750 | [11 empty] | 1037831 | [5 empty] | 210000 |  |  | 55000 | [6 empty] | 1596360
R. B. Cox ES | [9 empty] | 425000 | [28 empty] | 6510441 | [12 empty] | 6935441
2 | [38 empty] | 6510441 | [12 empty] | 6510441
3 | [9 empty] | 425000 | [41 empty] | 425000
R.B. Stewart MS | [12 empty] | 125000 |  |  | 88779 | [22 empty] | 4646472 | [12 empty] | 4860251
1 | [12 empty] | 125000 | [25 empty] | 4646472 | [12 empty] | 4771472
6 | [15 empty] | 88779 | [35 empty] | 88779
Richey ES | [38 empty] | 760236 | [12 empty] | 760236
1 | [38 empty] | 760236 | [12 empty] | 760236
Ridgewood HS |  |  |  |  | 60000 |  | 2500000 | 50000 | 400000 | 1100000 | [11 empty] | 25000 |  | 2200000 | [6 empty] | 400000 | [7 empty] | 9000000 | [12 empty] | 15735000
1 | [9 empty] | 800000 | [13 empty] | 2200000 | [27 empty] | 3000000
2 | [7 empty] | 25000 | 100000 | [42 empty] | 125000
3 | [7 empty] | 25000 | 250000 | [12 empty] | 25000 | [29 empty] | 300000
4 |  |  |  |  | 60000 |  |  |  | 50000 | [42 empty] | 110000
5 | [9 empty] | 300000 | [20 empty] | 400000 | [7 empty] | 9000000 | [12 empty] | 9700000
6 | [6 empty] | 2500000 | [44 empty] | 2500000
River Ridge HS | [6 empty] | 100000 |  |  | 800000 |  |  | 150000 | [8 empty] | 750000 |  | 993880 |  |  |  | 30000 | [7 empty] | 1086115 | [8 empty] | 300000 | [6 empty] | 4209995
1 | [6 empty] | 100000 | [5 empty] | 150000 | [8 empty] | 50000 |  | 493880 | [11 empty] | 1086115 | [15 empty] | 1879995
2 | [21 empty] | 700000 | [29 empty] | 700000
3 | [9 empty] | 800000 | [17 empty] | 30000 | [23 empty] | 830000
6 | [23 empty] | 500000 | [20 empty] | 300000 | [6 empty] | 800000
River Ridge MS | [8 empty] | 50000 | 650000 |  |  | 125000 | [8 empty] | 860000 | [22 empty] | 166000 | [6 empty] | 1851000
1 | [12 empty] | 125000 | [38 empty] | 125000
2 | [21 empty] | 860000 | [29 empty] | 860000
3 | [9 empty] | 650000 | [41 empty] | 650000
4 | [8 empty] | 50000 | [42 empty] | 50000
6 | [44 empty] | 166000 | [6 empty] | 166000
San Antonio ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 1300000 | [14 empty] | 3965541 | [12 empty] | 5790541
1 | [9 empty] | 425000 |  |  | 100000 | [38 empty] | 525000
2 | [23 empty] | 1300000 | [27 empty] | 1300000
5 | [38 empty] | 3965541 | [12 empty] | 3965541
Sand Pine ES | [9 empty] | 425000 |  |  | 100000 |  |  | 88779 | [7 empty] | 375000 | [11 empty] | 381751 | [8 empty] | 13000 | [6 empty] | 1383530
1 | [12 empty] | 100000 | [38 empty] | 100000
2 | [9 empty] | 425000 | [41 empty] | 425000
4 | [23 empty] | 180000 | [27 empty] | 180000
5 | [23 empty] | 195000 | [11 empty] | 381751 | [15 empty] | 576751
6 | [15 empty] | 88779 | [28 empty] | 13000 | [6 empty] | 101779
Sanders Memorial ES | [38 empty] | 16902130 | [12 empty] | 16902130
1 | [38 empty] | 16902130 | [12 empty] | 16902130
Schrader ES | [9 empty] | 425000 |  |  | 40000 | [25 empty] | 13936000 | [12 empty] | 14401000
1 | [12 empty] | 40000 | [25 empty] | 13936000 | [12 empty] | 13976000
3 | [9 empty] | 425000 | [41 empty] | 425000
Seven Oaks ES | [12 empty] | 100000 | [10 empty] | 195000 | [11 empty] | 530562 | [15 empty] | 825562
1 | [12 empty] | 100000 | [38 empty] | 100000
4 | [23 empty] | 195000 | [27 empty] | 195000
6 | [35 empty] | 530562 | [15 empty] | 530562
Seven Springs ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 244750 | [11 empty] | 687047 | [8 empty] | 28980 | [6 empty] | 1485777
1 | [12 empty] | 100000 | [38 empty] | 100000
2 | [23 empty] | 40000 | [27 empty] | 40000
4 | [9 empty] | 425000 | [25 empty] | 347047 | [15 empty] | 772047
5 | [23 empty] | 204750 | [27 empty] | 204750
6 | [35 empty] | 340000 | [8 empty] | 28980 | [6 empty] | 368980
Seven Springs MS | [7 empty] | 75000 | 6366 | 650000 |  |  |  | 125000 |  | 184638 | [7 empty] | 68774 | [21 empty] | 80000 | [5 empty] | 1189778
1 | [8 empty] | 6366 | 650000 |  |  |  | 125000 |  | 184638 | [7 empty] | 68774 | [27 empty] | 1034778
2 | [7 empty] | 75000 | [43 empty] | 75000
6 | [45 empty] | 80000 | [5 empty] | 80000
Shady Hills ES | [9 empty] | 425000 | [20 empty] | 300000 |  |  |  |  | 465289 |  |  | 11528577 | [12 empty] | 12718866
1 | [30 empty] | 300000 | [7 empty] | 11528577 | [12 empty] | 11828577
2 | [9 empty] | 425000 | [25 empty] | 10000 | [15 empty] | 435000
4 | [35 empty] | 73538 | [15 empty] | 73538
5 | [35 empty] | 381751 | [15 empty] | 381751
Sunlake HS |  |  |  |  | 25000 |  | 6108 | [28 empty] | 1187868 | [15 empty] | 1218976
1 | [6 empty] | 6108 | [44 empty] | 6108
5 |  |  |  |  | 25000 | [46 empty] | 25000
6 | [35 empty] | 1187868 | [15 empty] | 1187868
Sunray ES | [9 empty] | 425000 |  |  | 100000 | [10 empty] | 195000 | [6 empty] | 80000 |  |  |  |  | 381751 | [8 empty] | 30000 | [6 empty] | 1211751
1 | [12 empty] | 100000 | [38 empty] | 100000
3 | [30 empty] | 80000 | [20 empty] | 80000
5 | [9 empty] | 425000 | [13 empty] | 195000 | [11 empty] | 381751 | [15 empty] | 1001751
6 | [44 empty] | 30000 | [6 empty] | 30000
Thomas E. Weightman MS | [8 empty] | 80000 |  |  |  | 125000 |  |  | 80709 | [7 empty] | 400000 |  |  |  | 20000 | [11 empty] | 540000 |  |  |  |  | 194400 | [6 empty] | 1440109
1 | [12 empty] | 125000 | [38 empty] | 125000
2 | [23 empty] | 400000 | [27 empty] | 400000
3 | [8 empty] | 80000 | [18 empty] | 20000 | [23 empty] | 100000
5 | [15 empty] | 80709 | [35 empty] | 80709
6 | [39 empty] | 540000 |  |  |  |  | 194400 | [6 empty] | 734400
Transportation E | [21 empty] | 250000 | [29 empty] | 250000
5 | [21 empty] | 250000 | [29 empty] | 250000
Transportation NW | [38 empty] | 2500000 | 18891 | [11 empty] | 2518891
1 | [39 empty] | 18891 | [11 empty] | 18891
5 | [38 empty] | 2500000 | [12 empty] | 2500000
Transportation SE | [39 empty] | 48713 | [11 empty] | 48713
1 | [39 empty] | 48713 | [11 empty] | 48713
Transportation SW | [38 empty] | 5500000 | 218000 | [11 empty] | 5718000
1 | [39 empty] | 218000 | [11 empty] | 218000
5 | [38 empty] | 5500000 | [12 empty] | 5500000
Transportation W | [21 empty] | 650000 | [29 empty] | 650000
5 | [21 empty] | 650000 | [29 empty] | 650000
Trinity ES | [9 empty] | 425000 |  |  | 100000 | [17 empty] | 130000 |  |  |  |  | 57881 | [15 empty] | 712881
1 | [12 empty] | 100000 | [17 empty] | 50000 |  |  |  |  | 57881 | [15 empty] | 207881
4 | [30 empty] | 80000 | [20 empty] | 80000
5 | [9 empty] | 425000 | [41 empty] | 425000
Trinity Oaks ES | [23 empty] | 196006 | [11 empty] | 419926 | [15 empty] | 615932
1 | [23 empty] | 1006 | [27 empty] | 1006
4 | [23 empty] | 195000 | [27 empty] | 195000
6 | [35 empty] | 419926 | [15 empty] | 419926
Veterans ES | [35 empty] | 706178 | [15 empty] | 706178
6 | [35 empty] | 706178 | [15 empty] | 706178
Wesley Chapel ES | [9 empty] | 425000 | [41 empty] | 425000
4 | [9 empty] | 425000 | [41 empty] | 425000
Wesley Chapel HS | [6 empty] | 6053 | 75000 | 150000 | 800000 | [13 empty] | 650000 |  | 0 |  |  |  |  | 100000 |  |  |  | 16416 | [9 empty] | 20000 | [6 empty] | 1817469
1 | [6 empty] | 6053 | 75000 | 150000 | [14 empty] | 350000 |  | 0 | [8 empty] | 16416 | [16 empty] | 597469
2 | [9 empty] | 800000 | [41 empty] | 800000
3 | [23 empty] | 300000 | [27 empty] | 300000
4 | [30 empty] | 100000 | [20 empty] | 100000
6 | [44 empty] | 20000 | [6 empty] | 20000
West Zephyrhills ES | [9 empty] | 425000 | [13 empty] | 600000 | [6 empty] | 301220 | [7 empty] | 8226665 | [5 empty] | 220000 | [6 empty] | 9772885
1 | [9 empty] | 425000 | [20 empty] | 301220 | [20 empty] | 726220
2 | [38 empty] | 8226665 | [12 empty] | 8226665
6 | [23 empty] | 600000 | [20 empty] | 220000 | [6 empty] | 820000
Wiregrass Ranch HS |  |  |  |  | 40000 |  | 6162 | 75000 | 25000 |  |  |  | 51000 |  |  | 88779 | [18 empty] | 420000 | 1187868 |  |  | 4000000 | 125000 | [11 empty] | 6018809
1 | [6 empty] | 6162 | [5 empty] | 51000 | [26 empty] | 125000 | [11 empty] | 182162
2 | [34 empty] | 420000 | [16 empty] | 420000
3 | [38 empty] | 4000000 | [12 empty] | 4000000
4 | [8 empty] | 25000 | [42 empty] | 25000
5 |  |  |  |  | 40000 |  |  | 75000 | [43 empty] | 115000
6 | [15 empty] | 88779 | [19 empty] | 1187868 | [15 empty] | 1276647
Woodland ES | [9 empty] | 425000 |  | 21000 | 100000 | [10 empty] | 4447860 | [14 empty] | 4514705 | [5 empty] | 432000 | [6 empty] | 9940565
1 | [11 empty] | 21000 | 100000 | [38 empty] | 121000
3 | [23 empty] | 4447860 | [27 empty] | 4447860
4 | [9 empty] | 425000 | [41 empty] | 425000
5 | [38 empty] | 4514705 | [12 empty] | 4514705
6 | [44 empty] | 432000 | [6 empty] | 432000
Zephyrhills HS | [6 empty] | 2968257 |  | 50000 | 800000 | [5 empty] | 73371 | [7 empty] | 89671 | [10 empty] | 560000 |  |  |  | 20600000 | [12 empty] | 25141299
1 | [6 empty] | 468257 | [16 empty] | 89671 | [27 empty] | 557928
2 | [9 empty] | 800000 | [41 empty] | 800000
3 | [34 empty] | 560000 |  |  |  | 20600000 | [12 empty] | 21160000
4 | [15 empty] | 73371 | [35 empty] | 73371
5 | [6 empty] | 2500000 |  | 50000 | [42 empty] | 2550000
Grand Total | 309067804 | 100000 | 1200000 | 40000 | 960000 | 1100000 | 16086580 | 1140000 | 5977459 | 36772365 | 5064864 | 1541000 | 4176000 | 125000 | 54616228 | 1974668.25 | 46831230 | 25992234 |  | 4777563 | 11277535 | 6070418 | 15014590 | 28209394 | 3505000 | 0 | 725000 | 145000 | 7700000 | 60000 | 6792470 | 2200000 | 1100000 | 50000 | 996416 | 36972651.4725 | 100000 | 8000000 | 293264189 | 3830006 | 5350000 | 1710000 | 8500000 | 1100000 | 4706676 | 108000 | 18597372 | 18801000 | 20121372 | 62700000 | 5500000 | 1090750084.7225

## Escalator
2.2% escalator chart
| Year | Value
Multiply the preceding year | 1 | 100000 | 0%
by 1.022 to find the new | 2 | 102200 | 2.2% | 102200
value at an escalator | 3 | 104448.4 | 4.448% | 104448.4
of 2.2% | 4 | 106746.2648 | 6.746% | 106746.2648
| 5 | 109094.6826 | 9.095% | 109094.6826
| 6 | 111494.7656 | 11.49% | 111494.7656
| 7 | 113947.6505 | 13.95% | 113947.6505
| 8 | 116454.4988 | 16.45% | 116454.4988
| 9 | 119016.4978 | 19.02% | 119016.4978
| 10 | 121634.8607 | 21.63% | 121634.8607
| 11 | 124310.8277 | 24.31% | 124310.8277
| 12 | 127045.6659 | 27.05% | 127045.6659

## 12-13
Cost Center | School Name | Year Open | Request Dept | Assigned Dept | Project Description | Priority | Bgt Yr | Type | Budget Estimate | Adjusted Estimate | Final Cost | Status | Notes
0901 | Anclote ES | 1973 | PRT | MAINT | Roof Replacement | 1 | 12/13 |  | 405000 | 405000
0113 | Anclote HS | 2009 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 6000 | 6000 |  | Complete
0342 | Bayonet Point MS | 1973 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0100 | Charles S. Rushe MS | 2007 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0069 | Chasco MS | 2001 | PRT | MAINT | Replace Gutters | 1 | 12/13 |  | 91250 | 91250 |  | Purchasing
0311 | Cotee River ES | 1993 | PRT | MAINT | Roof Replacement | 1 | 12/13 |  | 700000 | 700000 |  | Design
0103 | Crews Lake MS | 2008 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0103 | Crews Lake MS | 2008 | PRT | CS&CC | Playground and Temporary Covered Play Area | 1 | 12/13 |  | 120000 | 120000 |  |  | Due to SHES move
0421 | Deer Park ES | 1988 | FNS | FNS | Cooler / Freezer | 1 | 12/13 |  | 60638 | 60638 |  | Complete
9999 | District Complex | 1974 | PRT | CS&CC | District Complex - Building 4 Remodel/Expansion - Parking Addition | 1 | 12/13 |  | 5447765 | 5447765 |  | In Design
9999 | District Complex | 1974 | PRT | MAINT | Roof Replacement - Building 8 | 1 | 12/13 |  | 387000 | 387000 |  | 40% Complete
9999 | District Wide |  | FIN | FIN | ERP System | 1 | 12/13 |  | 5004000 | 5004000
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - Elementary Site in 54 Corridor in Odessa Area | 1 | 12/13 |  | 2200000 | 2200000 |  | In Progress
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - Handcart Rd Property Next to High School "III" | 1 | 12/13 |  | 265000 | 265000 |  | Complete
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - High School Site in 54 Corridor in Odessa Area | 1 | 12/13 |  | 4000000 | 4000000
0086 | Dr. John Long MS | 2006 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
6997 | Energy Marine Center |  | MAINT | MAINT | Roof Maintenance | 1 | 12/13 |  | 60000 | 60000
0114 | Fivay HS | 2010 | CS&CC | CS&CC | Equipment | 1 | 12/13 |  | 409041 | 409041
0114 | Fivay HS | 2010 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 8000 | 8000 |  | Complete
0351 | Fox Hollow ES | 1990 | FNS | CS&CC | Serving Line Renovation | 1 | 12/13 |  | 272262 | 272262 |  | In Progress
0331 | Gulf HS | 1971 | ATH | MAINT | ADA Bleacher Retrofit | 1 | 12/13 |  | 25000 | 25000 |  | Complete
0331 | Gulf HS | 1971 | FNS | CS&CC | Cooler / Freezer | 1 | 12/13 |  | 60638 | 60638 |  | Summer | Needs an additional $9500
0331 | Gulf HS | 1971 | PRT | MAINT | HVAC Hydronic Boiler Replacement | 1 | 12/13 |  | 300000 | 300000 |  | Design
0331 | Gulf HS | 1971 | PRT | MAINT | HVAC Hydronic Pipe Replacement | 1 | 12/13 |  | 200000 | 200000 |  | Complete
0331 | Gulf HS | 1971 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 6000 | 6000 |  | Complete
0261 | Gulf MS | 1964 | PRT | CS&CC | Fire Sprinkle System | 1 | 12/13 | LCIF | 175000 | 175000 |  | Cancelled | Stage <1,000 sq ft so no fire sprinkling needed
0261 | Gulf MS | 1964 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0911 | Gulfside ES | 1977 | PRT | MAINT | Replace Chiller | 1 | 12/13 |  | 220000 | 220000 |  | Complete | This became an emergency item
0911 | Gulfside ES | 1977 | PRT | MAINT | Roofing Maintenance | 1 | 12/13 |  | 60000 | 60000
0521 | Hudson HS | 1973 | ATH | MAINT | Football Bleacher Renovations | 1 | 12/13 | LCIF | 4000 | 4000 |  | Complete
0521 | Hudson HS | 1973 | FNS | CS&CC | Kitchen Renovation - Phase 1 | 1 | 12/13 | LCIF | 50000 | 50000 |  | On Hold | Pending Kelley School Renovation
0521 | Hudson HS | 1973 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 46000 | 46000 |  | Complete
0951 | Hudson MS | 1984 | FNS | CS&CC | Kitchen & Serving Line Renovation | 1 | 12/13 |  | 1119000 | 1119000 |  | Summer
0073 | J.W. Mitchell HS | 2000 | FNS | CS&CC | Kitchen Renovation - Phase 1 | 1 | 12/13 |  | 750000 | 750000 |  | Design
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT | Overlay Courts - Tennis | 1 | 12/13 |  | 45000 | 45000
0961 | Lake Myrtle ES | 1984 | FNS | MAINT | HVAC Renovation Building #7 | 1 | 12/13 |  | 5000 | 5000 |  | Complete
0801 | Land O' Lakes HS | 1973 | ATH | MAINT | ADA Bleacher Retrofit | 1 | 12/13 | LCIF | 25000 | 25000 |  | Complete
0801 | Land O' Lakes HS | 1973 | PRT | CS&CC | Culinary Academy - Phase II. Equipment Additions | 1 | 12/13 |  | 70000 | 70000 |  | In Progress
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC | Replace Gym Floor | 1 | 12/13 |  | 161000 | 161000 |  | Summer
2081 | Longleaf ES | 2005 | FNS | MAINT | Kitchen Floor Renovation | 1 | 12/13 |  | 25000 | 25000 |  | Complete
9999 | Maintenance Dept Building |  | PRT | MAINT | Roofing Maintenance | 1 | 12/13 |  | 25000 | 25000 |  | Not Started
0211 | Mittye P. Locke ES | 1966 | MAINT | MAINT | Roof Maintenance | 1 | 12/13 |  | 80000 | 80000 |  | Not Started
0117 | Odessa ES | 2009 | CS&CC | CS&CC | Equipment | 1 | 12/13 |  | 128088 | 128088
0031 | Pasco HS | 1964 | PRT | CS&CC | Master Plan Redevelopment - Finish Road/Retaining Wall | 1 | 12/13 | Penny/Intrl | 315982 | 315982 |  | In Progress
0031 | Pasco HS | 1964 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 8000 | 8000 |  | Complete
0031 | Pasco HS | 1964 | PRT | CS&CC | Replace Gym Floor | 1 | 12/13 |  | 57856 | 57856 |  | Complete
0071 | Pasco MS | 1946 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0089 | Paul R. Smith MS | 2006 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0921 | Pine View MS | 1977 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0361 | Quail Hollow ES | 1975 | FNS | FNS | Kitchen Hood - Code Violations | 1 | 12/13 |  | 57881 | 57881 |  | On Hold
0102 | R.B. Stewart MS | 1926 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Replace Gym Bld #3 - Phase 1 | 1 | 12/13 | Penny | 1950000 | 1950000 |  | In Progress
0271 | Richey ES | 1958 | PRT | CS&CC | Campus Redevelopment - Master Plan | 1 | 12/13 | Imp/Intrl | 544302 | 544302 |  | Close Out
0931 | Ridgewood HS | 1977 | ATH | MAINT | ADA Bleacher Retrofit | 1 | 12/13 | LCIF | 25000 | 25000 |  | Complete
0471 | River Ridge HS | 1990 | ATH | MAINT | ADA Bleacher Retrofit | 1 | 12/13 | LCIF | 25000 | 25000 |  | Complete
0471 | River Ridge HS | 1990 | FNS | CS&CC | Cafeteria Renovation - Phase 1 | 1 | 12/13 |  | 1000000 | 1000000 |  | Design
0471 | River Ridge HS | 1990 | PRT | CS&CC | HVAC Renovation (controls) | 1 | 12/13 |  | 500000 | 500000 |  | In Progress
0471 | River Ridge HS | 1990 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 10000 | 10000 |  | Complete
0201 | Sanders Memorial ES | 1944 | PRT | CS&CC | Campus Redevelopment | 1 | 12/13 |  | 16447623 | 16447623 |  | Open 2015 | Site Work Completed
0341 | Schrader ES | 1972 | PRT | CS&CC | Replacement Bldg #1 - Design | 1 | 12/13 |  | 984330 | 984330 |  | In Progress
0341 | Schrader ES | 1972 | PRT | CS&CC | Replacement Bldg #1 - Phase 1 | 1 | 12/13 | Interlocal | 6984000 | 6984000 |  | Summer
0057 | Seven Springs MS | 1995 | ATH | MAINT | Basketball Court/Tennis Overlay | 1 | 12/13 |  | 85000 | 85000 |  | Summer
0057 | Seven Springs MS | 1995 | FNS | FNS | Cafeteria Renovation - Serving Line Only | 1 | 12/13 |  | 6860 | 6860 |  | Complete
0057 | Seven Springs MS | 1995 | FNS | FNS | Cooler / Freezer | 1 | 12/13 |  | 204000 | 204000 |  | Summer
0057 | Seven Springs MS | 1995 | PRT | CS&CC | HVAC Chiller Pipe Replacement | 1 | 12/13 |  | 2000000 | 2000000 |  | In Progress
0057 | Seven Springs MS | 1995 | FNS | CS&CC | Kitchen Renovation - Phase 2 | 1 | 12/13 |  | 439030 | 439030 |  | Complete
0057 | Seven Springs MS | 1995 | PRT | MAINT | Metal Roof re-coat | 1 | 12/13 |  | 83770 | 83770 |  | Complete
0057 | Seven Springs MS | 1995 | ATH | MAINT | Sand & Paint Gym Floors | 1 | 12/13 |  | 25000 | 25000 |  | Summer
0101 | Sunlake HS | 2007 | ATH | MAINT | Add Air Conditioning To Field House | 1 | 12/13 |  | 110000 | 110000 |  | Need funding
0101 | Sunlake HS | 2007 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 6000 | 6000 |  | Complete
0072 | Sunray ES | 2000 | FNS | MAINT | Kitchen Floor Renovation | 1 | 12/13 |  | 33600 | 33600 |  | Complete
0461 | Thomas E. Weightman MS | 1990 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 4000 | 4000 |  | Complete
0032 | Trinity ES | 2000 | FNS | CS&CC | Cooler/Freezer | 1 | 12/13 |  | 70000 | 70000 |  | Complete
0085 | Trinity Oaks ES | 2007 | PRT | CS&CC | Add Dehumidification | 1 | 12/13 |  | 40000 | 40000 |  | In Progress
2071 | Wesley Chapel ES | 2002 | PRT | MAINT | LCD Projector Installation | 1 | 12/13 |  | 100000 | 100000 |  | Complete
0063 | Wesley Chapel HS | 1998 | ATH | MAINT | Add Air Conditioning To Field House | 1 | 12/13 |  | 110000 | 110000 |  | Need funding
0063 | Wesley Chapel HS | 1998 | CCTE | CS&CC | Career Academy - Automotive | 1 | 12/13 | LCIF | 446877 | 446877 |  | Complete
0063 | Wesley Chapel HS | 1998 | CCTE | CS&CC | Career Academy - Remodel TV Production Lab | 1 | 12/13 | LCIF | 83398 | 83398 |  | Complete
0063 | Wesley Chapel HS | 1998 | PRT | CS&CC | HVAC Controls Replacement - Phase 2 | 1 | 12/13 |  | 83248 | 83248 |  | Cancelled
0063 | Wesley Chapel HS | 1998 | PRT | CS&CC | Parking Lot - Add Lights | 1 | 12/13 |  | 80455 | 80455 |  | Complete
0063 | Wesley Chapel HS | 1998 | ATH | ATH | Scoreboard Replacement(s) | 1 | 12/13 |  | 75000 | 75000
0091 | West Zephyrhills ES | 1958 | MAINT | MAINT | Roof Replacement - Cafeteria and Media | 1 | 12/13 |  | 301220 | 301220 |  | Purchasing
0090 | Wiregrass Ranch HS | 2006 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 6000 | 6000 |  | Complete
0132 | Woodland ES | 1977 | MAINT | MAINT | Replace Cafeteria Tile | 1 | 12/13 |  | 19000 | 19000 |  | Complete
0131 | Zephyrhills HS | 1973 | ATH | MAINT | ADA Bleacher Retrofit | 1 | 12/13 |  | 25000 | 25000 |  | Complete
0131 | Zephyrhills HS | 1973 | FNS | FNS | New Automated Menu System due to New Federal Regulations | 1 | 12/13 |  | 6000 | 6000 |  | Complete
0131 | Zephyrhills HS | 1973 | PRT | MAINT | Rebuild Gym Air Handlers | 1 | 12/13 |  | 90000 | 90000 |  | Summer
0131 | Zephyrhills HS | 1973 | ATH | CS&CC | Weight Room Renovation/Expansion | 1 | 12/13 |  | 143590 | 143590 |  | No dollar match from school. Need direction
0342 | Bayonet Point MS | 1973 | PRT | MAINT | Roof Replacement | 1 | 13/14 |  | 1000000 | 1000000
0069 | Centennial MS | 2001 | FNS | MAINT | Cooler/Freezer Flooding | 1 | 13/14 |  | 70000 | 70000
0081 | Moore Mickens EC | 1952 | CTE | MAINT | Remodel CNA Room | 1 |  |  | 108000 | 108000
0081 | Moore Mickens EC | 1952 | CTE | MAINT | Remodel Or Build New Space For Cosmetology | 1 |  |  | 600000 | 600000
0081 | Moore Mickens EC | 1952 | FNS | MAINT | Cooler / Freezer | 4 |  |  | 73371 | 83606.2545
0081 | Moore Mickens EC | 1952 | PRT | MAINT | Remodel School | 2 |  |  | 445419 | 465240.1455
0701 | Cypress ES | 1973 | PRT | MAINT | Roof Replacement | 1 | 13/14 |  | 300000 | 300000
9999 | District Wide |  | ATH | MAINT | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 1 | 13/14 |  | 150000 | 150000
9999 | District Wide |  | ATH | MAINT | Annual Bleacher Repair ($100,000 Annually) | 1 | 13/14 |  | 100000 | 100000
9999 | District Wide |  | FIN | FIN | Annual Buses & Other Vehicles | 1 | 13/14 |  | 1502500 | 1502500
9999 | District Wide |  | FIN | FIN | Annual Compliance w/Environmental Reg | 1 | 13/14 |  | 202000 | 202000
9999 | District Wide |  | FIN | FIN | Annual Compliance with ADA | 1 | 13/14 |  | 150000 | 150000 |  |  | Added at the request of CS&CC
9999 | District Wide |  | FIN | FIN | Annual Debt Service Payments | 1 | 13/14 |  | 38306254 | 38306254
9999 | District Wide |  | PRT | MAINT | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 1 | 13/14 |  | 850000 | 850000
9999 | District Wide |  | PRT | MAINT | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 1 | 13/14 |  | 200000 | 200000
9999 | District Wide |  | PRT | CS&CC | Annual Fire Loop / Hydrants ($500,000 Annually) | 1 | 13/14 |  | 500000 | 500000
9999 | District Wide |  | FIN | FIN | Annual FISH Signage | 1 | 13/14 |  | 10000 | 10000
9999 | District Wide |  | PRT | MAINT | Annual Flooring Replacement ($300,000 Annually) | 1 | 13/14 |  | 300000 | 300000
9999 | District Wide |  | ATH | MAINT | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 1 | 13/14 |  | 60000 | 60000
9999 | District Wide |  | PRT | MAINT | Annual HVAC Equipment Replacements ($250,000 Annually) | 1 | 13/14 |  | 250000 | 250000
9999 | District Wide |  | PRT | MAINT | Annual Lift Station Upgrades ($100,000 Annually) | 1 | 13/14 |  | 100000 | 100000
9999 | District Wide |  | FIN | FIN | Annual Maintenance & Repairs Projects (Small) | 1 | 13/14 |  | 1212000 | 1212000
9999 | District Wide |  | FIN | FIN | Annual Maintenance Health & Safety | 1 | 13/14 |  | 202000 | 202000
9999 | District Wide |  | PRT | MAINT | Annual Marquee Sign Replacements ($15,000 Annually) | 1 | 13/14 |  | 15000 | 15000
9999 | District Wide |  | PRT | MAINT | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 1 | 13/14 |  | 500000 | 500000
9999 | District Wide |  | PRT | MAINT | Annual Physical Education Equipment Replacements ($200,000 Annually) | 1 | 13/14 |  | 200000 | 200000
9999 | District Wide |  | PRT | MAINT | Annual Portable Maintenance & Moving ($100,000 Annually) | 1 | 13/14 |  | 100000 | 100000
9999 | District Wide |  | PRT | MAINT | Annual Security Cameras & Alarms ($100,000 Annually) | 1 | 13/14 |  | 100000 | 100000
9999 | District Wide |  | ATH | MAINT | Annual Sound System Repairs ($75,000 Annually) | 1 | 13/14 |  | 75000 | 75000
9999 | District Wide |  | FIN | FIN | Annual Technology and Equipment (Incl Student Computers) | 1 | 13/14 |  | 8098375 | 8098375
9999 | District Wide |  | FIN | FIN | Annual Telecommunications Repairs Projects (Small) | 1 | 13/14 |  | 820000 | 820000
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - Elementary Site in 54 Corridor in Odessa Area | 1 | 13/14 |  | 2200000 | 2200000 |  |  | Added for 2nd elementary site - Ashley Glen and Smith 54
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - If land becomes available next to existing school sites | 1 | 13/14 |  | 735000 | 735000
9999 | District Wide |  | FIN | FIN | Property Insurance | 1 | 13/14 |  | 4200000 | 4200000
0093 | Gulf Trace ES | 2008 | PRT | CS&CC | Traffic Safety and Parking Improvements | 1 | 13/14 |  | 655000 | 655000 |  | In Progress | Need addl funding - $165,000 more than original $490,000
0521 | Hudson HS | 1973 | ATH | MAINT | ADA Bleacher Retrofit | 1 | 13/14 | LCIF | 25000 | 25000 |  | Complete
0073 | J.W. Mitchell HS | 2000 | FNS | CS&CC | Kitchen Renovation - Phase 2 | 1 | 13/14 |  | 1290015 | 1290015 |  | Summer
0801 | Land O' Lakes HS | 1973 | PRT | MAINT | Roof Maintenance - SMS | 1 | 13/14 |  | 160000 | 160000
0451 | Mary Giella ES | 1989 | PRT | CS&CC | Traffic Safety and Parking Improvements | 1 | 13/14 |  | 390000 | 390000 |  |  | Need to do in conjunction with Offsite Infrastructure Project
0941 | Moon Lake ES | 1982 | PRT | MAINT | Roof Replacement | 1 | 13/14 |  | 500000 | 500000
0921 | Pine View MS | 1977 | PRT | MAINT | Roof Replacement | 1 | 13/14 |  | 900000 | 900000
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Replace Gym Bld #3 - Phase 2 | 1 | 13/14 |  | 1750000 | 1750000 |  | Funding | Need $1.4 million additional
0102 | R.B. Stewart MS | 1926 | PRT | CS&CC | Remodel Bld #4 #5 (Media And ESE) | 2 | 13/14 |  | 1000000 | 1044500 |  |  | Combined with Gym Replacement in Priority 1
0471 | River Ridge HS | 1990 | FNS | CS&CC | Cafeteria Renovation - Phase 2 | 1 | 13/14 |  | 1000000 | 1000000 |  | Summer
0471 | River Ridge HS | 1990 | ATH | CS&CC | Concession Stand Bathrooms - Baseball/Softball | 1 | 13/14 |  | 350000 | 350000 |  | Design
0341 | Schrader ES | 1972 | PRT | CS&CC | Replacement Bldg #1 - Phase 2 | 1 | 13/14 |  | 6500000 | 6500000 |  | Summer
0341 | Schrader ES | 1972 | PRT | CS&CC | Traffic Safety and Parking Improvements | 1 | 13/14 |  | 432000 | 432000 |  | Summer
0601 | Shady Hills ES | 1973 | PRT | MAINT | Roof Replacement | 1 | 13/14 |  | 300000 | 300000 |  |  | Roll Funds into Remodel
9035 | Transportation NW | 1979 | PRT | CS&CC | Retention Pond and Flooding Repairs | 1 | 13/14 |  | 170000 | 170000 |  |  | Flooding issue as a result of Tropical Storm Debby. Need additional money another $90,000
9038 | Transportation SE |  | PRT | CS&CC | Retention Pond and Flooding Repairs | 1 | 13/14 |  | 80000 | 80000 |  |  | Retention pond overflowing to neighboring property
9999 | Transportation SW |  | PRT | CS&CC | Pre-Installation of Utilities | 1 | 13/14 |  | 150000 | 150000 |  |  | Install Utilities while Interlaken Road being constructed
0063 | Wesley Chapel HS | 1998 | PRT | CS&CC | Maintenance of Drainage Canal behind school complex | 1 | 13/14 |  | 0 | 0
0063 | Wesley Chapel HS | 1998 | ATH | MAINT | Overlay Courts | 1 | 13/14 |  | 150000 | 150000
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT | Add Air Conditioning To Field House | 1 | 13/14 |  | 110000 | 110000 |  | Need funding
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC | Traffic Safety and Parking Improvements - Traffic Light @ Mansfield | 1 | 13/14 |  | 125000 | 125000 |  |  | Need to add to 5-Year Work Plan Infrastructure
0931 | Ridgewood HS | 1977 | PRT | CS&CC | HVAC Renovation | 1 | 14/15 |  | 2200000 | 2200000 |  | Design | Will do in 13/14 if money available
0321 | Lacoochee ES | 1971 | PRT | CS&CC | Remodel - Add Multi-Purpose Space - Phase 1 | 1 | LCIF |  | 650000 | 650000 |  | Complete
0901 | Anclote ES | 1973 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0901 | Anclote ES | 1973 | PRT | CS&CC | Remodel School - Kelley School + Add Capacity | 2 |  |  | 8500000 | 8878250
0901 | Anclote ES | 1973 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 425000 | 443912.5
0901 | Anclote ES | 1973 | FNS | FNS | Kitchen Hood | 3 |  |  | 66853 | 72929.9377
0901 | Anclote ES | 1973 | FNS | CS&CC | Serving Line Renovation | 3 |  |  | 315497 | 344175.6773
0901 | Anclote ES | 1973 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 114696 | 142578.5976
0113 | Anclote HS | 2009 | ATH | ATH | Sand & Paint Gym Floors | 5 |  |  | 25000 | 29755
0113 | Anclote HS | 2009 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0342 | Bayonet Point MS | 1973 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0342 | Bayonet Point MS | 1973 | PRT | CS&CC | Remodel School - Kelley School | 1 |  | Penny | 14500000 | 14500000
0342 | Bayonet Point MS | 1973 | FNS | CS&CC | Cooler / Freezer with Renovations (Stock Room) | 2 |  |  | 203963 | 213039.3535
0342 | Bayonet Point MS | 1973 | ATH | MAINT | Renovate Girls & Boys Locker Rooms | 2 |  |  | 100000 | 104450
0342 | Bayonet Point MS | 1973 | FNS | CS&CC | Serving Line Renovation | 3 |  |  | 120329 | 131266.9061
0342 | Bayonet Point MS | 1973 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 650000 | 773630
0342 | Bayonet Point MS | 1973 | SCHOOL | MAINT | Covered Walkways | 6 |  |  | 25000 | 31077.5
0932 | Calusa ES | 1979 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0932 | Calusa ES | 1979 | FNS | CS&CC | Cooler / Freezer with Renovations | 2 |  |  | 203963 | 213039.3535
0932 | Calusa ES | 1979 | FNS | FNS | Kitchen Hood | 2 |  |  | 60775 | 63479.4875
0932 | Calusa ES | 1979 | FNS | CS&CC | Serving Line Renovation | 2 |  |  | 286815 | 299578.2675
0932 | Calusa ES | 1979 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 425000 | 484287.5
0932 | Calusa ES | 1979 | PRT | CS&CC | Traffic Safety and Parking Improvements | 5 |  |  | 650000 | 773630
0932 | Calusa ES | 1979 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 206000 | 256078.6
0401 | Centennial ES | 1986 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0401 | Centennial ES | 1986 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0401 | Centennial ES | 1986 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 204750 | 243693.45
0069 | Centennial MS | 2001 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0074 | Centennial MS | 2001 | FNS | FNS | Outside Dining Sun Shade | 4 |  |  | 10000 | 11395
0074 | Centennial MS | 2001 | PRT | MAINT | Roof Maintenance | 4 |  |  | 80000 | 91160
0074 | Centennial MS | 2001 | FNS | CS&CC | Serving Line Renovation | 4 |  |  | 981709 | 1118657.4055
0074 | Centennial MS | 2001 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 650000 | 740675
0074 | Centennial MS | 2001 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0074 | Centennial MS | 2001 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 130000 | 161603
0100 | Charles S. Rushe MS | 2007 | ATH | ATH | Resurface Track Courts | 5 |  |  | 50000 | 59510
0100 | Charles S. Rushe MS | 2007 | ATH | ATH | Sand & Paint Gym Floors | 5 |  |  | 25000 | 29755
0100 | Charles S. Rushe MS | 2007 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0070 | Chasco ES | 2000 | PRT | MAINT | Roof Maintenance | 4 |  |  | 40000 | 45580
0070 | Chasco ES | 2000 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 425000 | 484287.5
0070 | Chasco ES | 2000 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 195000 | 232089
0070 | Chasco ES | 2000 | FNS | CS&CC | Kitchen Renovation | 5 |  |  | 943483 | 1122933.4666
0070 | Chasco ES | 2000 | SCHOOL | CS&CC | Covered Walkways - Bus Loop | 6 |  |  | 100000 | 124310
0070 | Chasco ES | 2000 | SCHOOL | MAINT | Restroom for PE Classes | 6 |  |  | 300000 | 372930 |  | New | Evaluating
0069 | Chasco MS | 2001 | FNS | FNS | Cooler / Freezer | 2 |  |  | 66701.25 | 69669.4556
0069 | Chasco MS | 2001 | PRT | MAINT | Roof Maintenance | 4 |  |  | 80000 | 91160
0069 | Chasco MS | 2000 | ATH | ATH | Sand & Paint Gym Floors | 4 |  |  | 25000 | 28487.5
0069 | Chasco MS | 2001 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 650000 | 740675
0069 | Chasco MS | 2001 | FNS | FNS | Outside Dining Sun Shade | 5 |  |  | 8000 | 9521.6
0069 | Chasco MS | 2001 | FNS | CS&CC | Serving Line Renovation | 5 |  |  | 811329.75 | 965644.6684
0060 | Chester Taylor ES | 1996 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0060 | Chester Taylor ES | 1996 | PRT | MAINT | Roof Maintenance | 2 |  |  | 80000 | 83560
0060 | Chester Taylor ES | 1996 | FNS | CS&CC | A/C Renovation To Kitchen | 3 |  |  | 195000 | 212725.5
0060 | Chester Taylor ES | 1996 | FNS | CS&CC | Serving Line Renovation | 3 |  |  | 315497 | 344175.6773
0060 | Chester Taylor ES | 1996 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
0060 | Chester Taylor ES | 1996 | FNS | FNS | Cooler / Freezer | 5 |  |  | 80709 | 96059.8518
0311 | Cotee River ES | 1993 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0311 | Cotee River ES | 1993 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 425000 | 443912.5
0311 | Cotee River ES | 1993 | PRT | CS&CC | Traffic Safety and Parking Improvements | 3 |  |  | 1000000 | 1090900
0311 | Cotee River ES | 1993 | FNS | FNS | Cooler / Freezer | 4 |  |  | 73371 | 83606.2545
0311 | Cotee River ES | 1993 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 162000 | 201382.2
0103 | Crews Lake MS | 2008 | ATH | ATH | Resurface Track Courts | 5 |  |  | 50000 | 59510
0103 | Crews Lake MS | 2008 | ATH | ATH | Sand & Paint Gym Floors | 5 |  |  | 25000 | 29755
0103 | Crews Lake MS | 2008 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 2314818 | 2877550.2558
0701 | Cypress ES | 1973 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0701 | Cypress ES | 1973 | PRT | CS&CC | Remodel School - Kelley School + Add Capacity | 1 |  |  | 8500000 | 8500000
0701 | Cypress ES | 1973 | FNS | FNS | Cooler / Freezer | 2 |  |  | 66701 | 69669.1945
0701 | Cypress ES | 1973 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
0701 | Cypress ES | 1973 | FNS | FNS | Kitchen Hood | 4 |  |  | 73538 | 83796.551
0701 | Cypress ES | 1973 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 475000 | 590472.5
0421 | Deer Park ES | 1988 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0421 | Deer Park ES | 1988 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0421 | Deer Park ES | 1988 | FNS | CS&CC | Serving Line Renovation | 4 |  |  | 347047 | 395460.0565
0421 | Deer Park ES | 1988 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 204750 | 243693.45
0059 | Denham Oaks ES | 1994 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0059 | Denham Oaks ES | 1994 | PRT | MAINT | Roof Maintenance and Internal Gutters | 3 |  |  | 50000 | 54545
0059 | Denham Oaks ES | 1994 | FNS | CS&CC | Serving Line Renovation | 3 |  |  | 315497 | 344175.6773
0059 | Denham Oaks ES | 1994 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
0059 | Denham Oaks ES | 1994 | FNS | FNS | Cooler / Freezer | 5 |  |  | 80709 | 96059.8518
0059 | Denham Oaks ES | 1994 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 135000 | 167818.5
9999 | District Complex | 1974 | PRT | CS&CC | District Complex - Phase 2 ? | 2 |  |  | 0 | 0
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - Elementary School Site in North Land O' Lakes area | 1 |  |  | 1000000 | 1000000
9999 | District Wide |  | FIN | FIN | Student Information System - New | 1 |  |  | 11277535 | 11277535
9999 | District Wide |  | ATH | MAINT | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 2 |  |  | 300000 | 313350
9999 | District Wide |  | ATH | MAINT | Annual Bleacher Repair ($100,000 Annually) | 2 |  |  | 200000 | 208900
9999 | District Wide |  | FIN | FIN | Annual Buses & Other Vehicles | 2 |  |  | 4225402 | 4413432.389
9999 | District Wide |  | FIN | FIN | Annual Compliance w/Environmental Reg | 2 |  |  | 420322 | 439026.329
10000 | District Wide |  | FIN | FIN | Annual Compliance with ADA | 2 |  |  | 300000 | 313350 |  |  | Added at the request of CS&CC
9999 | District Wide |  | FIN | FIN | Annual Debt Service Payments | 2 |  |  | 62938379 | 62938379
9999 | District Wide |  | PRT | MAINT | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 2 |  |  | 1700000 | 1775650
9999 | District Wide |  | PRT | MAINT | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 2 |  |  | 400000 | 417800
9999 | District Wide |  | PRT | CS&CC | Annual Fire Loop / Hydrants ($500,000 Annually) | 2 |  |  | 1000000 | 1044500
9999 | District Wide |  | PRT | MAINT | Annual Flooring Replacement | 2 |  |  | 600000 | 626700
9999 | District Wide |  | ATH | ATH | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 2 |  |  | 120000 | 125340
9999 | District Wide |  | PRT | MAINT | Annual HVAC Equipment Replacements ($250,000 Annually) | 2 |  |  | 500000 | 522250
9999 | District Wide |  | PRT | MAINT | Annual Lift Station Upgrades ($100,000 Annually) | 2 |  |  | 200000 | 208900
9999 | District Wide |  | FIN | FIN | Annual Maintenance & Repairs Projects (Small) | 2 |  |  | 2521930 | 2634155.885
9999 | District Wide |  | FIN | FIN | Annual Maintenance Health & Safety | 2 |  |  | 420322 | 439026.329
9999 | District Wide |  | PRT | MAINT | Annual Marquee Sign Replacements ($15,000 Annually) | 2 |  |  | 30000 | 31335
9999 | District Wide |  | PRT | MAINT | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 2 |  |  | 1000000 | 1044500
9999 | District Wide |  | PRT | MAINT | Annual Physical Education Equipment Replacements ($200,000 Annually) | 2 |  |  | 400000 | 417800
9999 | District Wide |  | PRT | MAINT | Annual Portable Maintenance & Moving ($100,000 Annually) | 2 |  |  | 200000 | 208900
9999 | District Wide |  | PRT | MAINT | Annual Security Cameras & Alarms | 2 |  |  | 200000 | 208900
9999 | District Wide |  | ATH | MAINT | Annual Sound System Repairs ($75,000 Annually) | 2 |  |  | 150000 | 156675
9999 | District Wide |  | FIN | FIN | Annual Technology and Equipment (Incl Student Computers) | 2 |  |  | 17065403 | 17824813.4335
9999 | District Wide |  | FIN | FIN | Annual Telecommunications Repairs Projects (Small) | 2 |  |  | 1730736 | 1807753.752
9999 | District Wide |  | ATH | MAINT | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 3 |  |  | 300000 | 327270
9999 | District Wide |  | ATH | MAINT | Annual Bleacher Repair ($100,000 Annually) | 3 |  |  | 200000 | 218180
9999 | District Wide |  | FIN | FIN | Annual Buses & Other Vehicles | 3 |  |  | 4667428 | 5091697.2052
9999 | District Wide |  | FIN | FIN | Annual Compliance w/Environmental Reg | 3 |  |  | 437303 | 477053.8427
10001 | District Wide |  | FIN | FIN | Annual Compliance with ADA | 3 |  |  | 300000 | 327270 |  |  | Added at the request of CS&CC
9999 | District Wide |  | FIN | FIN | Annual Debt Service Payments | 3 |  |  | 50340588 | 50340588
9999 | District Wide |  | PRT | MAINT | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 3 |  |  | 1700000 | 1854530
9999 | District Wide |  | PRT | MAINT | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 3 |  |  | 400000 | 436360
9999 | District Wide |  | PRT | CS&CC | Annual Fire Loop / Hydrants ($500,000 Annually) | 3 |  |  | 1000000 | 1090900
9999 | District Wide |  | PRT | MAINT | Annual Flooring Replacement | 3 |  |  | 600000 | 654540
9999 | District Wide |  | ATH | ATH | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 3 |  |  | 120000 | 130908
9999 | District Wide |  | PRT | MAINT | Annual HVAC Equipment Replacements ($250,000 Annually) | 3 |  |  | 500000 | 545450
9999 | District Wide |  | PRT | MAINT | Annual Lift Station Upgrades ($100,000 Annually) | 3 |  |  | 200000 | 218180
9999 | District Wide |  | FIN | FIN | Annual Maintenance & Repairs Projects (Small) | 3 |  |  | 2623816 | 2862320.8744
9999 | District Wide |  | FIN | FIN | Annual Maintenance Health & Safety | 3 |  |  | 437303 | 477053.8427
9999 | District Wide |  | PRT | MAINT | Annual Marquee Sign Replacements ($15,000 Annually) | 3 |  |  | 30000 | 32727
9999 | District Wide |  | PRT | MAINT | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 3 |  |  | 1000000 | 1090900
9999 | District Wide |  | PRT | MAINT | Annual Physical Education Equipment Replacements ($200,000 Annually) | 3 |  |  | 400000 | 436360
9999 | District Wide |  | PRT | MAINT | Annual Portable Maintenance & Moving ($100,000 Annually) | 3 |  |  | 200000 | 218180
9999 | District Wide |  | PRT | MAINT | Annual Security Cameras & Alarms | 3 |  |  | 200000 | 218180
9999 | District Wide |  | ATH | MAINT | Annual Sound System Repairs ($75,000 Annually) | 3 |  |  | 150000 | 163635
9999 | District Wide |  | FIN | FIN | Annual Technology and Equipment (Incl Student Computers) | 3 |  |  | 18104686 | 19750401.9574
9999 | District Wide |  | FIN | FIN | Annual Telecommunications Repairs Projects (Small) | 3 |  |  | 1800658 | 1964337.8122
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - Middle/High Site in River Landing (Wesley Chapel) | 3 |  |  | 4000000 | 4363600
9999 | District Wide |  | ATH | MAINT | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 4 |  |  | 300000 | 341850
9999 | District Wide |  | ATH | MAINT | Annual Bleacher Repair ($100,000 Annually) | 4 |  |  | 200000 | 227900
9999 | District Wide |  | FIN | FIN | Annual Buses & Other Vehicles | 4 |  |  | 4855992 | 5533402.884
9999 | District Wide |  | FIN | FIN | Annual Compliance w/Environmental Reg | 4 |  |  | 454970 | 518438.315
10002 | District Wide |  | FIN | FIN | Annual Compliance with ADA | 4 |  |  | 300000 | 341850 |  |  | Added at the request of CS&CC
9999 | District Wide |  | FIN | FIN | Annual Debt Service Payments | 4 |  |  | 54561680 | 54561680
9999 | District Wide |  | PRT | MAINT | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 4 |  |  | 1700000 | 1937150
9999 | District Wide |  | PRT | MAINT | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 4 |  |  | 400000 | 455800
9999 | District Wide |  | PRT | CS&CC | Annual Fire Loop / Hydrants ($500,000 Annually) | 4 |  |  | 1000000 | 1139500
9999 | District Wide |  | PRT | MAINT | Annual Flooring Replacement | 4 |  |  | 600000 | 683700
9999 | District Wide |  | ATH | ATH | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 4 |  |  | 120000 | 136740
9999 | District Wide |  | PRT | MAINT | Annual HVAC Equipment Replacements ($250,000 Annually) | 4 |  |  | 500000 | 569750
9999 | District Wide |  | PRT | MAINT | Annual Lift Station Upgrades ($100,000 Annually) | 4 |  |  | 200000 | 227900
9999 | District Wide |  | FIN | FIN | Annual Maintenance & Repairs Projects (Small) | 4 |  |  | 2729818 | 3110627.611
9999 | District Wide |  | FIN | FIN | Annual Maintenance Health & Safety | 4 |  |  | 454970 | 518438.315
9999 | District Wide |  | PRT | MAINT | Annual Marquee Sign Replacements ($15,000 Annually) | 4 |  |  | 30000 | 34185
9999 | District Wide |  | PRT | MAINT | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 4 |  |  | 1000000 | 1139500
9999 | District Wide |  | PRT | MAINT | Annual Physical Education Equipment Replacements ($200,000 Annually) | 4 |  |  | 400000 | 455800
9999 | District Wide |  | PRT | MAINT | Annual Portable Maintenance & Moving ($100,000 Annually) | 4 |  |  | 200000 | 227900
9999 | District Wide |  | PRT | MAINT | Annual Security Cameras & Alarms | 4 |  |  | 200000 | 227900
9999 | District Wide |  | ATH | MAINT | Annual Sound System Repairs ($75,000 Annually) | 4 |  |  | 150000 | 170925
9999 | District Wide |  | FIN | FIN | Annual Technology and Equipment (Incl Student Computers) | 4 |  |  | 18923410 | 21563225.695
9999 | District Wide |  | FIN | FIN | Annual Telecommunications Repairs Projects (Small) | 4 |  |  | 1873404 | 2134743.858
9999 | District Wide |  | ATH | MAINT | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 5 |  |  | 300000 | 357060
9999 | District Wide |  | ATH | MAINT | Annual Bleacher Repair ($100,000 Annually) | 5 |  |  | 200000 | 238040
9999 | District Wide |  | FIN | FIN | Annual Buses & Other Vehicles | 5 |  |  | 5052174 | 6013097.4948
9999 | District Wide |  | FIN | FIN | Annual Compliance w/Environmental Reg | 5 |  |  | 473350 | 563381.17
10003 | District Wide |  | FIN | FIN | Annual Compliance with ADA | 5 |  |  | 300000 | 357060 |  |  | Added at the request of CS&CC
9999 | District Wide |  | FIN | FIN | Annual Debt Service Payments | 5 |  |  | 50647051 | 50647051
9999 | District Wide |  | PRT | MAINT | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 5 |  |  | 1700000 | 2023340
9999 | District Wide |  | PRT | MAINT | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 5 |  |  | 400000 | 476080
9999 | District Wide |  | PRT | CS&CC | Annual Fire Loop / Hydrants ($500,000 Annually) | 5 |  |  | 1000000 | 1190200
9999 | District Wide |  | PRT | MAINT | Annual Flooring Replacement | 5 |  |  | 600000 | 714120
9999 | District Wide |  | ATH | ATH | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 5 |  |  | 120000 | 142824
9999 | District Wide |  | PRT | MAINT | Annual HVAC Equipment Replacements ($250,000 Annually) | 5 |  |  | 500000 | 595100
9999 | District Wide |  | PRT | MAINT | Annual Lift Station Upgrades ($100,000 Annually) | 5 |  |  | 200000 | 238040
9999 | District Wide |  | FIN | FIN | Annual Maintenance & Repairs Projects (Small) | 5 |  |  | 2840102 | 3380289.4004
9999 | District Wide |  | FIN | FIN | Annual Maintenance Health & Safety | 5 |  |  | 473350 | 563381.17
9999 | District Wide |  | PRT | MAINT | Annual Marquee Sign Replacements ($15,000 Annually) | 5 |  |  | 30000 | 35706
9999 | District Wide |  | PRT | MAINT | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 5 |  |  | 1000000 | 1190200
9999 | District Wide |  | PRT | MAINT | Annual Physical Education Equipment Replacements ($200,000 Annually) | 5 |  |  | 400000 | 476080
9999 | District Wide |  | PRT | MAINT | Annual Portable Maintenance & Moving ($100,000 Annually) | 5 |  |  | 200000 | 238040
9999 | District Wide |  | PRT | MAINT | Annual Security Cameras & Alarms | 5 |  |  | 200000 | 238040
9999 | District Wide |  | ATH | MAINT | Annual Sound System Repairs ($75,000 Annually) | 5 |  |  | 150000 | 178530
9999 | District Wide |  | FIN | FIN | Annual Technology and Equipment (Incl Student Computers) | 5 |  |  | 19491113 | 23198322.6926
9999 | District Wide |  | FIN | FIN | Annual Telecommunications Repairs Projects (Small) | 5 |  |  | 1949090 | 2319806.918
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - Elementary site #2 in Wiregrass | 5 |  |  | 750000 | 892650
9999 | District Wide |  | ATH | MAINT | Annual Athletic Court Maint 5 Year Rotation ($150,000 Annually) | 6 |  |  | 300000 | 372930
9999 | District Wide |  | ATH | MAINT | Annual Bleacher Repair ($100,000 Annually) | 6 |  |  | 200000 | 248620
9999 | District Wide |  | FIN | FIN | Annual Buses & Other Vehicles | 6 |  |  | 5491238 | 6826157.9578
9999 | District Wide |  | FIN | FIN | Annual Compliance w/Environmental Reg | 6 |  |  | 514487 | 639558.7897
10004 | District Wide |  | FIN | FIN | Annual Compliance with ADA | 6 |  |  | 300000 | 372930 |  |  | Added at the request of CS&CC
9999 | District Wide |  | FIN | FIN | Annual Debt Service Payments | 6 |  |  | 50936250 | 50936250
9999 | District Wide |  | PRT | MAINT | Annual Exterior Paint 5 Yr. Rotation ($850,000 Annually) | 6 |  |  | 1700000 | 2113270
9999 | District Wide |  | PRT | MAINT | Annual Fire Alarm & Suppression Upgrades ($200,000 Annually) | 6 |  |  | 400000 | 497240
9999 | District Wide |  | PRT | CS&CC | Annual Fire Loop / Hydrants ($500,000 Annually) | 6 |  |  | 1000000 | 1243100
9999 | District Wide |  | PRT | MAINT | Annual Flooring Replacement | 6 |  |  | 600000 | 745860
9999 | District Wide |  | ATH | ATH | Annual Gym Wood Floor Annual Maintenance ($60,000 Annually) | 6 |  |  | 120000 | 149172
9999 | District Wide |  | PRT | MAINT | Annual HVAC Equipment Replacements ($250,000 Annually) | 6 |  |  | 500000 | 621550
9999 | District Wide |  | PRT | MAINT | Annual Lift Station Upgrades ($100,000 Annually) | 6 |  |  | 200000 | 248620
9999 | District Wide |  | FIN | FIN | Annual Maintenance & Repairs Projects (Small) | 6 |  |  | 3086924 | 3837355.2244
9999 | District Wide |  | FIN | FIN | Annual Maintenance Health & Safety | 6 |  |  | 514487 | 639558.7897
9999 | District Wide |  | PRT | MAINT | Annual Marquee Sign Replacements ($15,000 Annually) | 6 |  |  | 30000 | 37293
9999 | District Wide |  | PRT | MAINT | Annual Pavement Maintenance 5 Yr. Rotation ($500,000 Annually) | 6 |  |  | 1000000 | 1243100
9999 | District Wide |  | PRT | MAINT | Annual Physical Education Equipment Replacements ($200,000 Annually) | 6 |  |  | 400000 | 497240
9999 | District Wide |  | PRT | MAINT | Annual Portable Maintenance & Moving ($100,000 Annually) | 6 |  |  | 200000 | 248620
9999 | District Wide |  | PRT | MAINT | Annual Security Cameras & Alarms | 6 |  |  | 200000 | 248620
9999 | District Wide |  | ATH | MAINT | Annual Sound System Repairs ($75,000 Annually) | 6 |  |  | 150000 | 186465
9999 | District Wide |  | FIN | FIN | Annual Technology and Equipment (Incl Student Computers) | 6 |  |  | 20075846 | 24956284.1626
9999 | District Wide |  | FIN | FIN | Annual Telecommunications Repairs Projects (Small) | 6 |  |  | 2118477 | 2633478.7587
9999 | District Wide |  | PLAN | PLAN | Property Acquisition - Elementary site #3 in Wiregrass | 6 |  |  | 750000 | 932325
0084 | Double Branch ES | 2007 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
0084 | Double Branch ES | 2007 | FNS | FNS | Cooler / Freezer & Serving Line | 6 |  |  | 583619 | 725496.7789
0084 | Double Branch ES | 2007 | PRT | CS&CC | Traffic Safety and Parking Improvements - Add Turn Lane to Chauncey | 6 |  |  | 500000 | 621550
0086 | Dr. John Long MS | 2006 | PRT | CS&CC | Addition - Classroom Wing | 3 |  |  | 4000000 | 4363600
0086 | Dr. John Long MS | 2006 | ATH | ATH | Sand & Paint Gym Floors | 3 |  |  | 25000 | 27272.5
0086 | Dr. John Long MS | 2006 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0114 | Fivay HS | 2010 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0351 | Fox Hollow ES | 1990 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0351 | Fox Hollow ES | 1990 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0351 | Fox Hollow ES | 1990 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
0351 | Fox Hollow ES | 1990 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel Automotive Technology | 2 |  |  | 1500000 | 1566750
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel Carpentry & Vet Assisting Program to HVAC Program | 2 |  |  | 700000 | 731150
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel Commercial Art Room | 2 |  |  | 110000 | 114895
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel Cosmetology Room | 2 |  |  | 1007000 | 1051811.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel Culinary Arts Room | 2 |  |  | 1200000 | 1253400
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel Electricity Room | 2 |  |  | 415000 | 433467.5
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel HVAC Program Room | 2 |  |  | 530000 | 553585
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel Marine Service Technology Program | 2 |  |  | 300000 | 313350
0991 | Fred K. Marchman EC | 1984 | PRT | CS&CC | Remodel School | 2 |  |  | 518529 | 541603.5405
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Remodel TV Production Space | 2 |  |  | 80000 | 83560
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Renovate Autobody Repair Bld., New Paint Booth, Paint Mixing Room, Frame Straightener, Welding Booth | 2 |  |  | 500000 | 522250
0991 | Fred K. Marchman EC | 1984 | CCTE | CS&CC | Sign - New Marquee | 2 |  |  | 7000 | 7311.5
0991 | Fred K. Marchman EC | 1984 | PRT | MAINT | Roof Replacement | 4 |  |  | 250000 | 284875
0083 | Gulf Highlands ES | 2006 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0083 | Gulf Highlands ES | 2006 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
0083 | Gulf Highlands ES | 2006 | FNS | FNS | Cooler / Freezer & Serving Line | 6 |  |  | 583619 | 725496.7789
0331 | Gulf HS | 1971 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 150000 | 150000 |  | On Hold
0331 | Gulf HS | 1971 | PRT | CS&CC | Remodel School Phase 1 - Bld #1 | 2 |  |  | 9150000 | 9557175
0331 | Gulf HS | 1971 | PRT | CS&CC | Remodel School Phase 2 | 2 |  |  | 2514150 | 2626029.675
0331 | Gulf HS | 1971 | ATH | ATH | Scoreboard Replacement(s) | 2 |  |  | 40000 | 41780
0331 | Gulf HS | 1971 | ATH | MAINT | Fencing - Baseball Field | 3 |  |  | 20000 | 21818
0331 | Gulf HS | 1971 | ATH | MAINT | Fencing - Tennis Court Fence | 3 |  |  | 15000 | 16363.5 |  |  | Phil will check to see if need to move up in priority
0331 | Gulf HS | 1971 | ATH | MAINT | Replace Wall Tile In PE Locker Room | 4 |  |  | 15000 | 17092.5
0331 | Gulf HS | 1971 | ATH | CS&CC | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 |  |  | 2500000 | 2975500
0331 | Gulf HS | 1971 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 800000 | 952160
0331 | Gulf HS | 1971 | PRT | MAINT | Replace Quarry Tile throughout campus | 6 |  |  | 355000 | 441300.5
0261 | Gulf MS | 1964 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0261 | Gulf MS | 1964 | PRT | MAINT | Renovate Restroom Bld #17 | 2 |  |  | 100000 | 104450
0261 | Gulf MS | 1964 | FNS | MAINT | Kitchen Renovation Flooring, Paint, Ovens, Steamers | 3 |  |  | 120329 | 131266.9061
0261 | Gulf MS | 1964 | PRT | CS&CC | Remodel School Bld 1, 2, 3, 9. 10, 11, 14 | 3 |  |  | 8653000 | 9439557.7
0261 | Gulf MS | 1964 | ATH | ATH | Sand & Paint Gym Floors | 4 |  |  | 25000 | 28487.5
0261 | Gulf MS | 1964 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 650000 | 773630
0261 | Gulf MS | 1964 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0093 | Gulf Trace ES | 2008 | FNS | FNS | Cooler / Freezer & Serving Line | 6 |  |  | 641980 | 798045.338
0911 | Gulfside ES | 1977 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0911 | Gulfside ES | 1977 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 425000 | 443912.5
0911 | Gulfside ES | 1977 | PRT | CS&CC | Remodel Bld #1 & 2 Parking And Traffic Improvements | 4 |  |  | 2500000 | 2848750
0911 | Gulfside ES | 1977 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 204750 | 243693.45
0911 | Gulfside ES | 1977 | SCHOOL | CS&CC | Covered Walkways - 224' each side of school | 6 | [5 empty] | New
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC | Determine Long Range Use | 5 |  |  |  | 0
0242 | Harry Schwettman EC | 1923 | PRT | CS&CC | Remodel School | 5 |  |  | 266999 | 317782.2098
0242 | Harry Schwettman EC | 1923 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0301 | Hudson ES | 1966 | FNS | MAINT | Kitchen Floor Renovation | 2 |  |  | 35280 | 36849.96
0301 | Hudson ES | 1966 | PRT | CS&CC | Remodel Restrooms ADA | 2 |  |  | 700000 | 731150
0301 | Hudson ES | 1966 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 425000 | 443912.5
0302 | Hudson ES | 1967 | PRT | CS&CC | Remodel Bld #1 | 3 |  |  | 400000 | 436360
0301 | Hudson ES | 1966 | FNS | CS&CC | Remodel Kitchen And Serving Line | 3 |  |  | 779738 | 850616.1842
0301 | Hudson ES | 1966 | FNS | FNS | Cooler / Freezer | 4 |  |  | 73371 | 83606.2545
0521 | Hudson HS | 1973 | FNS | CS&CC | Kitchen Renovation - Phase 2 | 1 |  |  | 892462.725 | 892462.725 |  | On Hold | Pending Kelley School Renovation
0521 | Hudson HS | 1973 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 150000 | 150000 |  | On Hold
0521 | Hudson HS | 1973 | ATH | CS&CC | Concession Stand Bathrooms - Baseball/Softball | 2 |  |  | 250000 | 261125
0521 | Hudson HS | 1973 | ATH | CS&CC | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 2 |  |  | 2500000 | 2611250
0521 | Hudson HS | 1973 | ATH | CS&CC | Renovate/Build Athletic Field House | 2 |  |  | 1000000 | 1044500
0521 | Hudson HS | 1973 | ATH | MAINT | Fencing - Perimeter | 3 |  |  | 20000 | 21818
0521 | Hudson HS | 1973 | PRT | CS&CC | Remodel School - Kelley School | 4 |  |  | 19100000 | 21764450
0521 | Hudson HS | 1973 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 800000 | 911600
0521 | Hudson HS | 1973 | ATH | ATH | Track Overlay | 4 |  |  | 50000 | 56975
0521 | Hudson HS | 1973 | PRT | CS&CC | Traffic Safety and Parking Improvements | 4 |  |  | 860000 | 979970
0521 | Hudson HS | 1973 | CCTE | CS&CC | Agriculture Barn for Vet Assisting Program | 6 |  |  | 50000 | 62155
0521 | Hudson HS | 1973 | SCHOOL | CS&CC | Covered Walkways - Bus Loop | 6 |  |  | 100000 | 124310
0951 | Hudson MS | 1984 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0951 | Hudson MS | 1984 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 650000 | 678925
0073 | J.W. Mitchell HS | 2000 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 150000 | 150000 |  | On Hold
0073 | J.W. Mitchell HS | 2000 | ATH | CS&CC | Refurbish Football Field Elevation and Field Drainage | 3 |  |  | 320000 | 349088
0073 | J.W. Mitchell HS | 2000 | ATH | MAINT | Storage Garage | 4 |  |  | 25000 | 28487.5
0073 | J.W. Mitchell HS | 2000 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 800000 | 952160
0073 | J.W. Mitchell HS | 2000 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 150000 | 186465
7071 | James Irvin EC | 1995 | CCTE | CS&CC | Redevelopment of Campus | 1 |  |  | 5000000 | 5000000
7071 | James Irvin EC | 1995 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 135600 | 168564.36
0065 | James M. Marlowe ES | 1998 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0065 | James M. Marlowe ES | 1999 | PRT | MAINT | Roof Maintenance | 3 |  |  | 80000 | 87272
0065 | James M. Marlowe ES | 1999 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 195000 | 232089
0065 | James M. Marlowe ES | 1999 | FNS | FNS | Cooler / Freezer | 5 |  |  | 80709 | 96059.8518
0065 | James M. Marlowe ES | 1999 | FNS | CS&CC | Serving Line Renovation | 5 |  |  | 381751 | 454360.0402
0321 | Lacoochee ES | 1971 | FNS | FNS | Kitchen Hood | 2 |  |  | 60775 | 63479.4875
0321 | Lacoochee ES | 1971 | FNS | CS&CC | Kitchen Renovation | 2 |  |  | 708852 | 740395.914
0321 | Lacoochee ES | 1971 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 425000 | 443912.5
0321 | Lacoochee ES | 1971 | PRT | CS&CC | Remodel Classroom Bld #8,9,11,12,13 | 3 |  |  | 1348655 | 1471247.7395
0961 | Lake Myrtle ES | 1984 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0961 | Lake Myrtle ES | 1984 | FNS | FNS | Serving Line Update - from RES | 4 |  |  | 7383 | 8412.9285
0961 | Lake Myrtle ES | 1984 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 425000 | 484287.5
0961 | Lake Myrtle ES | 1984 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 204750 | 243693.45
0801 | Land O' Lakes HS | 1973 | PRT | CS&CC | Remodel School - Kelley School + Add Capacity | 1 |  | Penny | 20600000 | 20600000
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC | Cooler / Freezer with Renovations | 2 |  |  | 203963 | 213039.3535
0801 | Land O' Lakes HS | 1973 | ATH | MAINT | Lighting - Replace Baseball Field | 2 |  |  | 100000 | 104450
0801 | Land O' Lakes HS | 1973 | FNS | CS&CC | Serving Line Renovation | 2 |  |  | 981708.9975 | 1025395.0479
0801 | Land O' Lakes HS | 1973 | ATH | MAINT | Fencing - Tennis | 3 |  |  | 15000 | 16363.5
0801 | Land O' Lakes HS | 1973 | PRT | MAINT | Roof Replacement | 4 |  |  | 600000 | 683700
0801 | Land O' Lakes HS | 1973 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 800000 | 911600
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC | Concession Stand Bathrooms - Baseball/Softball | 5 |  |  | 250000 | 297550
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 |  |  | 2500000 | 2975500
0801 | Land O' Lakes HS | 1973 | ATH | CS&CC | Renovate/Build Athletic Field House | 5 |  |  | 1500000 | 1785300
2081 | Longleaf ES | 2005 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
2081 | Longleaf ES | 2005 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
2081 | Longleaf ES | 2005 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 425000 | 505835
2081 | Longleaf ES | 2005 | FNS | FNS | Cooler / Freezer & Serving Line | 6 |  |  | 530562 | 659541.6222
0451 | Mary Giella ES | 1989 | SCHOOL | MAINT | Fencing - Clear Line and Install 6' Chain Link Fence on Bus Loop Side | 1 |  |  | 25000 | 25000 |  | New
0451 | Mary Giella ES | 1989 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0451 | Mary Giella ES | 1989 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 204750 | 243693.45
0451 | Mary Giella ES | 1989 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 425000 | 505835
0451 | Mary Giella ES | 1989 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 110000 | 136741
0211 | Mittye P. Locke ES | 1966 | PRT | CS&CC | Fire Egress Remodeling to Pre-K Building | 1 |  |  | 20000 | 20000 |  | TBD | Pre-K moving to Richey Elem?
0211 | Mittye P. Locke ES | 1966 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0211 | Mittye P. Locke ES | 1966 | FNS | CS&CC | Kitchen Renovation | 2 |  |  | 708852 | 740395.914
0211 | Mittye P. Locke ES | 1966 | PRT | CS&CC | Remodel School, Replace Covered Walks, Traffic Improvements | 3 |  |  | 8000000 | 8727200
0941 | Moon Lake ES | 1982 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0941 | Moon Lake ES | 1982 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0941 | Moon Lake ES | 1982 | FNS | CS&CC | A/C Renovation To Kitchen | 2 |  |  | 204750 | 213861.375
0941 | Moon Lake ES | 1982 | FNS | CS&CC | Serving Line Renovation | 2 |  |  | 286815 | 299578.2675
0941 | Moon Lake ES | 1982 | PRT | CS&CC | Remodel Bld #1 | 4 |  |  | 5539200 | 6311918.4
0941 | Moon Lake ES | 1982 | PRT | CS&CC | Traffic Safety and Parking Improvements | 4 |  |  | 758000 | 863741
0081 | Moore Mickens EC | 1952 | PRT | CS&CC | Redevelopment of Campus | 1 |  |  | 5000000 | 5000000 |  | On Hold
9999 | New Elementary School |  | PLAN | CS&CC | Elementary W - Wiregrass | 2 |  |  | 18000000 | 18801000
9999 | New Elementary School |  | PLAN | CS&CC | Elementary U - Northwood | 5 |  |  | 18597372 | 22134592.1544
9999 | New Elementary School |  | PLAN | CS&CC | Elementary Q - 54 Corridor near Suncoast Parkway | 6 |  |  | 20121372 | 25012877.5332
0092 | New River ES | 2007 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
0092 | New River ES | 2007 | FNS | FNS | Cooler / Freezer & Serving Line | 6 |  |  | 641980 | 798045.338
0501 | Northwest ES | 1973 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0501 | Northwest ES | 1973 | FNS | MAINT | Kitchen Floor Renovation | 2 |  |  | 35280 | 36849.96
0501 | Northwest ES | 1973 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
0501 | Northwest ES | 1973 | FNS | FNS | Kitchen Hood | 4 |  |  | 73538 | 83796.551
0501 | Northwest ES | 1973 | PRT | CS&CC | Remodel School - Kelley School | 4 |  |  | 7000000 | 7976500
0501 | Northwest ES | 1973 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 419926 | 522010.0106
0082 | Oakstead ES | 2006 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
0082 | Oakstead ES | 2006 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0082 | Oakstead ES | 2006 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 419926 | 522010.0106
0061 | Pasco ES | 1954 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0061 | Pasco ES | 1954 | PRT | CS&CC | Renovate Bld #1-7, #9, #20, #21, #41 | 2 |  |  | 5614560 | 5864407.92 |  |  | added Bld 9 to include cafeteria serving line renovation
0061 | Pasco ES | 1954 | FNS | FNS | Cooler / Freezer | 5 |  |  | 80709 | 96059.8518
0031 | Pasco HS | 1964 | ATH | MAINT | Lighting - Replace Baseball Field | 2 |  |  | 100000 | 104450
0031 | Pasco HS | 1964 | ATH | CS&CC | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 2 |  |  | 2500000 | 2611250
0031 | Pasco HS | 1964 | FNS | FNS | Cooler / Freezer | 5 |  |  | 80709 | 96059.8518
0031 | Pasco HS | 1964 | FNS | CS&CC | Serving Line Renovation | 5 |  |  | 1079880 | 1285273.176
0071 | Pasco MS | 1946 | PRT | MAINT | LCD Projector installation - CCTE Building | 1 |  |  | 10000 | 10000 |  | On Hold
0071 | Pasco MS | 1946 | ATH | CS&CC | Replace Gym Floor | 5 |  |  | 175000 | 208285 |  |  | Gym Floor Synthetic Overlay just complete - does that replace this project?
0089 | Paul R. Smith MS | 2006 | ATH | ATH | Sand & Paint Gym Floors | 3 |  |  | 25000 | 27272.5
0089 | Paul R. Smith MS | 2006 | FNS | FNS | Outside Dining Sun Shade | 6 |  |  | 10000 | 12431
0089 | Paul R. Smith MS | 2006 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0902 | Pine View ES | 2003 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
0902 | Pine View ES | 2003 | PRT | MAINT | Roof Maintenance | 5 |  |  | 80000 | 95216
0902 | Pine View ES | 2003 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 425000 | 505835
0902 | Pine View ES | 2003 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0902 | Pine View ES | 2003 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 30000 | 37293
0902 | Pine View ES | 2003 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 419926 | 522010.0106
0921 | Pine View MS | 1977 | ATH | MAINT | Overlay Outdoor Courts | 2 |  |  | 30000 | 31335
0921 | Pine View MS | 1977 | ATH | ATH | Track Overlay | 2 |  |  | 40000 | 41780
0921 | Pine View MS | 1977 | PRT | CS&CC | Remodel School | 5 |  |  | 15930180 | 18960100.236
0921 | Pine View MS | 1977 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 800000 | 952160
0921 | Pine View MS | 1977 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0921 | Pine View MS | 1977 | SCHOOL | CS&CC | Covered Walkways - ESE | 6 |  |  | 406000 | 504698.6
0921 | Pine View MS | 1977 | SCHOOL | CS&CC | Covered Walkways - Bus Loop | 6 |  |  | 550000 | 683705
0921 | Pine View MS | 1977 | SCHOOL | CS&CC | Covered Walkways - Car Loop | 6 |  |  | 418000 | 519615.8
0902 | Pineview ES | 2003 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0361 | Quail Hollow ES | 1975 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0361 | Quail Hollow ES | 1975 | PRT | CS&CC | Remodel School - Kelley School + Add Capacity | 1 |  | Penny | 10500000 | 10500000
0361 | Quail Hollow ES | 1975 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
0361 | Quail Hollow ES | 1975 | PRT | MAINT | Roof Replacement | 5 |  |  | 600000 | 714120
0361 | Quail Hollow ES | 1975 | FNS | CS&CC | A/C Renovation To Kitchen | 6 |  |  | 204750 | 254524.725
0361 | Quail Hollow ES | 1975 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0361 | Quail Hollow ES | 1975 | SCHOOL | MAINT | Covered Walkways | 6 |  |  | 55000 | 68370.5
0361 | Quail Hollow ES | 1975 | FNS | CS&CC | Kitchen Renovation | 6 |  |  | 1037831 | 1290127.7161
0361 | Quail Hollow ES | 1975 | PRT | CS&CC | Traffic Safety and Parking Improvements | 6 |  |  | 210000 | 261051
0021 | R. B. Cox ES | 1925 | PRT | CS&CC | Remodel School - Build New Cafeteria, Tear Down Old Cafeteria, Remove Concrete Portables, Traffic And Parking Improvements, Replace Remaining Old Windows, Install Securtiy System | 2 |  |  | 6510441 | 6800155.6245
0021 | R. B. Cox ES | 1925 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
0102 | R.B. Stewart MS | 1926 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0102 | R.B. Stewart MS | 1926 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0931 | Ridgewood HS | 1977 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 800000 | 800000 |  |  | IS needs to prioritze
0931 | Ridgewood HS | 1977 | ATH | MAINT | Lighting - Replace Baseball Field | 2 |  |  | 100000 | 104450
0931 | Ridgewood HS | 1977 | ATH | ATH | Scoreboard Replacement(s) | 2 |  |  | 25000 | 26112.5
0931 | Ridgewood HS | 1977 | PRT | CS&CC | Remodel Bld #1 | 3 |  |  | 9000000 | 9818100
0931 | Ridgewood HS | 1977 | CCTE | CS&CC | Remodel Technology Lab - Room 404 | 3 |  |  | 300000 | 327270
0931 | Ridgewood HS | 1977 | ATH | MAINT | Replace Wall Tile In PE Locker Room | 3 |  |  | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | ATH | Scoreboard Replacement(s) | 3 |  |  | 25000 | 27272.5
0931 | Ridgewood HS | 1977 | ATH | MAINT | Tennis Court Renovation | 3 |  |  | 250000 | 272725
0931 | Ridgewood HS | 1977 | ATH | ATH | Sand & Paint Gym Floors | 4 |  |  | 60000 | 68370
0931 | Ridgewood HS | 1977 | ATH | ATH | Track Overlay | 4 |  |  | 50000 | 56975
0931 | Ridgewood HS | 1977 | PRT | MAINT | Roof Replacement | 5 |  |  | 400000 | 476080
0931 | Ridgewood HS | 1977 | ATH | CS&CC | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 6 |  |  | 2500000 | 3107750
0471 | River Ridge HS | 1990 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 150000 | 150000 |  | On Hold
0471 | River Ridge HS | 1990 | CCTE | MAINT | Open Doorway Between Engineering Rooms | 1 |  |  | 50000 | 50000 |  | Hold | Olga will speak with Rob
0471 | River Ridge HS | 1990 | PRT | CS&CC | Remodel Restrooms ADA | 2 |  |  | 700000 | 731150
0471 | River Ridge HS | 1990 | ATH | MAINT | Fencing - Tennis | 3 |  |  | 30000 | 32727
0471 | River Ridge HS | 1990 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 800000 | 872720
0471 | River Ridge HS | 1990 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 300000 | 372930
0472 | River Ridge MS | 1990 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0472 | River Ridge MS | 1990 | PRT | CS&CC | Remodel Restrooms ADA | 2 |  |  | 700000 | 731150
0472 | River Ridge MS | 1990 | CCTE | CS&CC | Remodel Technology Education Space for PLTW Curriculum | 2 |  |  | 160000 | 167120
0472 | River Ridge MS | 1990 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 650000 | 709085
0472 | River Ridge MS | 1990 | ATH | MAINT | Overlay Middle School Track | 4 |  |  | 50000 | 56975
0472 | River Ridge MS | 1990 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 166000 | 206354.6
0251 | San Antonio ES | 1981 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0251 | San Antonio ES | 1981 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0251 | San Antonio ES | 1981 | PRT | CS&CC | HVAC Upgrade - Phase 2 | 2 |  |  | 1200000 | 1253400
0251 | San Antonio ES | 1981 | PRT | CS&CC | Remodel Bld #1 #2 #10 | 2 |  |  | 3965541 | 4142007.5745
2061 | Sand Pine ES | 1998 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
2061 | Sand Pine ES | 1998 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 425000 | 443912.5
2061 | Sand Pine ES | 1998 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 195000 | 232089
2061 | Sand Pine ES | 1998 | FNS | CS&CC | Serving Line Renovation | 5 |  |  | 381751 | 454360.0402
2061 | Sand Pine ES | 1998 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
2061 | Sand Pine ES | 1998 | SCHOOL | MAINT | Covered Walkways | 6 |  |  | 13000 | 16160.3
0341 | Schrader ES | 1972 | PRT | MAINT | LCD Projector Installation - Bld #9 | 1 |  |  | 40000 | 40000 |  | On Hold
0341 | Schrader ES | 1972 | IS | IS | Technology Infrastructure Upgrades | 3 |  |  | 425000 | 463632.5
2091 | Seven Oaks ES | 2005 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
2091 | Seven Oaks ES | 2005 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
2091 | Seven Oaks ES | 2005 | FNS | FNS | Cooler / Freezer & Serving Line | 6 |  |  | 530562 | 659541.6222
0411 | Seven Springs ES | 1987 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0411 | Seven Springs ES | 1987 | FNS | CS&CC | Serving Line Renovation | 4 |  |  | 347047 | 395460.0565
0411 | Seven Springs ES | 1987 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 425000 | 484287.5
0411 | Seven Springs ES | 1987 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 204750 | 243693.45
0411 | Seven Springs ES | 1987 | FNS | CS&CC | Cooler / Freezer with Renovations | 6 |  |  | 340000 | 422654
0411 | Seven Springs ES | 1987 | SCHOOL | MAINT | Covered Walkways | 6 |  |  | 28980 | 36025.038
0057 | Seven Springs MS | 1995 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0057 | Seven Springs MS | 1995 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 650000 | 650000 |  |  | IS needs to prioritze
0057 | Seven Springs MS | 1995 | ATH | MAINT | Sound Panel Refurb In Gym | 2 |  |  | 75000 | 78337.5 |  |  | Phil checking to see if need to bump up in priority
0057 | Seven Springs MS | 1995 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 80000 | 99448
0601 | Shady Hills ES | 1973 | PRT | CS&CC | Remodel School - Kelley School + Add Capacity | 1 |  | Penny | 10500000 | 10500000
0601 | Shady Hills ES | 1973 | PRT | CS&CC | Traffic Safety and Parking Improvements | 1 |  |  | 700000 | 700000 |  | Design
0601 | Shady Hills ES | 1973 | FNS | FNS | Stock Room Renovation | 2 |  |  | 10000 | 10445
0601 | Shady Hills ES | 1973 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 425000 | 443912.5
0601 | Shady Hills ES | 1973 | FNS | FNS | Kitchen Hood | 4 |  |  | 73538 | 83796.551
0601 | Shady Hills ES | 1973 | FNS | CS&CC | Serving Line Renovation | 5 |  |  | 381751 | 454360.0402
0101 | Sunlake HS | 2007 | ATH | ATH | Sand & Paint Gym Floors | 5 |  |  | 25000 | 29755
0101 | Sunlake HS | 2007 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0072 | Sunray ES | 2000 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0072 | Sunray ES | 2000 | PRT | MAINT | Roof Maintenance | 3 |  |  | 80000 | 87272
0072 | Sunray ES | 2000 | FNS | CS&CC | A/C Renovation To Kitchen | 5 |  |  | 195000 | 232089
0072 | Sunray ES | 2000 | FNS | CS&CC | Serving Line Renovation | 5 |  |  | 381751 | 454360.0402
0072 | Sunray ES | 2000 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 425000 | 505835
0072 | Sunray ES | 2000 | SCHOOL | MAINT | Covered Walkways | 6 |  |  | 30000 | 37293
0461 | Thomas E. Weightman MS | 1990 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 125000 | 125000 |  | On Hold
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT | Fencing - Tennis Court Fence | 3 |  |  | 20000 | 21818 |  |  | Phil Bell will check to see if need to move up in priority
0461 | Thomas E. Weightman MS | 1990 | ATH | MAINT | Overlay Courts | 3 |  |  | 80000 | 87272
0461 | Thomas E. Weightman MS | 1990 | FNS | FNS | Cooler / Freezer | 5 |  |  | 80709 | 96059.8518
0461 | Thomas E. Weightman MS | 1990 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 194400 | 241658.64
0461 | Thomas E. Weightman MS | 1990 | PRT | CS&CC | Traffic Safety and Parking Improvements | 6 |  |  | 540000 | 671274
9032 | Transportation E | 1972 | PRT | CS&CC | Remodel Interior | 5 |  |  | 250000 | 297550
9035 | Transportation NW | 1979 | PRT | CS&CC | Remodel Office Interior, Add Parking | 5 |  |  | 2500000 | 2975500
9999 | Transportation SW |  | PRT | CS&CC | Construction of New Facility | 5 |  |  | 5500000 | 6546100
9033 | Transportation W | 1971 | PRT | CS&CC | Remodel Interior, Add Paint Booth, Expand Parking | 5 |  |  | 650000 | 773630
0032 | Trinity ES | 2000 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000 |  | On Hold
0032 | Trinity ES | 2000 | FNS | MAINT | Renovate Kitchen Floors | 1 |  |  | 75000 | 75000 |  | Need funding
0032 | Trinity ES | 2000 | PRT | MAINT | Roof Maintenance | 4 |  |  | 80000 | 91160
0032 | Trinity ES | 2000 | IS | IS | Technology Infrastructure Upgrades | 5 |  |  | 425000 | 505835
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC | A/C Renovation To Kitchen | 4 |  |  | 195000 | 222202.5
0085 | Trinity Oaks ES | 2007 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 419926 | 522010.0106
0110 | Veterans ES | 2008 | FNS | FNS | Cooler / Freezer & Serving Line | 6 |  |  | 706178 | 877849.8718
2071 | Wesley Chapel ES | 2002 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 425000 | 484287.5
0063 | Wesley Chapel HS | 1998 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 800000 | 835600
0063 | Wesley Chapel HS | 1998 | PRT | MAINT | Roof Maintenance | 4 |  |  | 100000 | 113950
0063 | Wesley Chapel HS | 1998 | SCHOOL | MAINT | Covered Walkways | 6 |  |  | 20000 | 24862
0091 | West Zephyrhills ES | 1958 | PRT | CS&CC | Remodel School - Tear Down Or Remodel Cafeteria Bld #2 Into Classrooms, Renovate Bld #1,3,4,5,8,9,14 | 1 |  |  | 8226665 | 8226665
0091 | West Zephyrhills ES | 1958 | IS | CS&CC | Technology Infrastructure Upgrades | 1 |  |  | 425000 | 425000 |  |  | IS needs to prioritze
0091 | West Zephyrhills ES | 1958 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 220000 | 273482
0090 | Wiregrass Ranch HS | 2006 | PRT | MAINT | LCD Projector Installation - audio only | 1 |  |  | 51000 | 51000 |  | On Hold
0090 | Wiregrass Ranch HS | 2006 | CCTE | CS&CC | Remodel/Expand Culinary Classroom | 2 |  |  | 420000 | 438690
0090 | Wiregrass Ranch HS | 2006 | PRT | CS&CC | Addition - Classroom Wing | 3 |  |  | 4000000 | 4363600
0090 | Wiregrass Ranch HS | 2006 | ATH | MAINT | Overlay Courts - Basketball & Tennis | 4 |  |  | 25000 | 28487.5
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH | Sand & Paint Gym Floors | 5 |  |  | 40000 | 47608
0090 | Wiregrass Ranch HS | 2006 | ATH | ATH | Scoreboard Replacement(s) | 5 |  |  | 75000 | 89265
0090 | Wiregrass Ranch HS | 2006 | FNS | FNS | Cooler / Freezer | 6 |  |  | 88779 | 110361.1749
0090 | Wiregrass Ranch HS | 2006 | FNS | CS&CC | Serving Line Renovation | 6 |  |  | 1187868 | 1476638.7108
0132 | Woodland ES | 1977 | PRT | MAINT | Fencing - Install Aluminum Weld Fence at Front Entrance and to Clinic | 1 |  |  | 21000 | 21000 |  | New
0132 | Woodland ES | 1977 | PRT | MAINT | LCD Projector Installation | 1 |  |  | 100000 | 100000
0132 | Woodland ES | 1977 | PRT | CS&CC | HVAC Upgrade - Phase 2 | 3 |  |  | 4447860 | 4852170.474
0132 | Woodland ES | 1977 | IS | IS | Technology Infrastructure Upgrades | 4 |  |  | 425000 | 484287.5
0132 | Woodland ES | 1977 | PRT | CS&CC | Remodel School, Expand Cafeteria | 5 |  |  | 4514705 | 5373401.891
0132 | Woodland ES | 1977 | SCHOOL | CS&CC | Covered Walkways | 6 |  |  | 432000 | 537019.2
0131 | Zephyrhills HS | 1973 | IS | IS | Technology Infrastructure Upgrades | 2 |  |  | 800000 | 835600
0131 | Zephyrhills HS | 1973 | CCTE | CS&CC | Remodel Automotive Technology To Lab Space/Convert To Health Academy | 3 |  |  | 560000 | 610904
0131 | Zephyrhills HS | 1973 | PRT | CS&CC | Remodel School - Kelley School + Add Capacity | 3 |  |  | 20600000 | 22472540
0131 | Zephyrhills HS | 1973 | FNS | FNS | Cooler / Freezer | 4 |  |  | 73371 | 83606.2545
0131 | Zephyrhills HS | 1973 | ATH | CS&CC | New Bleachers, Concession Stand, Public Restrooms, Male/Female Lockers | 5 |  |  | 2500000 | 2975500
0131 | Zephyrhills HS | 1973 | ATH | MAINT | Overlay Tennis Court | 5 |  |  | 50000 | 59510
Priority Code | Year | Escalator |  |  | Totals | All |  |  | 1024138723.7225 | 1093997916.7561
1 | 12/13 - 13/14 | 0% |  |  | Total for Priority 1 | 1 |  |  | 243780510.725 | 243780510.725
2 | 14/15 - 15/16 | 4.45% |  |  | Total for Priority 2 | 2 |  |  | 179460328.2475 | 184645554.989
3 | 16/17 - 17/18 | 9.09% |  |  | Total for Priority 3 | 3 |  |  | 160180037 | 170164442.9141
4 | 18/19 - 19/20 | 13.95% |  |  | Total for Priority 4 | 4 |  |  | 137878728 | 149501456.196
5 | 20/21 - 21/22 | 19.02% |  |  | Total for Priority 5 | 5 |  |  | 161392936.75 | 182456804.2196
6 | 22/23 - 23/24 | 24.31% |  |  | Total for Priority 6 | 6 |  |  | 141446183 | 163449147.7123
|  | = | 2012-2013 Budget Year Projects
|  | = | Penny for Pasco Projects